## CoverPage
EXPRO National Manual for Projects Management
Volume 6
BIM Level of Development Matrices
Document No. EPM-KE0-RG-000014 Rev 001

## Page2
Document Submittal History:
Revision: | Date: | Reason For Issue
000 | 21/02/2019 | For Use
001 | 15/08/2021 | For Use

## Page3
THIS NOTICE MUST ACCOMPANY EVERY COPY OF THIS DOCUMENT
IMPORTANT NOTICE
This document, (“Document”) is the exclusive property of the Government Expenditure and Projects Efficiency Authority. This Document should be read in its entirety including the terms of this Important Notice. The government entities may disclose this Document or extracts of this Document to their respective consultants and/or contractors, provided that such disclosure includes this Important Notice. Any use or reliance on this Document, or extracts thereof, by any party, including government entities and their respective consultants and/or contractors, is at that third party’s sole risk and responsibility. Government Expenditure and Projects Efficiency Authority, to the maximum extent permitted by law, disclaim all liability (including for losses or damages of whatsoever nature claimed on whatsoever basis including negligence or otherwise) to any third party howsoever arising with respect to or in connection with the use of this Document including any liability caused by negligent acts or omissions. This Document and its contents are valid only for the conditions reported in it and as of the date of this Document.

## General Matrix
BIM Level of Development Matrix - General
Model Element Author (MEA) | [19 empty] | Level of Development (LOD)
MEA | Discipline | [18 empty] | LOD 100 | The Model element may be graphically represented in the model with a symbol or other generic representation, but does not satisfy the requirements for LOD 200. Information related to the Model Element (i.e. Cost per square meter, tonnage of HVAC etc.) can be derived from othe Model Elements
A | Architectural | [18 empty] | LOD 200 | The Model Element is graphically represented within the Model as a generic system, object, or assembly with approximate quantities, size, shape, location and orientation. Non-graphic information may also be attached to the Model Element.
S | Structural | [18 empty] | LOD 300 | The Model Element is graphically represented within the Model as a specific system, object or assembly in terms of quantity, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element.
A/S | Architectural / Structural | [18 empty] | LOD 400 | The Model Element is graphically represented within the Model as a specific System, object or assmbly in terms of size, shape, location, quantity, and orientation with detailing, fabrication, assembly and installation information. Non-graphic information may also be attached to Model Element
A/M | Architectural / Mechanical | [18 empty] | LOD 500 | The Model is a field verified representation in terms of size, shape, location, quantity, and orientation. Non-graphic information may also be attached to the Model Elements.
M | Mechanical
E | Electrical
C | Civil
N/A | Not applicable
For model contents definitions for stages see EPM-KE0-PR-000010 - 3D Model Review Procedure
[20 empty] | Use on this project | This work is licensed under the Creative Commons Attribution-NonCommercial 4.0 International License Project stages redefined to Mashroat Design Review Procedure - EPM-KE0-PR-000002 |  |  |  |  | 30% Design Review |  |  | 60% Design Review |  |  | 90% Design Review
| Model Object Category | Cost Code | Cost Code Title | MasterFormat | MasterFormat Description | Uniformat [Uniformat II] | Uniformat Level | [6 empty] | Omniclass Level | [7 empty] | Relevant Attribute Tables | Model | Object | Data Information / | Stage |  |  | Stage |  |  | Stage |  |  | RECORD/ HANDOVER
[13 empty] | Table | [9 empty] | Element |  | Detailed Component | Date: |  |  | Date: |  |  | Date: |  |  | Date:
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  | Author(MEA) |  |  | LOD | MEA | Notes | LOD | MEA | Notes | LOD | MEA | Notes | LOD | MEA | Notes
[13 empty] | 36- | [7 empty] | INFORMATION
[13 empty] | 36- | 51 | [6 empty] | OFFICE RESOURCES
[13 empty] | 36- | 51 | 73 | [5 empty] | Office Model Templates
[13 empty] | 36- | 51 | 73 | 11 |  |  |  |  | Model Content
[13 empty] | 36- | 51 | 73 | 11 | 13 |  |  |  | Model Annotation Content
[13 empty] | 36- | 51 | 73 | 11 | 13 | 11 |  |  | Properties
[13 empty] | 36- | 51 | 73 | 11 | 13 | 11 | 19 |  | Zones/Rooms/Spaces
[13 empty] | 36- | 51 | 73 | 11 | 13 | 17 |  |  | Symbols
[13 empty] | 36- | 51 | 73 | 11 | 13 | 17 | 11 |  | Horizontal Grids
[13 empty] | 36- | 51 | 73 | 11 | 13 | 17 | 13 |  | Vertical Levels
[13 empty] | 21- | [7 empty] | ELEMENTS
| A. SUBSTRUCTURE | [5 empty] | A | [5 empty] | 21- | 1 | [6 empty] | SUBSTRUCTURE
[6 empty] | A10 | A | 10 |  |  |  |  | 21- | 1 | 1 | [5 empty] | Foundations | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete
[6 empty] | A1010 | A | 10 | 10 |  |  |  | 21- | 1 | 1 | 1 |  |  |  |  | Standard Foundations | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete | S | X | 0 | 200 | S |  | 200 | S |  | 300 | S |  | 300 | S
[6 empty] | A10100.10 | A | 10 | 10 | 0.1 |  |  | 21- | 1 | 1 | 1 | 1 |  |  |  | Wall Foundations | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete
[6 empty] | A10100.30 | A | 10 | 10 | 0.3 |  |  | 21- | 1 | 1 | 1 | 3 |  |  |  | Column Foundations | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete
[6 empty] | A10100.90 | A | 10 | 10 | 0.9 |  |  | 21- | 1 | 1 | 1 | 9 |  |  |  | Standard Foundation Supplementary Components
|  | 11.4 | PILES & CAISSONS | 31 60 00 | Special foundations and load bearing elements | A1020 | A | 10 | 20 |  |  |  | 21- | 1 | 1 | 2 |  |  |  |  | Special Foundations | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | A1020.01 | A | 10 | 20 | .01 |  |  | 21- | 1 | 1 | 2 | 1 |  |  |  | Driven Piles
[6 empty] | A1020.15 | A | 10 | 20 | .15 |  |  | 21- | 1 | 1 | 2 | 15 |  |  |  | Bored Piles
[6 empty] | A1020.20 | A | 10 | 20 | .20 |  |  | 21- | 1 | 1 | 2 | 2 |  |  |  | Caissons
[6 empty] | A1020.30 | A | 10 | 20 | .30 |  |  | 21- | 1 | 1 | 2 | 3 |  |  |  | Special Foundation Walls
[6 empty] | A1020.40 | A | 10 | 20 | .40 |  |  | 21- | 1 | 1 | 2 | 4 |  |  |  | Foundation Anchors
[6 empty] | A1020.50 | A | 10 | 20 | .50 |  |  | 21- | 1 | 1 | 2 | 5 |  |  |  | Underpinning
[6 empty] | A1020.60 | A | 10 | 20 | .60 |  |  | 21- | 1 | 1 | 2 | 6 |  |  |  | Raft Foundations
[6 empty] | A1020.70 | A | 10 | 20 | .70 |  |  | 21- | 1 | 1 | 2 | 7 |  |  |  | Pile Caps
[6 empty] | A1020.80 | A | 10 | 20 | .80 |  |  | 21- | 1 | 1 | 2 | 8 |  |  |  | Grade Beams | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | A20 | A | 20 |  |  |  |  | 21- | 1 | 2 | [5 empty] | Subgrade Enclosures | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete
[6 empty] | A2010 | A | 20 | 10 |  |  |  | 21- | 1 | 2 | 1 |  |  |  |  | Walls for Subgrade Enclosures | A, B Concrete; A, B Wood; A, B Masonry; A, B Precast Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | A2010.10 | A | 20 | 10 | .10 |  |  | 21- | 1 | 2 | 1 | 1 |  |  |  | Subgrade Enclosure Wall Construction
[6 empty] | A2010.20 | A | 20 | 10 | .20 |  |  | 21- | 1 | 2 | 1 | 2 |  |  |  | Subgrade Enclosure Wall Interior Skin
[6 empty] | A2010.90 | A | 20 | 10 | .90 |  |  | 21- | 1 | 2 | 1 | 9 |  |  |  | Subgrade Enclosure Wall Supplementary Components
[6 empty] | A40 | A | 40 |  |  |  |  | 21- | 1 | 4 | [5 empty] | Slabs-on-Grade | A, B - Str. Concrete
[6 empty] | A4010 | A | 40 | 10 |  |  |  | 21- | 1 | 4 | 1 |  |  |  |  | Standard Slabs-on-Grade | A, B Concrete
[6 empty] | A4020 | A | 40 | 20 |  |  |  | 21- | 1 | 4 | 2 |  |  |  |  | Structural Slabs-on-Grade | A, B Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | A4030 | A | 40 | 30 |  |  |  | 21- | 1 | 4 | 3 |  |  |  |  | Slab Trenches
[6 empty] | A4040 | A | 40 | 40 |  |  |  | 21- | 1 | 4 | 4 |  |  |  |  | Pits and Bases
[6 empty] | A4090 | A | 40 | 90 |  |  |  | 21- | 1 | 4 | 9 |  |  |  |  | SlabOn-Grade Supplementary Components
[6 empty] | A4090.10 | A | 40 | 90 | .10 |  |  | 21- | 1 | 4 | 9 | 1 |  |  |  | Perimeter Insulation
[6 empty] | A4090.20 | A | 40 | 90 | .20 |  |  | 21- | 1 | 4 | 9 | 2 |  |  |  | Vapor Retarder
[6 empty] | A4090.30 | A | 40 | 90 | .30 |  |  | 21- | 1 | 4 | 9 | 3 |  |  |  | Waterproofing
[6 empty] | A4090.40 | A | 40 | 90 | .40 |  |  | 21- | 1 | 4 | 9 | 4 |  |  |  | Mud Slab
[6 empty] | A4090.50 | A | 40 | 90 | .50 |  |  | 21- | 1 | 4 | 9 | 5 |  |  |  | Subbase Layer
[6 empty] | A60 | A | 60 |  |  |  |  | 21- | 1 | 6 | [5 empty] | Water and Gas Mitigation
[6 empty] | A6010 | A | 60 | 10 |  |  |  | 21- | 1 | 6 | 1 |  |  |  |  | Building Subdrainage
[6 empty] | A6010.10 | A | 60 | 10 | .10 |  |  | 21- | 1 | 6 | 1 | 1 |  |  |  | Foundation Drainage
[6 empty] | A6010.20 | A | 60 | 10 | .20 |  |  | 21- | 1 | 6 | 1 | 2 |  |  |  | Underslab Drainage
[6 empty] | A6020 | A | 60 | 20 |  |  |  | 21- | 1 | 6 | 2 |  |  |  |  | Off-Gassing Mitigation
[6 empty] | A6020.10 | A | 60 | 20 | .10 |  |  | 21- | 1 | 6 | 2 | 1 |  |  |  | Radon Mitigation
[6 empty] | A6020.20 | A | 60 | 20 | .20 |  |  | 21- | 1 | 6 | 2 | 2 |  |  |  | Maethane Mitigation
[6 empty] | A90 | A | 90 |  |  |  |  | 21- | 1 | 9 | [5 empty] | Substructure Related Activities
[6 empty] | A9010 | A | 90 | 10 |  |  |  | 21- | 1 | 9 | 1 |  |  |  |  | Substructure Excavation
[6 empty] | A9020 | A | 90 | 20 |  |  |  | 21- | 1 | 9 | 2 |  |  |  |  | Construction Dewatering
[6 empty] | A9030 | A | 90 | 30 |  |  |  | 21- | 1 | 9 | 3 |  |  |  |  | Excavation Support
[6 empty] | A9030.10 | A | 90 | 30 | .10 |  |  | 21- | 1 | 9 | 3 | 1 |  |  |  | Anchor Tiebacks
[6 empty] | A9030.20 | A | 90 | 30 | .20 |  |  | 21- | 1 | 9 | 3 | 2 |  |  |  | Cofferdams
[6 empty] | A9030.40 | A | 90 | 30 | .40 |  |  | 21- | 1 | 9 | 3 | 4 |  |  |  | Cribbing and Walers
[6 empty] | A9030.60 | A | 90 | 30 | .60 |  |  | 21- | 1 | 9 | 3 | 6 |  |  |  | Ground Freezing
[6 empty] | A9030.70 | A | 90 | 30 | .70 |  |  | 21- | 1 | 9 | 3 | 7 |  |  |  | Slurry Walls
[6 empty] | A9040 | A | 90 | 40 |  |  |  | 21- | 1 | 9 | 4 |  |  |  |  | Soil Treatment
| B. SHELL |  |  |  |  | B | B | [5 empty] | 21- | 2 | [6 empty] | SHELL
[6 empty] | B10 | B | 10 |  |  |  |  | 21- | 2 | 1 | [5 empty] | Superstructure
[6 empty] | B1010 | B | 10 | 10 |  |  |  | 21- | 2 | 1 | 1 |  |  |  |  | Floor Construction | A, B Cold Formed Metal Framing; A, B Masonry; A, B Metal Deck; A, B Precast Concrete; A,B Steel Joist; A, B Structural Steel; A, B Concrete; A, B Wood
|  | 12.8 | PRECAST CONCRETE (OFFSITE) | 03 40 00 | Precast Concrete | B1010.10 | B | 10 | 10 | .10 |  |  | 21- | 2 | 1 | 1 | 1 |  |  |  | Floor Structural Frame |  | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
|  | 12.8 | PRECAST CONCRETE (OFFSITE) | 03 40 00 | Precast Concrete | B1010.10 | B | 10 | 10 | .10 | .10 |  | 21- | 2 | 1 | 1 | 1 | 1 |  |  | Concrete | A, B Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
|  | 12.8 | PRECAST CONCRETE (OFFSITE) | 03 40 00 | Precast Concrete | B1010.10 | B | 10 | 10 | .10 | .11 |  | 21- | 2 | 1 | 1 | 1 | 11 |  |  | Precast Structural Inverted T Beam | A, B Precast Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
|  | 12.8 | PRECAST CONCRETE (OFFSITE) | 03 40 00 | Precast Concrete | B1010.10 | B | 10 | 10 | .10 | .12 |  | 21- | 2 | 1 | 1 | 1 | 12 |  |  | Precast Structural Column | A, B Precast Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
|  | 12.8 | PRECAST CONCRETE (OFFSITE) | 03 40 00 | Precast Concrete | B1010.10 | B | 10 | 10 | .10 | 0.2 |  | 21- | 2 | 1 | 1 | 1 | 2 |  |  | Masonry | A, B Masonry | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.10 | B | 10 | 10 | .10 | 0.3 |  | 21- | 2 | 1 | 1 | 1 | 3 |  |  | Steel Framing Columns | A, B Structural Steel | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.10 | B | 10 | 10 | .10 | 0.4 |  | 21- | 2 | 1 | 1 | 1 | 4 |  |  | Steel Framing Beams | A, B Structural Steel | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.10 | B | 10 | 10 | .10 | 0.5 |  | 21- | 2 | 1 | 1 | 1 | 5 |  |  | Steel Framing Bracing Rods | A, B Structural Steel | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.10 | B | 10 | 10 | .10 | 0.6 |  | 21- | 2 | 1 | 1 | 1 | 6 |  |  | Steel Joists | A,B Steel Joist | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.10 | B | 10 | 10 | .10 | 0.7 |  | 21- | 2 | 1 | 1 | 1 | 7 |  |  | Cold-Formed Metal Framing | A, B Cold Formed Metal Framing | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.10 | B | 10 | 10 | .10 | 0.8 |  | 21- | 2 | 1 | 1 | 1 | 8 |  |  | Wood Floor Trusses | A, B Wood | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.20 | B | 10 | 10 | .20 |  |  | 21- | 2 | 1 | 1 | 2 |  |  |  | Floor Decks, Slabs, and Toppings |  | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.20 | B | 10 | 10 | .20 | 0.1 |  | 21- | 2 | 1 | 1 | 2 | 1 |  |  | Wood Floor Deck | A, B Wood | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.20 | B | 10 | 10 | .20 | 0.2 |  | 21- | 2 | 1 | 1 | 2 | 2 |  |  | Metal Floor Deck | A, B Metal Deck | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.20 | B | 10 | 10 | .20 | 0.3 |  | 21- | 2 | 1 | 1 | 2 | 3 |  |  | Composite Floor Deck | A, B Structural Steel; A, B Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.20 | B | 10 | 10 | .20 | 0.4 |  | 21- | 2 | 1 | 1 | 2 | 4 |  |  | Concrete | A, B Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.20 | B | 10 | 10 | .20 | 0.41 |  | 21- | 2 | 1 | 1 | 2 | 41 |  |  | Precast Structural Double Tee | A, B Precast Concrete | A/S | X | 0 | 200 | A/S |  | 200 | A/S |  | 300 | A/S |  | 300 | A/S
[6 empty] | B1010.30 | B | 10 | 10 | .30 |  |  | 21- | 2 | 1 | 1 | 3 |  |  |  | Balcony Floor Construction
[6 empty] | B1010.40 | B | 10 | 10 | .40 |  |  | 21- | 2 | 1 | 1 | 4 |  |  |  | Mezzanine Floor Construction
[6 empty] | B1010.50 | B | 10 | 10 | .50 |  |  | 21- | 2 | 1 | 1 | 5 |  |  |  | Ramps
[6 empty] | B1010.90 | B | 10 | 10 | .90 |  |  | 21- | 2 | 1 | 1 | 9 |  |  |  | Floor Construction Supplementary Components
[6 empty] | B1020 | B | 10 | 20 |  |  |  | 21- | 2 | 1 | 2 |  |  |  |  | Roof Construction | A, B Cold Formed Metal Framing; A, B Masonry; A, B Metal Deck; A, B Precast Concrete; A,B Steel Joist; A, B Structural Steel; A, B Concrete; A, B Wood | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | B1020.10 | B | 10 | 20 | .10 |  |  | 21- | 2 | 1 | 2 | 1 |  |  |  | Roof Structural Frame | A, B Structural Steel; A, B Concrete; A,B Steel Joist
|  | 12.2 | METAL DECKING (Including Roof Deck) | 05 30 00 | Metal deck | B1020.20 | B | 10 | 20 | .20 |  |  | 21- | 2 | 1 | 2 | 2 |  |  |  | Roof Decks, Slabs, and Sheathing | A,B Steel Joist; A, B Metal Deck
[6 empty] | B1020.30 | B | 10 | 20 | .30 |  |  | 21- | 2 | 1 | 2 | 3 |  |  |  | Canopy Construction
[6 empty] | B1020.90 | B | 10 | 20 | .90 |  |  | 21- | 2 | 1 | 2 | 9 |  |  |  | Roof Construction Supplementary Components
[6 empty] | B1080 | B | 10 | 80 |  |  |  | 21- | 2 | 1 | 8 |  |  |  |  | Stairs | A, B Cold Formed Metal Framing; A, B Masonry; A, B Metal Deck; A, B Precast Concrete; A, B Structural Steel; A, B Concrete; A, B Wood | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
|  | 13.33 | Stair Treads | 05 55 00 | Metal Stair Treads and Nosings | B1080.10 | B | 10 | 80 | .10 |  |  | 21- | 2 | 1 | 8 | 1 |  |  |  | Stair Construction | A, B Structural Steel; A, B Precast Concrete; A, B Concrete
[6 empty] | B1080.30 | B | 10 | 80 | .30 |  |  | 21- | 2 | 1 | 8 | 3 |  |  |  | Stair Soffits
|  | 13.35 | Handrail & Toeplate | 05 52 00 | Pipe and Tube Railings | B1080.50 | B | 10 | 80 | .50 |  |  | 21- | 2 | 1 | 8 | 5 |  |  |  | Stair Railings | A, B Structural Steel; A, B Precast Concrete; A, B Concrete
[6 empty] | B1080.60 | B | 10 | 80 | .60 |  |  | 21- | 2 | 1 | 8 | 6 |  |  |  | Fire Escapes | A, B Structural Steel; A, B Precast Concrete; A, B Concrete
|  | 13.31 | Walkways & Platforms - Shop Assembled | 05 51 36 | Metal Walkways | B1080.70 | B | 10 | 80 | .70 |  |  | 21- | 2 | 1 | 8 | 7 |  |  |  | Metal Walkways | A, B Structural Steel; A, B Precast Concrete; A, B Concrete
|  | 13.36 | Ladders & Safety Cages | 05 51 33 | Metal Ladders | B1080.80 | B | 10 | 80 | .80 |  |  | 21- | 2 | 1 | 8 | 8 |  |  |  | Ladders | A, B Structural Steel
[6 empty] | B20 | B | 20 |  |  |  |  | 21- | 2 | 2 | [5 empty] | Exterior Vertical Enclosures
[6 empty] | B2010 | B | 20 | 10 |  |  |  | 21- | 2 | 2 | 1 |  |  |  |  | Exterior Walls | B – Ext. Wall | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
|  | 14.11 | Siding | 07 46 00 | Siding | B2010.10 | B | 20 | 10 | .10 |  |  | 21- | 2 | 2 | 1 | 1 |  |  |  | Exterior Wall Veneer | A, B Masonry | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | B2010.20 | B | 20 | 10 | .20 |  |  | 21- | 2 | 2 | 1 | 2 |  |  |  | Exterior Wall Construction | A, B Cold Formed Metal Framing; A, B Wood | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | B2010.20 | B | 20 | 10 | .20 | 0.1 |  | 21- | 2 | 2 | 1 | 2 | 1 |  |  | Exterior Walls - Wood |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | B2010.20 | B | 20 | 10 | .20 | 0.2 |  | 21- | 2 | 2 | 1 | 2 | 2 |  |  | Exterior Walls - Cold-Form Metal Framing |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | B2010.20 | B | 20 | 10 | .20 | 0.3 |  | 21- | 2 | 2 | 1 | 2 | 3 |  |  | Exterior Walls - Masonry |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | B2010.20 | B | 20 | 10 | .20 | 0.4 |  | 21- | 2 | 2 | 1 | 2 | 4 |  |  | Exterior Walls - Precast Concrete |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
|  | 14.41 | Partitions Lath & Plaster | 09 20 00 | Plaster and Gypsum Board | B2010.30 | B | 20 | 10 | .30 |  |  | 21- | 2 | 2 | 1 | 3 |  |  |  | Exterior Wall Interior Skin
[6 empty] | B2010.40 | B | 20 | 10 | .40 |  |  | 21- | 2 | 2 | 1 | 4 |  |  |  | Fabricated Exterior Wall Assemblies
[6 empty] | B2010.50 | B | 20 | 10 | .50 |  |  | 21- | 2 | 2 | 1 | 5 |  |  |  | Parapets |  | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
|  | 18.61 | Equipment Enclosures | 08 92 00 | Louvered Equipment Enclosures | B2010.60 | B | 20 | 10 | .60 |  |  | 21- | 2 | 2 | 1 | 6 |  |  |  | Equipment Screens |  | A | X | X | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | B2010.80 | B | 20 | 10 | .80 |  |  | 21- | 2 | 2 | 1 | 8 |  |  |  | Exterior Wall Supplementary Compomnents
[6 empty] | B2010.90 | B | 20 | 10 | .90 |  |  | 21- | 2 | 2 | 1 | 9 |  |  |  | Exterior Wall Opening Supplementary Compomnents
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | B2020 | B | 20 | 20 |  |  |  | 21- | 2 | 2 | 2 |  |  |  |  | Exterior Windows | B – Ext. Openings | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | B2020.10 | B | 20 | 20 | .10 |  |  | 21- | 2 | 2 | 2 | 1 |  |  |  | Exterior Operating Windows
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | B2020.20 | B | 20 | 20 | .20 |  |  | 21- | 2 | 2 | 2 | 2 |  |  |  | Exterior Fixed Windows
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | B2020.30 | B | 20 | 20 | .30 |  |  | 21- | 2 | 2 | 2 | 3 |  |  |  | Exterior Window Wall
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | B2020.50 | B | 20 | 20 | .50 |  |  | 21- | 2 | 2 | 2 | 5 |  |  |  | Exterior Special Function Windows
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | B2050 [B2030] | B | 20 | 50 |  |  |  | 21- | 2 | 2 | 5 |  |  |  |  | Exterior Doors and Grilles | B – Ext. Doors | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | B2050.10 | B | 20 | 50 | .10 |  |  | 21- | 2 | 2 | 5 | 1 |  |  |  | Exterior Entrance Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | B2050.20 | B | 20 | 50 | .20 |  |  | 21- | 2 | 2 | 5 | 2 |  |  |  | Exterior Utility Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | B2050.30 | B | 20 | 50 | .30 |  |  | 21- | 2 | 2 | 5 | 3 |  |  |  | Exterior Oversize Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | B2050.40 | B | 20 | 50 | .40 |  |  | 21- | 2 | 2 | 5 | 4 |  |  |  | Exterior Special Function Doors
[6 empty] | B2050.60 | B | 20 | 50 | .60 |  |  | 21- | 2 | 2 | 5 | 6 |  |  |  | Exterior Grilles
[6 empty] | B2050.70 | B | 20 | 50 | .70 |  |  | 21- | 2 | 2 | 5 | 7 |  |  |  | Exterior Gates
[6 empty] | B2050.90 | B | 20 | 50 | .90 |  |  | 21- | 2 | 2 | 5 | 9 |  |  |  | Exterior Door Supplementary Components
[6 empty] | B2070 | B | 20 | 70 |  |  |  | 21- | 2 | 2 | 7 |  |  |  |  | Exterior Louvers and Vents | B - Ext. Louvers and Vents | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | B2070.10 | B | 20 | 70 | .10 |  |  | 21- | 2 | 2 | 7 | 1 |  |  |  | Exterior Louvers
[6 empty] | B2070.50 | B | 20 | 70 | .50 |  |  | 21- | 2 | 2 | 7 | 5 |  |  |  | Exterior Vents
[6 empty] | B2080 | B | 20 | 80 |  |  |  | 21- | 2 | 2 | 8 |  |  |  |  | Exterior Wall Appurtenances
[6 empty] | B2080.10 | B | 20 | 80 | .10 |  |  | 21- | 2 | 2 | 8 | 1 |  |  |  | Exterior Fixed Grilles and Screens
[6 empty] | B2080.30 | B | 20 | 80 | .30 |  |  | 21- | 2 | 2 | 8 | 3 |  |  |  | Exterior Opening Protection Devices
[6 empty] | B2080.50 | B | 20 | 80 | .50 |  |  | 21- | 2 | 2 | 8 | 5 |  |  |  | Exterior Balcony Walls and Railings
[6 empty] | B2080.70 | B | 20 | 80 | .70 |  |  | 21- | 2 | 2 | 8 | 7 |  |  |  | Exterior Fabrications
[6 empty] | B2080.80 | B | 20 | 80 | .80 |  |  | 21- | 2 | 2 | 8 | 8 |  |  |  | Bird Control Devices
[6 empty] | B2090 | B | 20 | 90 |  |  |  | 21- | 2 | 2 | 9 |  |  |  |  | Exterior Wall Specialties
[6 empty] | B30 | B | 30 |  |  |  |  | 21- | 2 | 3 | [5 empty] | Exterior Horizontal Enclosures
[6 empty] | B3010 | B | 30 | 10 |  |  |  | 21- | 2 | 3 | 1 |  |  |  |  | Roofing | B – Roof | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | B3010.10 | B | 30 | 10 | .10 |  |  | 21- | 2 | 3 | 1 | 1 |  |  |  | Steep Slope Roofing
[6 empty] | B3010.50 | B | 30 | 10 | .50 |  |  | 21- | 2 | 3 | 1 | 5 |  |  |  | Low Slope Roofing
[6 empty] | B3010.70 | B | 30 | 10 | .70 |  |  | 21- | 2 | 3 | 1 | 7 |  |  |  | Canopy Roofing
[6 empty] | B3010.90 | B | 30 | 10 | .90 |  |  | 21- | 2 | 3 | 1 | 9 |  |  |  | Roofing Supplementary Components
[6 empty] | B3020 | B | 30 | 20 |  |  |  | 21- | 2 | 3 | 2 |  |  |  |  | Roof Appurtenances
[6 empty] | B3020.10 | B | 30 | 20 | .10 |  |  | 21- | 2 | 3 | 2 | 1 |  |  |  | Roof Accessories
[6 empty] | B3020.30 | B | 30 | 20 | .30 |  |  | 21- | 2 | 3 | 2 | 3 |  |  |  | Roof Specialties
[6 empty] | B3020.70 | B | 30 | 20 | .70 |  |  | 21- | 2 | 3 | 2 | 7 |  |  |  | Rainwater Management
[6 empty] | B3040 | B | 30 | 40 |  |  |  | 21- | 2 | 3 | 4 |  |  |  |  | Traffic Bearing Horizontal Enclosures | B – Roof | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 200 | A
[6 empty] | B3040.10 | B | 30 | 40 | .10 |  |  | 21- | 2 | 3 | 4 | 1 |  |  |  | Traffic Bearing Coatings
[6 empty] | B3040.30 | B | 30 | 40 | .30 |  |  | 21- | 2 | 3 | 4 | 3 |  |  |  | Horizontal Waterproofing Membrane
[6 empty] | B3040.50 | B | 30 | 40 | .50 |  |  | 21- | 2 | 3 | 4 | 5 |  |  |  | Wear Surfaces
[6 empty] | B3040.90 | B | 30 | 40 | .90 |  |  | 21- | 2 | 3 | 4 | 9 |  |  |  | Horizontal Enclosure Supplementary Components
[6 empty] | B3060 [B3020] | B | 30 | 60 |  |  |  | 21- | 2 | 3 | 6 |  |  |  |  | Horizontal Openings | B – Ext. Openings | S | X | 0 | 200 | S |  | 200 | S |  | 200 | S |  | 500 | S
[6 empty] | B3060.10 | B | 30 | 60 | .10 |  |  | 21- | 2 | 3 | 6 | 1 |  |  |  | Roof Windows and Skylights
[6 empty] | B3060.50 | B | 30 | 60 | .50 |  |  | 21- | 2 | 3 | 6 | 5 |  |  |  | Vents and Hatches
[6 empty] | B3060.90 | B | 30 | 60 | .90 |  |  | 21- | 2 | 3 | 6 | 9 |  |  |  | Horizontal Openings Supplementary Components
[6 empty] | B3080 | B | 30 | 80 |  |  |  | 21- | 2 | 3 | 8 |  |  |  |  | Overhead Exterior Enclosures | Ceilings (susp. Ceilings)
[6 empty] | B3080.10 | B | 30 | 80 | .10 |  |  | 21- | 2 | 3 | 8 | 1 |  |  |  | Exterior Ceilings
[6 empty] | B3080.20 | B | 30 | 80 | .20 |  |  | 21- | 2 | 3 | 8 | 2 |  |  |  | Exterior Soffits |  | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | B3080.30 | B | 30 | 80 | .30 |  |  | 21- | 2 | 3 | 8 | 3 |  |  |  | Exterior Bulkheads
| C. INTERIORS |  |  |  |  | C | C | [5 empty] | 21- | 3 | [6 empty] | INTERIORS
[6 empty] | C10 | C | 10 |  |  |  |  | 21- | 3 | 1 | [5 empty] | Interior Construction
[6 empty] | C1010 | C | 10 | 10 |  |  |  | 21- | 3 | 1 | 1 |  |  |  |  | Partitions | C - Partitions | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
|  | 14.42 | Partitions - Drywall, Metal Studs | 10 22 00 | Partitions | C1010.10 | C | 10 | 10 | .10 |  |  | 21- | 3 | 1 | 1 | 1 |  |  |  | Interior Fixed Partitions
[6 empty] | C1010.10 | C | 10 | 10 | .10 | 0.1 |  | 21- | 3 | 1 | 1 | 1 | 1 |  |  | Masonry | A, B Masonry
[6 empty] | C1010.10 | C | 10 | 10 | .10 | 0.2 |  | 21- | 3 | 1 | 1 | 1 | 2 |  |  | Cold-Form Metal Framing | A, B Cold Formed Metal Framing
[6 empty] | C1010.10 | C | 10 | 10 | .10 | 0.3 |  | 21- | 3 | 1 | 1 | 1 | 3 |  |  | Wood | A, B Wood
[6 empty] | C1010.20 | C | 10 | 10 | .20 |  |  | 21- | 3 | 1 | 1 | 2 |  |  |  | Interior Glazed Partitions |  | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | C1010.40 | C | 10 | 10 | .40 |  |  | 21- | 3 | 1 | 1 | 4 |  |  |  | Interior Demountable Partitions
[6 empty] | C1010.50 | C | 10 | 10 | .50 |  |  | 21- | 3 | 1 | 1 | 5 |  |  |  | Interior Operable Partitions
[6 empty] | C1010.70 | C | 10 | 10 | .70 |  |  | 21- | 3 | 1 | 1 | 7 |  |  |  | Interior Screens
[6 empty] | C1010.90 | C | 10 | 10 | .90 |  |  | 21- | 3 | 1 | 1 | 9 |  |  |  | Interior Partitions Supplementary Components
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | C1020 | C | 10 | 20 |  |  |  | 21- | 3 | 1 | 2 |  |  |  |  | Interior Windows | C – Int. Windows | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | C1020.10 | C | 10 | 20 | .10 |  |  | 21- | 3 | 1 | 2 | 1 |  |  |  | Interior Operating Windows
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | C1020.20 | C | 10 | 20 | .20 |  |  | 21- | 3 | 1 | 2 | 2 |  |  |  | Interior Fixed Windows
|  | 14.14 | Windows & Glazing | 08 50 00 | Windows | C1020.50 | C | 10 | 20 | .50 |  |  | 21- | 3 | 1 | 2 | 5 |  |  |  | Interior Special Function Windows |  | A |  |  | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
[6 empty] | C1020.90 | C | 10 | 20 | .90 |  |  | 21- | 3 | 1 | 2 | 9 |  |  |  | Interior Window Supplementary Components
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030 [C1020] | C | 10 | 30 |  |  |  | 21- | 3 | 1 | 3 |  |  |  |  | Interior Doors | C – Int. Doors | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.10 | C | 10 | 30 | .10 |  |  | 21- | 3 | 1 | 3 | 1 |  |  |  | Interior Swinging Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.20 | C | 10 | 30 | .20 |  |  | 21- | 3 | 1 | 3 | 2 |  |  |  | Interior Entrance Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.25 | C | 10 | 30 | .25 |  |  | 21- | 3 | 1 | 3 | 25 |  |  |  | Interior Sliding Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.30 | C | 10 | 30 | .30 |  |  | 21- | 3 | 1 | 3 | 3 |  |  |  | Interior Folding Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.40 | C | 10 | 30 | .40 |  |  | 21- | 3 | 1 | 3 | 4 |  |  |  | Interior Coiling Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.50 | C | 10 | 30 | .50 |  |  | 21- | 3 | 1 | 3 | 5 |  |  |  | Interior Panel Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.70 | C | 10 | 30 | .70 |  |  | 21- | 3 | 1 | 3 | 7 |  |  |  | Interior Special Function Doors
|  | 14.13 | Doors | 08 10 00 | Doors and Frames | C1030.80 | C | 10 | 30 | .80 |  |  | 21- | 3 | 1 | 3 | 8 |  |  |  | Interior Access Doors and Panels |  | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
[6 empty] | C1030.90 | C | 10 | 30 | .90 |  |  | 21- | 3 | 1 | 3 | 9 |  |  |  | Interior Door Supplementary Components
[6 empty] | C1040 | C | 10 | 40 |  |  |  | 21- | 3 | 1 | 4 |  |  |  |  | Interior Grilles and Gates | C - Int. Doors
[6 empty] | C1040.10 | C | 10 | 40 | .10 |  |  | 21- | 3 | 1 | 4 | 1 |  |  |  | Interior Grilles |  | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | C1040.50 | C | 10 | 40 | .50 |  |  | 21- | 3 | 1 | 4 | 5 |  |  |  | Interior Gates |  | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
[6 empty] | C1060 | C | 10 | 60 |  |  |  | 21- | 3 | 1 | 6 |  |  |  |  | Raised Floor Construction | C - Raised Floor | A | X | X | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
[6 empty] | C1060.10 | C | 10 | 60 | .10 |  |  | 21- | 3 | 1 | 6 | 1 |  |  |  | Access Flooring
[6 empty] | C1060.30 | C | 10 | 60 | .30 |  |  | 21- | 3 | 1 | 6 | 3 |  |  |  | Platform/Stage Floors
[6 empty] | C1070 | C | 10 | 70 |  |  |  | 21- | 3 | 1 | 7 |  |  |  |  | Suspended Ceiling Construction | C - Susp. Clg. | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 500 | A
[6 empty] | C1070.10 | C | 10 | 70 | .10 |  |  | 21- | 3 | 1 | 7 | 1 |  |  |  | Acoustical Suspended Ceilings
[6 empty] | C1070.20 | C | 10 | 70 | .20 |  |  | 21- | 3 | 1 | 7 | 2 |  |  |  | Suspended Plaster and Gypsum Board Ceilings
[6 empty] | C1070.50 | C | 10 | 70 | .50 |  |  | 21- | 3 | 1 | 7 | 5 |  |  |  | Specialty Suspended Ceilings
[6 empty] | C1070.70 | C | 10 | 70 | .70 |  |  | 21- | 3 | 1 | 7 | 7 |  |  |  | Special Function Suspended Ceilings
[6 empty] | C1070.90 | C | 10 | 70 | .90 |  |  | 21- | 3 | 1 | 7 | 9 |  |  |  | Ceiling Suspension Components
[6 empty] | C1090 | C | 10 | 90 |  |  |  | 21- | 3 | 1 | 9 |  |  |  |  | Interior Specialties
[6 empty] | C1090.10 | C | 10 | 90 | .10 |  |  | 21- | 3 | 1 | 9 | 1 |  |  |  | Interior Railings and Handrails | A, B Miscellaneous Steel | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | C1090.15 | C | 10 | 90 | .15 |  |  | 21- | 3 | 1 | 9 | 15 |  |  |  | Interior Louvers | B,C Louvers and Vents
[6 empty] | C1090.20 | C | 10 | 90 | .20 |  |  | 21- | 3 | 1 | 9 | 2 |  |  |  | Information Specialties
[6 empty] | C1090.25 | C | 10 | 90 | .25 |  |  | 21- | 3 | 1 | 9 | 25 |  |  |  | Compartments and Cubicles
[6 empty] | C1090.30 | C | 10 | 90 | .30 |  |  | 21- | 3 | 1 | 9 | 3 |  |  |  | Service Walls
[6 empty] | C1090.35 | C | 10 | 90 | .35 |  |  | 21- | 3 | 1 | 9 | 35 |  |  |  | Wall and Door Protection
[6 empty] | C1090.40 | C | 10 | 90 | .40 |  |  | 21- | 3 | 1 | 9 | 4 |  |  |  | Toilet, Bath and Laundry Accessories
[6 empty] | C1090.45 | C | 10 | 90 | .45 |  |  | 21- | 3 | 1 | 9 | 45 |  |  |  | Interior Gas Lighting
[6 empty] | C1090.50 | C | 10 | 90 | .50 |  |  | 21- | 3 | 1 | 9 | 5 |  |  |  | Fireplaces and Stoves
[6 empty] | C1090.60 | C | 10 | 90 | .60 |  |  | 21- | 3 | 1 | 9 | 6 |  |  |  | Safety Specialties
[6 empty] | C1090.70 | C | 10 | 90 | .70 |  |  | 21- | 3 | 1 | 9 | 7 |  |  |  | Storage Specialties
[6 empty] | C1090.90 | C | 10 | 90 | .90 |  |  | 21- | 3 | 1 | 9 | 9 |  |  |  | Other Interior Specialties | A, B Miscellaneous Steel
[6 empty] | C20 | C | 20 |  |  |  |  | 21- | 3 | 2 | [5 empty] | Interior Finishes
[6 empty] | C2010 [C3010] | C | 20 | 10 |  |  |  | 21- | 3 | 2 | 1 |  |  |  |  | Wall Finishes |  | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | C2010.10 | C | 20 | 10 | .10 |  |  | 21- | 3 | 2 | 1 | 1 |  |  |  | Tile Wall Finish
[6 empty] | C2010.20 | C | 20 | 10 | .20 |  |  | 21- | 3 | 2 | 1 | 2 |  |  |  | Wall Paneling
[6 empty] | C2010.30 | C | 20 | 10 | .30 |  |  | 21- | 3 | 2 | 1 | 3 |  |  |  | Wall Coverings
[6 empty] | C2010.35 | C | 20 | 10 | .35 |  |  | 21- | 3 | 2 | 1 | 35 |  |  |  | Wall Carpeting
[6 empty] | C2010.50 | C | 20 | 10 | .50 |  |  | 21- | 3 | 2 | 1 | 5 |  |  |  | Stone Facing
[6 empty] | C2010.60 | C | 20 | 10 | .60 |  |  | 21- | 3 | 2 | 1 | 6 |  |  |  | Special Wall Surfacing
[6 empty] | C2010.70 | C | 20 | 10 | .70 |  |  | 21- | 3 | 2 | 1 | 7 |  |  |  | Wall Painting and Coating
[6 empty] | C2010.80 | C | 20 | 10 | .80 |  |  | 21- | 3 | 2 | 1 | 8 |  |  |  | Acoustical Wall Treatment
[6 empty] | C2010.90 | C | 20 | 10 | .90 |  |  | 21- | 3 | 2 | 1 | 9 |  |  |  | Wall Finish Supplementary Components
[6 empty] | C2020 | C | 20 | 20 |  |  |  | 21- | 3 | 2 | 2 |  |  |  |  | Interior Fabrications |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | C2030 [C3020] | C | 20 | 30 |  |  |  | 21- | 3 | 2 | 3 |  |  |  |  | Flooring |  | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | C2030.10 | C | 20 | 30 | .10 |  |  | 21- | 3 | 2 | 3 | 1 |  |  |  | Flooring Treatment
[6 empty] | C2030.20 | C | 20 | 30 | .20 |  |  | 21- | 3 | 2 | 3 | 2 |  |  |  | Tile Flooring
[6 empty] | C2030.30 | C | 20 | 30 | .30 |  |  | 21- | 3 | 2 | 3 | 3 |  |  |  | Specialty Flooring
[6 empty] | C2030.40 | C | 20 | 30 | .40 |  |  | 21- | 3 | 2 | 3 | 4 |  |  |  | Masonry Flooring
[6 empty] | C2030.45 | C | 20 | 30 | .45 |  |  | 21- | 3 | 2 | 3 | 45 |  |  |  | Wood Flooring
[6 empty] | C2030.50 | C | 20 | 30 | .50 |  |  | 21- | 3 | 2 | 3 | 5 |  |  |  | Resilient Flooring
[6 empty] | C2030.60 | C | 20 | 30 | .60 |  |  | 21- | 3 | 2 | 3 | 6 |  |  |  | Terrazzo Flooring
[6 empty] | C2030.70 | C | 20 | 30 | .70 |  |  | 21- | 3 | 2 | 3 | 7 |  |  |  | Fluid-Applied Flooring
[6 empty] | C2030.75 | C | 20 | 30 | .75 |  |  | 21- | 3 | 2 | 3 | 75 |  |  |  | Carpeting
[6 empty] | C2030.80 | C | 20 | 30 | .80 |  |  | 21- | 3 | 2 | 3 | 8 |  |  |  | Athletic Flooring
[6 empty] | C2030.85 | C | 20 | 30 | .85 |  |  | 21- | 3 | 2 | 3 | 85 |  |  |  | Entrance Flooring
[6 empty] | C2030.90 | C | 20 | 30 | .90 |  |  | 21- | 3 | 2 | 3 | 9 |  |  |  | Flooring Supplementary Components
[6 empty] | C2040 | C | 20 | 40 |  |  |  | 21- | 3 | 2 | 4 |  |  |  |  | Stair Finishes |  | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | C2040.20 | C | 20 | 40 | .20 |  |  | 21- | 3 | 2 | 4 | 2 |  |  |  | Tile Stair Finish
[6 empty] | C2040.40 | C | 20 | 40 | .40 |  |  | 21- | 3 | 2 | 4 | 4 |  |  |  | Masonry Stair Finish
[6 empty] | C2040.45 | C | 20 | 40 | .45 |  |  | 21- | 3 | 2 | 4 | 45 |  |  |  | Wood Stair Finish
[6 empty] | C2040.50 | C | 20 | 40 | .50 |  |  | 21- | 3 | 2 | 4 | 5 |  |  |  | Resilient Stair Finish
[6 empty] | C2040.60 | C | 20 | 40 | .60 |  |  | 21- | 3 | 2 | 4 | 6 |  |  |  | Terrazzo Stair Finish
[6 empty] | C2040.75 | C | 20 | 40 | .75 |  |  | 21- | 3 | 2 | 4 | 75 |  |  |  | Carpeted Stair Finish
[6 empty] | C2050 [C3030] | C | 20 | 50 |  |  |  | 21- | 3 | 2 | 5 |  |  |  |  | Ceiling Finishes |  | A | X | 0 | 200 | A |  | 200 | A |  | 300 | A |  | 300 | A
[6 empty] | C2050.10 | C | 20 | 50 | .10 |  |  | 21- | 3 | 2 | 5 | 1 |  |  |  | Plaster and Gypsum Board Finish
[6 empty] | C2050.20 | C | 20 | 50 | .20 |  |  | 21- | 3 | 2 | 5 | 2 |  |  |  | Ceiling Paneling
[6 empty] | C2050.70 | C | 20 | 50 | .70 |  |  | 21- | 3 | 2 | 5 | 7 |  |  |  | Ceiling Painting and Coating
[6 empty] | C2050.80 | C | 20 | 50 | .80 |  |  | 21- | 3 | 2 | 5 | 8 |  |  |  | Acoustic Ceiling Treatment
[6 empty] | C2050.90 | C | 20 | 50 | .90 |  |  | 21- | 3 | 2 | 5 | 9 |  |  |  | Ceiling Finish Supplementary Components
| D. SERVICES |  |  |  |  | D | D | [5 empty] | 21- | 4 | [6 empty] | SERVICES
[6 empty] | D10 | D | 10 |  |  |  |  | 21- | 4 | 1 | [5 empty] | Conveying |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | D1010 | D | 10 | 10 |  |  |  | 21- | 4 | 1 | 1 |  |  |  |  | Vertical Conveying Systems |  | A | X | X | 200 | A |  | 200 | A/M |  | 300 | A/M |  | 500 | A/M
[6 empty] | D1010.10 | D | 10 | 10 | .10 |  |  | 21- | 4 | 1 | 1 | 1 |  |  |  | Elevators
[6 empty] | D1010.20 | D | 10 | 10 | .20 |  |  | 21- | 4 | 1 | 1 | 2 |  |  |  | Lifts
[6 empty] | D1010.30 | D | 10 | 10 | .30 |  |  | 21- | 4 | 1 | 1 | 3 |  |  |  | Escalators
[6 empty] | D1010.50 | D | 10 | 10 | .50 |  |  | 21- | 4 | 1 | 1 | 5 |  |  |  | Dumbwaiters
[6 empty] | D1010.60 | D | 10 | 10 | .60 |  |  | 21- | 4 | 1 | 1 | 6 |  |  |  | Moving Ramps
[6 empty] | D1030 [D1020] | D | 10 | 30 |  |  |  | 21- | 4 | 1 | 3 |  |  |  |  | Horizontal Conveying
[6 empty] | D1030.10 | D | 10 | 30 | .10 |  |  | 21- | 4 | 1 | 3 | 1 |  |  |  | Moving Walks
[6 empty] | D1030.30 | D | 10 | 30 | .30 |  |  | 21- | 4 | 1 | 3 | 3 |  |  |  | Turntables
[6 empty] | D1030.50 | D | 10 | 30 | .50 |  |  | 21- | 4 | 1 | 3 | 5 |  |  |  | Passenger Loading Bridges
[6 empty] | D1030.70 | D | 10 | 30 | .70 |  |  | 21- | 4 | 1 | 3 | 7 |  |  |  | People Movers
[6 empty] | D1050 [D1090] | D | 10 | 50 |  |  |  | 21- | 4 | 1 | 5 |  |  |  |  | Material Handling
[6 empty] | D1050.10 | D | 10 | 50 | .10 |  |  | 21- | 4 | 1 | 5 | 1 |  |  |  | Cranes
[6 empty] | D1050.20 | D | 10 | 50 | .20 |  |  | 21- | 4 | 1 | 5 | 2 |  |  |  | Hoists
[6 empty] | D1050.30 | D | 10 | 50 | .30 |  |  | 21- | 4 | 1 | 5 | 3 |  |  |  | Derrecks
[6 empty] | D1050.40 | D | 10 | 50 | .40 |  |  | 21- | 4 | 1 | 5 | 4 |  |  |  | Conveyors
[6 empty] | D1050.50 | D | 10 | 50 | .50 |  |  | 21- | 4 | 1 | 5 | 5 |  |  |  | Baggage Handling Equipment
[6 empty] | D1050.60 | D | 10 | 50 | .60 |  |  | 21- | 4 | 1 | 5 | 6 |  |  |  | Chutes
[6 empty] | D1050.70 | D | 10 | 50 | .70 |  |  | 21- | 4 | 1 | 5 | 7 |  |  |  | Pneumatic Tube Systems
[6 empty] | D1080 | D | 10 | 80 |  |  |  | 21- | 4 | 1 | 8 |  |  |  |  | Operable Access Systems
[6 empty] | D1080.10 | D | 10 | 80 | .10 |  |  | 21- | 4 | 1 | 8 | 1 |  |  |  | Suspended Scaffolding
[6 empty] | D1080.20 | D | 10 | 80 | .20 |  |  | 21- | 4 | 1 | 8 | 2 |  |  |  | Rope Climbers
[6 empty] | D1080.30 | D | 10 | 80 | .30 |  |  | 21- | 4 | 1 | 8 | 3 |  |  |  | Elevating Platforms
[6 empty] | D1080.40 | D | 10 | 80 | .40 |  |  | 21- | 4 | 1 | 8 | 4 |  |  |  | Powered Scaffolding
[6 empty] | D1080.50 | D | 10 | 80 | .50 |  |  | 21- | 4 | 1 | 8 | 5 |  |  |  | Building Envelope Access
|  | 14.5 | PLUMBING EQUIPMENT including SINKS | 22 00 00 | Plumbing | D20 | D | 20 |  |  |  |  | 21- | 4 | 2 | [5 empty] | Plumbing | D20 - Plumbing, D- Fluid_Gas Distribution; D50 - Electrical | M | X | 0 | 200 | M |  | 200 | M |  | 300 | M |  | 300 | M
[6 empty] | D2010 [D2020] | D | 20 | 10 |  |  |  | 21- | 4 | 2 | 1 |  |  |  |  | Domestic Water Distribution |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 300 | M
[6 empty] | D2010.10 | D | 20 | 10 | .10 |  |  | 21- | 4 | 2 | 1 | 1 |  |  |  | Facility Potable-Water Storage Tanks |  | M |  |  |  | M |  |  | M |  |  | M
|  | 23 | HEAT EXCHANGERS | 22 35 00 | Domestic Water Heat Exchangers | D2010.20 | D | 20 | 10 | .20 |  |  | 21- | 4 | 2 | 1 | 2 |  |  |  | Domestic Water Equipment |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2010.40 | D | 20 | 10 | .40 |  |  | 21- | 4 | 2 | 1 | 4 |  |  |  | Domestic Water Piping |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2010.60 | D | 20 | 10 | .60 |  |  | 21- | 4 | 2 | 1 | 6 |  |  |  | Plumbing Fixtures |  | M | X | 0 | 200 | M |  | 200 | M |  | 300 | M |  | 300 | M
|  | 18.62 | Pipe Lagging | 22 07 00 | Plumbing Insulation | D2010.90 | D | 20 | 10 | .90 |  |  | 21- | 4 | 2 | 1 | 9 |  |  |  | Domestic Water Distribution Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2020 [D2030] | D | 20 | 20 |  |  |  | 21- | 4 | 2 | 2 |  |  |  |  | Sanitary Drainage |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 300 | M
[6 empty] | D202010 | D | 20 | 20 | 10 |  |  | 21- | 4 | 2 | 2 | 1 |  |  |  | Sanitary Sewerage Equipment |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2020.30 | D | 20 | 20 | .30 |  |  | 21- | 4 | 2 | 2 | 3 |  |  |  | Sanitary Sewerage Piping |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2020.90 | D | 20 | 20 | .90 |  |  | 21- | 4 | 2 | 2 | 9 |  |  |  | Sanitary Drainage Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2030 [D2040] | D | 20 | 30 |  |  |  | 21- | 4 | 2 | 3 |  |  |  |  | Building Support Plumbing Systems |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 300 | M
[6 empty] | D2030.10 | D | 20 | 30 | .10 |  |  | 21- | 4 | 2 | 3 | 1 |  |  |  | Stormwater Drainage Equipment |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2030.20 | D | 20 | 30 | .20 |  |  | 21- | 4 | 2 | 3 | 2 |  |  |  | Stormwater Drainage Piping |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2030.30 | D | 20 | 30 | .30 |  |  | 21- | 4 | 2 | 3 | 3 |  |  |  | Facility Stormwater Drains |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2030.60 | D | 20 | 30 | .60 |  |  | 21- | 4 | 2 | 3 | 6 |  |  |  | Gray Water Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2030.90 | D | 20 | 30 | .90 |  |  | 21- | 4 | 2 | 3 | 9 |  |  |  | Building Support Plumbing System Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2050 [D2090] | D | 20 | 50 |  |  |  | 21- | 4 | 2 | 5 |  |  |  |  | General Service Compressed-Air |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2060 [D2090.99] | D | 20 | 60 |  |  |  | 21- | 4 | 2 | 6 |  |  |  |  | Process Support Plumbing Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2060.10 | D | 20 | 60 | .10 |  |  | 21- | 4 | 2 | 6 | 1 |  |  |  | Compressed-Air Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2060.20 | D | 20 | 60 | .20 |  |  | 21- | 4 | 2 | 6 | 2 |  |  |  | Vacuum Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2060.30 | D | 20 | 60 | .30 |  |  | 21- | 4 | 2 | 6 | 3 |  |  |  | Gas Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2060.40 | D | 20 | 60 | .40 |  |  | 21- | 4 | 2 | 6 | 4 |  |  |  | Chemical-Waste Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2060.50 | D | 20 | 60 | .50 |  |  | 21- | 4 | 2 | 6 | 5 |  |  |  | Processed Water Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D2060.90 | D | 20 | 60 | .90 |  |  | 21- | 4 | 2 | 6 | 9 |  |  |  | Process Support Plumbing System Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D30 | D | 30 |  |  |  |  | 21- | 4 | 3 | [5 empty] | HVAC | D20 - Plumbing; D30 - HVAC; D- Air Distribution; D40 - Fire Protection; D- Fluid_Gas Distribution; D50 - Electrical; D- Electrical Distribution | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D3010 | D | 30 | 10 |  |  |  | 21- | 4 | 3 | 1 |  |  |  |  | Facility Fuel Systems |  | M |  |  | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D3010.10 | D | 30 | 10 | .10 |  |  | 21- | 4 | 3 | 1 | 1 |  |  |  | Fuel Piping |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3010.30 | D | 30 | 10 | .30 |  |  | 21- | 4 | 3 | 1 | 3 |  |  |  | Fuel Pumps |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3010.50 | D | 30 | 10 | .50 |  |  | 21- | 4 | 3 | 1 | 5 |  |  |  | Fuel Storage Tanks |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3020 | D | 30 | 20 |  |  |  | 21- | 4 | 3 | 2 |  |  |  |  | Heating Systems |  | M |  |  | 200 | M |  |  | M |  |  | M
|  | 27.7 | STACKS, FLARES, & CHIMNEYS | 23 51 00 | Breechings, Chimneys, and Stacks | D3020.10 | D | 30 | 20 | .10 |  |  | 21- | 4 | 3 | 2 | 1 |  |  |  | Heat Generation |  | M | X | X |  | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D3020.30 | D | 30 | 20 | .30 |  |  | 21- | 4 | 3 | 2 | 3 |  |  |  | Thermal Heat Storage |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3020.70 | D | 30 | 20 | .70 |  |  | 21- | 4 | 3 | 2 | 7 |  |  |  | Decentralized Heating Equipment |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3020.90 | D | 30 | 20 | .90 |  |  | 21- | 4 | 3 | 2 | 9 |  |  |  | Heating System Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3030 | D | 30 | 30 |  |  |  | 21- | 4 | 3 | 3 |  |  |  |  | Cooling Systems |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
|  | 23.3 | COOLING TOWERS (____GPM) | 23 65 00 | Cooling Towers | D3030.10 | D | 30 | 30 | .10 |  |  | 21- | 4 | 3 | 3 | 1 |  |  |  | Central Cooling |  | M |  |  |  | M |  |  | M |  |  | M
|  | 23.3 | COOLING TOWERS (____GPM) | 23 65 00 | Cooling Towers | D3030.10 | D | 30 | 30 | .10 |  |  | 21- | 4 | 3 | 3 | 3 |  |  |  | Evaporative Air-Cooling |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3030.40 | D | 30 | 30 | .40 |  |  | 21- | 4 | 3 | 3 | 4 |  |  |  | Thermal Cooling Storage |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3030.70 | D | 30 | 30 | .70 |  |  | 21- | 4 | 3 | 3 | 7 |  |  |  | Decentralized Cooling |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3030.00 | D | 30 | 30 | .00 |  |  | 21- | 4 | 3 | 3 |  |  |  |  | Cooling System Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3050 | D | 30 | 50 |  |  |  | 21- | 4 | 3 | 5 |  |  |  |  | Facility HVAC Distribution Systems |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D3050.10 | D | 30 | 50 | .10 |  |  | 21- | 4 | 3 | 5 | 1 |  |  |  | Facility Hydronic Distribution |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3050.30 | D | 30 | 50 | .30 |  |  | 21- | 4 | 3 | 5 | 3 |  |  |  | Facility Steam Distribution |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3050.50 | D | 30 | 50 | .50 |  |  | 21- | 4 | 3 | 5 | 5 |  |  |  | HVAC Air Distribution |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D3050.90 | D | 30 | 50 | .90 |  |  | 21- | 4 | 3 | 5 | 9 |  |  |  | Facility Distribution Systems Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3060 [D3040] | D | 30 | 60 |  |  |  | 21- | 4 | 3 | 6 |  |  |  |  | Ventilation |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D3060.10 | D | 30 | 60 | .10 |  |  | 21- | 4 | 3 | 6 | 1 |  |  |  | Supply Air |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3060.20 | D | 30 | 60 | .20 |  |  | 21- | 4 | 3 | 6 | 2 |  |  |  | Return Air |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3060.30 | D | 30 | 60 | .30 |  |  | 21- | 4 | 3 | 6 | 3 |  |  |  | Exhaust Air |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3060.40 | D | 30 | 60 | .40 |  |  | 21- | 4 | 3 | 6 | 4 |  |  |  | Outside Air |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3060.60 | D | 30 | 60 | .60 |  |  | 21- | 4 | 3 | 6 | 6 |  |  |  | Air-to-Air Energy Recovery |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3060.70 | D | 30 | 60 | .70 |  |  | 21- | 4 | 3 | 6 | 7 |  |  |  | HVAC Air Cleaning |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3060.90 | D | 30 | 60 | .90 |  |  | 21- | 4 | 3 | 6 | 9 |  |  |  | Ventilation Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3070 | D | 30 | 70 |  |  |  | 21- | 4 | 3 | 7 |  |  |  |  | Special Purpose HVAC Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D3070.10 | D | 30 | 70 | .10 |  |  | 21- | 4 | 3 | 7 | 1 |  |  |  | Snow Melting |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D40 | D | 40 |  |  |  |  | 21- | 4 | 4 | [5 empty] | Fire Protection | D40 - Fire Protection, D- Fluid_Gas Distribution; D50 - Electrical, | M |  |  | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D4010 | D | 40 | 10 |  |  |  | 21- | 4 | 4 | 1 |  |  |  |  | Fire Suppression |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D4010.10 | D | 40 | 10 | .10 |  |  | 21- | 4 | 4 | 1 | 1 |  |  |  | Water-Based Fire-Suppression |  | M | X | X |  | M |  |  | M |  |  | M
[6 empty] | D4010.50 | D | 40 | 10 | .50 |  |  | 21- | 4 | 4 | 1 | 5 |  |  |  | Fire-Extinguishing |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D4010.90 | D | 40 | 10 | .90 |  |  | 21- | 4 | 4 | 1 | 9 |  |  |  | Fire Suppression Supplementary Components |  | M |  |  |  | M |  |  | M |  |  | M
|  | 14.6 | FIRE (LOSS) PREVENTION & PROTECTION | 10 44 00 | Fire Protection Specialties | D4030 | D | 40 | 30 |  |  |  | 21- | 4 | 4 | 3 |  |  |  |  | Fire Protection Specialties |  | M | X | X | 200 | M |  | 200 | M |  | 300 | M |  | 500 | M
[6 empty] | D4030.10 | D | 40 | 30 | .10 |  |  | 21- | 4 | 4 | 3 | 1 |  |  |  | Fire Protection Cabinets |  | M |  |  |  | M |  |  | M |  |  | M
|  | 14.61 | Extinguishers & Cabinets | 10 44 16 | Fire Extinguishers | D4030.30 | D | 40 | 30 | .30 |  |  | 21- | 4 | 4 | 3 | 3 |  |  |  | Fire Extinguishers |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D4030.50 | D | 40 | 30 | .50 |  |  | 21- | 4 | 4 | 3 | 5 |  |  |  | Breathing Air Replenishment Systems |  | M |  |  |  | M |  |  | M |  |  | M
[6 empty] | D4030.70 | D | 40 | 30 | .70 |  |  | 21- | 4 | 4 | 3 | 7 |  |  |  | Fire Extinguisher Accessories |  | M |  |  |  | M |  |  | M |  |  | M
|  | 16 | ELECTRICAL BULK COMMODITIES | 26 00 00 | Electrical | D50 | D | 50 |  |  |  |  | 21- | 4 | 5 | [5 empty] | Electrical | D50 - Electrical, D- Electrical Distribution | E | X | X | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
[6 empty] | D5010 | D | 50 | 10 |  |  |  | 21- | 4 | 5 | 1 |  |  |  |  | Facility Power Generation |  | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
|  | 31 | COMBUSTION TURBINE-GENERATORS | 26 32 13 | Engine Generators | D5010.10 | D | 50 | 10 | .10 |  |  | 21- | 4 | 5 | 1 | 1 |  |  |  | Packaged Generator Assemblies |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5010.20 | D | 50 | 10 | .20 |  |  | 21- | 4 | 5 | 1 | 2 |  |  |  | Battery Equipment |  | E |  |  |  | E |  |  | E |  |  | E
|  | 16.64 | Photo Cells | 26 31 00 | Photovoltaic Collectors | D5010.30 | D | 50 | 10 | .30 |  |  | 21- | 4 | 5 | 1 | 3 |  |  |  | Photovoltaic Collectors |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5010.40 | D | 50 | 10 | .40 |  |  | 21- | 4 | 5 | 1 | 4 |  |  |  | Fuel Cells |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D501060 | D | 50 | 10 | 60 |  |  | 21- | 4 | 5 | 1 | 6 |  |  |  | Power Filtering and Conditioning |  | E |  |  |  | E |  |  | E |  |  | E
|  | 0 | 0 | 26 36 00 | Transfer Switches | D5010.70 | D | 50 | 10 | .70 |  |  | 21- | 4 | 5 | 1 | 7 |  |  |  | Transfer Switches |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5010.90 | D | 50 | 10 | .90 |  |  | 21- | 4 | 5 | 1 | 9 |  |  |  | Facility Power Generation Supplementary Components |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5020 [D5010] | D | 50 | 20 |  |  |  | 21- | 4 | 5 | 2 |  |  |  |  | Electrical Service and Distribution |  | E | X | X | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
|  | 16.62 | Transformers | 26 12 00 | Medium-Voltage Transformers | D5020.10 | D | 50 | 20 | .10 |  |  | 21- | 4 | 5 | 2 | 1 |  |  |  | Electrical Service Entrance |  | E |  |  |  | E |  |  | E |  |  | E
|  | 16.2 | CONDUIT & SUPPORTS | 26 05 33 | Conduit for Electrical Systems | D5020.30 | D | 50 | 20 | .30 |  |  | 21- | 4 | 5 | 2 | 3 |  |  |  | Power Distribution |  | E |  |  |  | E |  |  | E |  |  | E
|  | 16.5 | GROUNDING & LIGHTNING PROTECTION | 26 05 26 | Grounding and Bonding for Electrical Systems | D5020.70 | D | 50 | 20 | .70 |  |  | 21- | 4 | 5 | 2 | 7 |  |  |  | Facility Grounding |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D502090 | D | 50 | 20 | 90 |  |  | 21- | 4 | 5 | 2 | 9 |  |  |  | Electrical Service and Distribution Supplementary Components |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5030 | D | 50 | 30 |  |  |  | 21- | 4 | 5 | 3 |  |  |  |  | General Purpose Electrical Power |  | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
|  | 16.222 | (Under Ground) | 26 05 43 | Underground Ducts and Raceways for Electrical Systems | D5030.10 | D | 50 | 30 | .10 |  |  | 21- | 4 | 5 | 3 | 1 |  |  |  | Branch Wiring System |  | E | X | X |  | E |  |  | E |  |  | E
[6 empty] | D5030.50 | D | 50 | 30 | .50 |  |  | 21- | 4 | 5 | 3 | 5 |  |  |  | Wiring Devices |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5030.90 | D | 50 | 30 | .90 |  |  | 21- | 4 | 5 | 3 | 9 |  |  |  | General Purpose Electrical Power Supplementary Components |  | E |  |  |  | E |  |  | E |  |  | E
|  | 16.66 | Lighting Fixtures | 26 50 00 | Lighting | D5040 [D5020] | D | 50 | 40 |  |  |  | 21- | 4 | 5 | 4 |  |  |  |  | Lighting |  | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
|  | 16.61 | Panels | 26 09 26 | Lighting Control Panelboards | D5040.10 | D | 50 | 40 | .10 |  |  | 21- | 4 | 5 | 4 | 1 |  |  |  | Lighting Control |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5040.20 | D | 50 | 40 | .20 |  |  | 21- | 4 | 5 | 4 | 2 |  |  |  | Branch Wiring for Lighting |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5040.50 | D | 50 | 40 | .50 |  |  | 21- | 4 | 5 | 4 | 5 |  |  |  | Lighting Fixtures |  | E | X | X |  | E |  |  | E |  |  | E |  |  | E
[6 empty] | D5040.90 | D | 50 | 40 | .90 |  |  | 21- | 4 | 5 | 4 | 9 |  |  |  | Lighting Supplementary Components |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5080 [D5090] | D | 50 | 80 |  |  |  | 21- | 4 | 5 | 8 |  |  |  |  | Miscellaneous Electrical Systems |  | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
|  | 16.52 | Lightning Protection | 26 41 00 | Facility Lightning Protection | D5080.10 | D | 50 | 80 | .10 |  |  | 21- | 4 | 5 | 8 | 1 |  |  |  | Lightning Protection |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D5080.70 | D | 50 | 80 | .70 |  |  | 21- | 4 | 5 | 8 | 7 |  |  |  | Transient Voltage Suppression |  | E |  |  |  | E |  |  | E |  |  | E
|  | 72.4 | COMMUNICATIONS | 27 00 00 | Communications | D60 [D5030] | D | 60 |  |  |  |  | 21- | 4 | 6 | [5 empty] | Communications | D50 - Electrical, D- Electrical Distribution | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
[6 empty] | D6010 | D | 60 | 10 |  |  |  | 21- | 4 | 6 | 1 |  |  |  |  | Data Communications |  | E |  |  |  | E |  |  | E |  |  | E
|  | 16.83 | Communication (Voice) | 27 30 00 | Voice Communications | D6020 | D | 60 | 20 |  |  |  | 21- | 4 | 6 | 2 |  |  |  |  | Voice Communications |  | E | X | X |  | E |  |  | E |  |  | E
[6 empty] | D6030 | D | 60 | 30 |  |  |  | 21- | 4 | 6 | 3 |  |  |  |  | Audio-Video Communication |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D6060 | D | 60 | 60 |  |  |  | 21- | 4 | 6 | 6 |  |  |  |  | Distributed Communications and Monitoring |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D6090 | D | 60 | 90 |  |  |  | 21- | 4 | 6 | 9 |  |  |  |  | Communications Supplementary Components |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D70 [D5030] | D | 70 |  |  |  |  | 21- | 4 | 7 | [5 empty] | Electronic Safety and Security | D50 - Electrical, D- Electrical Distribution | E | X | X | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
[6 empty] | D7010 | D | 70 | 10 |  |  |  | 21- | 4 | 7 | 1 |  |  |  |  | Access Control and Intrusion Detection |  | E |  |  |  | E |  |  | E |  |  | E
|  | 16.86 | Electrical Devices | 28 20 00 | Electronic Surveillance | D7030 | D | 70 | 30 |  |  |  | 21- | 4 | 7 | 3 |  |  |  |  | Electronic Surveillance |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D7050 | D | 70 | 50 |  |  |  | 21- | 4 | 7 | 5 |  |  |  |  | Detection and Alarm |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D7070 | D | 70 | 70 |  |  |  | 21- | 4 | 7 | 7 |  |  |  |  | Electronic Monitoring and Control |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D7090 | D | 70 | 90 |  |  |  | 21- | 4 | 7 | 9 |  |  |  |  | Electronic Safety and Security Supplementary Components |  | E |  |  |  | E |  |  | E |  |  | E
[6 empty] | D80 | D | 80 |  |  |  |  | 21- | 4 | 8 | [5 empty] | Integrated Automation | D50 - Electrical, D- Electrical Distribution | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
[6 empty] | D8010 | D | 80 | 10 |  |  |  | 21- | 4 | 8 | 1 |  |  |  |  | Integrated Automation Facility Controls |  | E |  |  |  | E |  |  | E |  |  | E
| E. EQUIPMENT & FURNISHINGS |  |  |  |  | E | E | [5 empty] | 21- | 5 | [6 empty] | EQUIPMENT & FURNISHINGS
[6 empty] | E10 | E | 10 |  |  |  |  | 21- | 5 | 1 | [5 empty] | Equipment
[6 empty] | E1010 | E | 10 | 10 |  |  |  | 21- | 5 | 1 | 1 |  |  |  |  | Vehicle and Pedestrian Equipment |  | E | X | X | 200 | E |  | 200 | E |  | 300 | E |  | 300 | E
[6 empty] | E1010.10 | E | 10 | 10 | .10 |  |  | 21- | 5 | 1 | 1 | 1 |  |  |  | Vehicle Servicing Equipment
[6 empty] | E1010.30 | E | 10 | 10 | .30 |  |  | 21- | 5 | 1 | 1 | 3 |  |  |  | Interior Parking Control Equipment
[6 empty] | E1010.50 | E | 10 | 10 | .50 |  |  | 21- | 5 | 1 | 1 | 5 |  |  |  | Loading Dock Equipment
[6 empty] | E1010.70 | E | 10 | 10 | .70 |  |  | 21- | 5 | 1 | 1 | 7 |  |  |  | Interior Pedestrian Control Equipment
|  | 14.81 | Commercial Equipment | 11 20 00 | Commercial Equipment | E1030 | E | 10 | 30 |  |  |  | 21- | 5 | 1 | 3 |  |  |  |  | Commercial Equipment |  | E | X | X | 200 | E |  | 200 | E |  | 300 | E |  | 300 | E
[6 empty] | E1030.10 | E | 10 | 30 | .10 |  |  | 21- | 5 | 1 | 3 | 1 |  |  |  | Mercantile and Service Equipment
[6 empty] | E1030.20 | E | 10 | 30 | .20 |  |  | 21- | 5 | 1 | 3 | 2 |  |  |  | Vault Equipment
[6 empty] | E1030.25 | E | 10 | 30 | .25 |  |  | 21- | 5 | 1 | 3 | 25 |  |  |  | Teller and Service Equipment
[6 empty] | E1030.30 | E | 10 | 30 | .30 |  |  | 21- | 5 | 1 | 3 | 3 |  |  |  | Refrigerated Display Equipment
[6 empty] | E1030.35 | E | 10 | 30 | .35 |  |  | 21- | 5 | 1 | 3 | 35 |  |  |  | Commercial Laundry and Dry Cleaning Equipment
[6 empty] | E1030.40 | E | 10 | 30 | .40 |  |  | 21- | 5 | 1 | 3 | 4 |  |  |  | Maintenance Equipment
[6 empty] | E1030.50 | E | 10 | 30 | .50 |  |  | 21- | 5 | 1 | 3 | 5 |  |  |  | Hospitality Equipment
[6 empty] | E1030.55 | E | 10 | 30 | .55 |  |  | 21- | 5 | 1 | 3 | 55 |  |  |  | Unit Kitchens
[6 empty] | E1030.60 | E | 10 | 30 | .60 |  |  | 21- | 5 | 1 | 3 | 6 |  |  |  | Photographic Processing Equipment
[6 empty] | E1030.70 | E | 10 | 30 | .70 |  |  | 21- | 5 | 1 | 3 | 7 |  |  |  | Postal, Packaging and Shipping Equipment
|  | 14.87 | Office Equipment | 11 28 00 | Office Equipment | E1030.75 | E | 10 | 30 | .75 |  |  | 21- | 5 | 1 | 3 | 75 |  |  |  | Office Equipment
[6 empty] | E1030.80 | E | 10 | 30 | .80 |  |  | 21- | 5 | 1 | 3 | 8 |  |  |  | Foodservice Equipment
|  | 14.83 | Educational/Cultural/Social Equipment | 11 50 00 | Educational and Scientific Equipment | E1040 | E | 10 | 40 |  |  |  | 21- | 5 | 1 | 4 |  |  |  |  | Institutional Equipment
|  | 14.85 | Lab Equipment | 11 53 00 | Laboratory Equipment | E1040.10 | E | 10 | 40 | .10 |  |  | 21- | 5 | 1 | 4 | 1 |  |  |  | Educational and Scientific Equipment
|  | 14.86 | Medical & Food Service Equipment | 11 71 00 | Medical Sterilizing Equipment | E1040.20 | E | 10 | 40 | .20 |  |  | 21- | 5 | 1 | 4 | 2 |  |  |  | Healthcare Equipment
[6 empty] | E1040.40 | E | 10 | 40 | .40 |  |  | 21- | 5 | 1 | 4 | 4 |  |  |  | Religious Equipment
[6 empty] | E1040.60 | E | 10 | 40 | .60 |  |  | 21- | 5 | 1 | 4 | 6 |  |  |  | Security Equipment
[6 empty] | E1040.70 | E | 10 | 40 | .70 |  |  | 21- | 5 | 1 | 4 | 7 |  |  |  | Detention Equipment
|  | 14.88 | Residential Equipment | 11 30 00 | Residential Equipment | E1060 | E | 10 | 60 |  |  |  | 21- | 5 | 1 | 6 |  |  |  |  | Residential Equipment
[6 empty] | E1060.10 | E | 10 | 60 | .10 |  |  | 21- | 5 | 1 | 6 | 1 |  |  |  | Residential Appliances
[6 empty] | E1060.50 | E | 10 | 60 | .50 |  |  | 21- | 5 | 1 | 6 | 5 |  |  |  | Residential Stairs
[6 empty] | E1060.70 | E | 10 | 60 | .70 |  |  | 21- | 5 | 1 | 6 | 7 |  |  |  | Residential Ceiling Fans
[6 empty] | E1070 | E | 10 | 70 |  |  |  | 21- | 5 | 1 | 7 |  |  |  |  | Entertainment and Recreational Equipment
[6 empty] | E1070.10 | E | 10 | 70 | .10 |  |  | 21- | 5 | 1 | 7 | 1 |  |  |  | Theater and Stage Equipment
[6 empty] | E1070.20 | E | 10 | 70 | .20 |  |  | 21- | 5 | 1 | 7 | 2 |  |  |  | Musical Equipment
[6 empty] | E1070.50 | E | 10 | 70 | .50 |  |  | 21- | 5 | 1 | 7 | 5 |  |  |  | Athletic Equipment
[6 empty] | E1070.60 | E | 10 | 70 | .60 |  |  | 21- | 5 | 1 | 7 | 6 |  |  |  | Recreational Equipment |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | E1090 | E | 10 | 90 |  |  |  | 21- | 5 | 1 | 9 |  |  |  |  | Other Equipment
[6 empty] | E1090.10 | E | 10 | 90 | .10 |  |  | 21- | 5 | 1 | 9 | 1 |  |  |  | Solid Waste Handling Equipment
|  | 14.89 | Waste Disposal & Cleaning Equipment | 11 92 23 | Agricultural Waste Clean-Up Equipment | E1090.30 | E | 10 | 90 | .30 |  |  | 21- | 5 | 1 | 9 | 3 |  |  |  | Agricultural Equipment
[6 empty] | E1090.40 | E | 10 | 90 | .40 |  |  | 21- | 5 | 1 | 9 | 4 |  |  |  | Horticultural Equipment
[6 empty] | E1090.60 | E | 10 | 90 | .60 |  |  | 21- | 5 | 1 | 9 | 6 |  |  |  | Decontamination Equipment
|  | 14.33 | Furnishings | 12 00 00 | Furnishings | E20 | E | 20 |  |  |  |  | 21- | 5 | 2 | [5 empty] | Furnishings
[6 empty] | E2010 | E | 20 | 10 |  |  |  | 21- | 5 | 2 | 1 |  |  |  |  | Fixed Furnishings |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | E2010.10 | E | 20 | 10 | .10 |  |  | 21- | 5 | 2 | 1 | 1 |  |  |  | Fixed Art
[6 empty] | E2010.20 | E | 20 | 10 | .20 |  |  | 21- | 5 | 2 | 1 | 2 |  |  |  | Window Treatments
[6 empty] | E2010.30 | E | 20 | 10 | .30 |  |  | 21- | 5 | 2 | 1 | 3 |  |  |  | Casework
[6 empty] | E2010.70 | E | 20 | 10 | .70 |  |  | 21- | 5 | 2 | 1 | 7 |  |  |  | Fixed Multiple Seating
[6 empty] | E2010.90 | E | 20 | 10 | .90 |  |  | 21- | 5 | 2 | 1 | 9 |  |  |  | Other Fixed Furnishings
[6 empty] | E2050 | E | 20 | 50 |  |  |  | 21- | 5 | 2 | 5 |  |  |  |  | Movable Furnishings |  | A | X | 0 | 200 | A |  | 200 | A |  | 200 | A |  | 300 | A
[6 empty] | E2050.10 | E | 20 | 50 | .10 |  |  | 21- | 5 | 2 | 5 | 1 |  |  |  | Movable Art
|  | 72.2 | OFFICE FURNISHINGS & EQUIPMENT | 12 51 00 | Office Furniture | E2050.30 | E | 20 | 50 | .30 |  |  | 21- | 5 | 2 | 5 | 3 |  |  |  | Furniture
[6 empty] | E2050.40 | E | 20 | 50 | .40 |  |  | 21- | 5 | 2 | 5 | 4 |  |  |  | Accessories
[6 empty] | E2050.60 | E | 20 | 50 | .60 |  |  | 21- | 5 | 2 | 5 | 6 |  |  |  | Movable Multiple Seating
[6 empty] | E2050.90 | E | 20 | 50 | .90 |  |  | 21- | 5 | 2 | 5 | 9 |  |  |  | Other Movable Furnishings
| F. SPECIAL CONSTRUCTION & DEMOLITION |  |  |  |  | F | F | [5 empty] | 21- | 6 | [6 empty] | SPECIAL CONSTRUCTION & DEMOLITION
[6 empty] | F10 | F | 10 |  |  |  |  | 21- | 6 | 1 | [5 empty] | Special Construction
[6 empty] | F1010 | F | 10 | 10 |  |  |  | 21- | 6 | 1 | 1 |  |  |  |  | Integrated Construction
|  | 14.97 | Other Special Construction | 13 30 00 | Special Structures | F1020 | F | 10 | 20 |  |  |  | 21- | 6 | 1 | 2 |  |  |  |  | Special Structures
[6 empty] | F1030 | F | 10 | 30 |  |  |  | 21- | 6 | 1 | 3 |  |  |  |  | Special Function Construction
[6 empty] | F1050 | F | 10 | 50 |  |  |  | 21- | 6 | 1 | 5 |  |  |  |  | Special Facility Components
[6 empty] | F1060 | F | 10 | 60 |  |  |  | 21- | 6 | 1 | 6 |  |  |  |  | Athletic and Recreational Special Construction
[6 empty] | F1080 | F | 10 | 80 |  |  |  | 21- | 6 | 1 | 8 |  |  |  |  | Special Instrumentation
[6 empty] | F20 | F | 20 |  |  |  |  | 21- | 6 | 2 | [5 empty] | Facility Remediation
[6 empty] | F2010 | F | 20 | 10 |  |  |  | 21- | 6 | 2 | 1 |  |  |  |  | Hazardous Materials Remediation
[6 empty] | F30 | F | 30 |  |  |  |  | 21- | 6 | 3 | [5 empty] | Demolition
[6 empty] | F3010 | F | 30 | 10 |  |  |  | 21- | 6 | 3 | 1 |  |  |  |  | Structure Demolition
[6 empty] | F3030 | F | 30 | 30 |  |  |  | 21- | 6 | 3 | 3 |  |  |  |  | Selective Demolition
[6 empty] | F3050 | F | 30 | 50 |  |  |  | 21- | 6 | 3 | 5 |  |  |  |  | Structure Moving
| G. BUILDING SITEWORK |  |  |  |  | G | G | [5 empty] | 21- | 7 | [6 empty] | BUILDING SITEWORK
[6 empty] | G10 | G | 10 |  |  |  |  | 21- | 7 | 1 | [5 empty] | Site Preparation |  | C |  |  | 200 | C |  | 200 | C |  | 300 | C |  | 300 | C
|  | 11.2 | GRADING, SITE WORK, DRAINAGE AND SEWERS | 31 11 00 | Clearing and grubbing | G1010 | G | 10 | 10 |  |  |  | 21- | 7 | 1 | 1 |  |  |  |  | Site Clearing
[6 empty] | G1020 | G | 10 | 20 |  |  |  | 21- | 7 | 1 | 2 |  |  |  |  | Site Elements Demolition
[6 empty] | G1030 | G | 10 | 30 |  |  |  | 21- | 7 | 1 | 3 |  |  |  |  | Site Element Relocations
[6 empty] | G1050 | G | 10 | 50 |  |  |  | 21- | 7 | 1 | 5 |  |  |  |  | Site Remediation
[6 empty] | G1070 | G | 10 | 70 |  |  |  | 21- | 7 | 1 | 7 |  |  |  |  | Site Earthwork
[6 empty] | G107010 | G | 10 | 70 | 10 |  |  | 21- | 7 | 1 | 7 | 1 |  |  |  | Grading
[6 empty] | G20 | G | 20 |  |  |  |  | 21- | 7 | 2 | [5 empty] | Site Improvements |  | C |  |  | 200 | C |  | 200 | C |  | 300 | C |  | 400 | C
[6 empty] | G2010 | G | 20 | 10 |  |  |  | 21- | 7 | 2 | 1 |  |  |  |  | Roadways
[6 empty] | G2020 | G | 20 | 20 |  |  |  | 21- | 7 | 2 | 2 |  |  |  |  | Parking Lots
|  | 11.93 | Paved Surfaces | 32 10 00 | Bases, Ballasts, and Paving | G2020.10 | G | 20 | 20 | .10 |  |  | 21- | 7 | 2 | 2 | 1 |  |  |  | Parking Lot Pavement
[6 empty] | G2020.20 | G | 20 | 20 | .20 |  |  | 21- | 7 | 2 | 2 | 2 |  |  |  | Parking Lot Curbs and Gutters
[6 empty] | G2020.40 | G | 20 | 20 | .40 |  |  | 21- | 7 | 2 | 2 | 4 |  |  |  | Parking Lot Appurtenances
[6 empty] | G2030 | G | 20 | 30 |  |  |  | 21- | 7 | 2 | 3 |  |  |  |  | Pedestrian Plazas and Walkways
[6 empty] | G2040 | G | 20 | 40 |  |  |  | 21- | 7 | 2 | 4 |  |  |  |  | Airfields
[6 empty] | G2050 | G | 20 | 50 |  |  |  | 21- | 7 | 2 | 5 |  |  |  |  | Athletic, Recreational, and Playfield Areas
[6 empty] | G2060 | G | 20 | 60 |  |  |  | 21- | 7 | 2 | 6 |  |  |  |  | Site Development
[6 empty] | G2080 | G | 20 | 80 |  |  |  | 21- | 7 | 2 | 8 |  |  |  |  | Landscaping
[6 empty] | G30 | G | 30 |  |  |  |  | 21- | 7 | 3 | [5 empty] | Liquid and Gas Site Utilities |  | C |  |  | 200 | C |  | 200 | C |  | 300 | C |  | 300 | C
[6 empty] | G3010 | G | 30 | 10 |  |  |  | 21- | 7 | 3 | 1 |  |  |  |  | Water Utilities
[6 empty] | G3010.10 | G | 30 | 10 | .10 |  |  | 21- | 7 | 3 | 1 | 1 |  |  |  | Site Domestic Water Distribution
[6 empty] | G3010.30 | G | 30 | 10 | .30 |  |  | 21- | 7 | 3 | 1 | 3 |  |  |  | Site Fire Protection Water Distribution
|  |  |  | 33 30 00 | Sanitary sewers | G3020 | G | 30 | 20 |  |  |  | 21- | 7 | 3 | 2 |  |  |  |  | Sanitary Sewerage Utilities
[6 empty] | G3020.20 | G | 30 | 20 | .20 |  |  | 21- | 7 | 3 | 2 | 2 |  |  |  | Sanitary Sewerage Piping
|  | 12.65 | Manholes (Formed in Place) | 33 39 13 | Sanitary Manholes | G3020.50 | G | 30 | 20 | .50 |  |  | 21- | 7 | 3 | 2 | 5 |  |  |  | Sanitary Sewerage Structures
[6 empty] | G3030 | G | 30 | 30 |  |  |  | 21- | 7 | 3 | 3 |  |  |  |  | Storm Drainage Utilities
[6 empty] | G3050 | G | 30 | 50 |  |  |  | 21- | 7 | 3 | 5 |  |  |  |  | Site Energy Distribution
[6 empty] | G3060 | G | 30 | 60 |  |  |  | 21- | 7 | 3 | 6 |  |  |  |  | Site Fuel Distribution
[6 empty] | G3090 | G | 30 | 90 |  |  |  | 21- | 7 | 3 | 9 |  |  |  |  | Liquid and Gas Site Utilities Supplementary Components
[6 empty] | G40 | G | 40 |  |  |  |  | 21- | 7 | 4 | [5 empty] | Electrical Site Improvements |  | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
[6 empty] | G4010 | G | 40 | 10 |  |  |  | 21- | 7 | 4 | 1 |  |  |  |  | Site Electric Distribution Systems
[6 empty] | G4050 | G | 40 | 50 |  |  |  | 21- | 7 | 4 | 5 |  |  |  |  | Site Lighting
[6 empty] | G50 | G | 50 |  |  |  |  | 21- | 7 | 5 | [5 empty] | Site Communications |  | E |  |  | 200 | E |  | 200 | E |  | 300 | E |  | 500 | E
[6 empty] | G5010 | G | 50 | 10 |  |  |  | 21- | 7 | 5 | 1 |  |  |  |  | Site Communications Systems
[6 empty] | G90 | G | 90 |  |  |  |  | 21- | 7 | 9 | [5 empty] | Miscellaneous Site Construction
[6 empty] | G9010 | G | 90 | 10 |  |  |  | 21- | 7 | 9 | 1 |  |  |  |  | Tunnels
[13 empty] | 23- | [7 empty] | Products
[13 empty] | 23- | 13 | [6 empty] | Structural and Exterior Enclosure Products
[13 empty] | 23- | 13 | 23 | [5 empty] | Mechanical Fasteners, Adhesives, and Sealants
[13 empty] | 23- | 13 | 23 | 11 |  |  |  |  | Mechanical Fasteners
[13 empty] | 23- | 13 | 31 | [5 empty] | Structural Concrete Products
[13 empty] | 23- | 13 | 31 | 17 |  |  |  |  | Concrete Formwork

## Civil Matrix
BIM LEVEL OF DEVELOPMENT MATRIX 2 - CIVIL WORKS
Civil Information Modeling refers to Civil Work Models generated using tools such as Autodesk Civil3D and Bentley Systems InRoads.
Model Element Author (MEA) | [19 empty] | Level of Development (LOD) |  |  | LOD Interpretation
MEA | Discipline | [18 empty] | LOD 100 | The Model element may be graphically represented in the model with a symbol or other generic representation, but does not satisfy the requirements for LOD 200. Information related to the Model Element (i.e. Cost per square foot, tonnage of HVAC etc.) can be derived from othe Model Elements |  | Approximate location using 2D centerline or surface, rough excavation
A | Architectural | [18 empty] | LOD 200 | The Model Element is graphically represented within the Model as a generic system, object, or assembly with approximate quantities, size, shape, location and orientation. Non-graphic information may also be attached to the Model Element. |  | Approximate location using 3D centerline/ surface/ model element. 3D surface based on manual points or 2D surface specifying substructure, rough excavation along 3D model element.
S | Structural | [18 empty] | LOD 300 | The Model Element is graphically represented within the Model as a specific system, object or assembly in terms of quantity, size, shape, location, and orientation. Non-graphic information may also be attached to the Model Element. |  | Accurate location using 3D model element/ surface. 3D surface based on point cloud or 3D surface with connection to terrain, excavation as 3D surface with preliminary sloping.
C/S | Civil / Structural | [18 empty] | LOD 350 | The Model Element is graphically represented within the Model as a specific system, object, or assembly in terms of quantity, size, shape, location, orientation, and interfaces with other building systems. Non-graphic information may also be attached to the Model Element |  | Final location using 3D model element/ surface post coordination with nearby elements. 3D surface based on point cloud or 3D surfaces final sloping down to terrain, excavation as 3D surface with final sloping/ walls.
A/S | Architectural / Structural | [18 empty] | LOD 400 | The Model Element is graphically represented within the Model as a specific System, object or assmbly in terms of size, shape, location, quantity, and orientation with detailing, fabrication, assembly and installation information. Non-graphic information may also be attached to Model Element |  | Final location using 3D model element with detail and accuracy for fabrication/ construction, post coordination with nearby elements. 3D surface based on point cloud and 3D surfaces sloping down to terrain, excavation as 3D surface with final sloping/ walls.
A/M | Architectural / Mechanical | [18 empty] | LOD 500 | The Model is a field verified representation in terms of size, shape, location, quantity, and orientation. Non-graphic information may also be attached to the Model Elements. |  | Final location using 3D model element is field verified.
M | Mechanical
E | Electrical | [18 empty] | RECORD/ HANDOVER of the Model(s) to support the population and implementation of the Asset Information Management System (AIM) per Project Agreement and outlined in the discipline specific DSRs. See Asset Information Handover section of BIM Execution Strategy (Exhibit D.) for more information.
C | Civil
N/A | Not applicable
For model contents definitions for stages see EPM-KE0-PR-000010 - 3D Model Review Procedure
[20 empty] | Use on this project | This work is licensed under the Creative Commons Attribution-NonCommercial 4.0 International License Project stages redefined to Mashroat Design Review Procedure - EPM-KE0-PR-000002 |  |  |  |  | 30% Design Review |  |  | 60% Design Review |  |  | 90% Design Review
| Model Object Category | Cost Code | Cost Code Title | MasterFormat | MasterFormat Description | CODE | Uniformat Level | [6 empty] | Omniclass Level | [7 empty] | Details | Model | Object | Data Information / | Stage |  |  | Stage |  |  | Stage |  |  | RECORD/HANDOVER
[13 empty] | Table | [9 empty] | Element |  | Detailed Component | Date: |  |  | Date: |  |  | Date: |  |  | Date:
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  | Author |  |  | LOD | MEA | Notes | LOD | MEA | Notes | LOD | MEA | Notes | LOD | MEA | Notes
[21 empty] | INFORMATION |  | (MEA)
[15 empty] | 73 | 11 | 13 |  |  |  | Model Annotation Content
[15 empty] | 73 | 11 | 13 | 11 |  |  | Properties
[15 empty] | 73 | 11 | 13 | 11 | 19 |  | Zones/Rooms/Spaces
[15 empty] | 73 | 11 | 13 | 17 |  |  | Symbols
[15 empty] | 73 | 11 | 13 | 17 | 11 |  | Horizontal Grids
[15 empty] | 73 | 11 | 13 | 17 | 13 |  | Vertical Levels
ELEMENTS
| P. TERRAIN |  |  |  |  | P | A | [13 empty] | TERRAIN |  | C | X | 0 | 200 | C |  | 300 | C |  | 350 | C |  | 350 | C
| Q. LEVELLING/GRADINGS |  |  |  |  | Q | B | [13 empty] | LEVELLING/GRADINGS |  | C | X | 0 | 200 | C |  | 300 | C |  | 400 | C |  | 500 | C
| R. FOUNDATION EXCAVATION |  |  |  |  | R | C | [13 empty] | FOUNDATION EXCAVATION |  | C | X | 0 | 200 | C |  | 300 | C |  | 400 | C |  | 500 | C
| S. PIPEWORK EXCAVATION |  |  |  |  | S | D | [13 empty] | PIPEWORK EXCAVATION |  | C | X | 0 | 200 | C |  | 300 | C |  | 400 | C |  | 500 | C
| T. ROAD AND RAILWAY |  |  |  |  | T | E | [13 empty] | ROAD AND RAILWAY |  | C | X | 0 | 300 | C |  | 300 | C |  | 400 | C |  | 500 | C
| U. ROAD AND RAILWAY EQUIPMENT |  |  |  |  | U | E | [13 empty] | ROAD AND RAILWAY EQUIPMENT |  | C | X | 0 | 200 | C |  | 200 | C |  | 400 | C |  | 500 | C
| V. EXISTING PIPEWORK IN TERRAIN |  |  |  |  | V | G | [13 empty] | EXISTING PIPEWORK IN TERRAIN |  | C | X | 0 | 200 | C |  | 200 | C |  | 400 | C |  | 500 | C
|  | 11.2 | GRADING, SITE WORK, DRAINAGE AND SEWERS | 31 11 00 | Clearing and grubbing
| W. DRAINAGE |  |  |  |  | W | H | [13 empty] | DRAINAGE |  | C | X | 0 | 200 | C |  | 300 | C |  | 400 | C |  | 500 | C
|  | 11.2 | GRADING, SITE WORK, DRAINAGE AND SEWERS | 31 11 00 | Clearing and grubbing

## Lists (hidden)
VPD Requirements | IDP - Categories | Yes / No | Functions
2D Documentation Generation | Commercial Management | Y | Document Control
3D Coordination of Trades | Competency Assessment | N | Engineering
4D Phase Planning | Information Management |  | Construction
4D with data connections |  |  | Procurement
Access Data in the Field |  |  | Project Controls
Advanced Work Packaging |  |  | Start Up
Asset Information Modeling (O&M) |  |  | Project Management
BIM Object Library
CAD Authoring
Capture Asset Management Information for Turnover
Capture Engineering, Procurement and Constructions information for Start-up
Clash Detection
Complete Digital Field Inspections
Develop 3D Model
Development of SR/MR for Construction Scope
Development of SR/MR for Engineering Scope
Digital Supply Chain Integration with Construction
Digital Supply Chain Integration with Engineering
Document Control
ES&H / CDM Management
Existing Conditions Modeling
Flowdown BIM Requirements to Subcontractors
Generate Bill of Quantities
Material Management/Quantity Tracking
Model Data Checking
Perform Engineering MTO/QTO
Project Common Data Environment
Project Performance Dashboard
Requirements Management
Tracking of Field Materials and Issuing MWRs
Quantity Tracking and Reporting