| PROJECT NAME: |  |  |  |  |  | DISCIPLINE: |  |  | REV. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Stage No. | Requirements |  |  |  |  |  | MANDATORY | Completeness Status |  |  |
|  |  |  |  |  |  |  |  | N/A | YES | NO |
| - Initial Planning |  |  |  |  |  |  |  |  |  |  |
| 1.1 | The preliminary commissioning Owner Project Requirements are being established, Refer to EPM-KT0-GL-000003_002 T&C guidline part#3.1.1 |  |  |  |  |  | √ |  |  |  |
| 1.2 | The preliminary commissioning plan is being developed which should include at a minimum commissioning budget and schedule. Refer to EPM-KT0-PR-000006_002 part# 6.1 |  |  |  |  |  | √ |  |  |  |
| 1.3 | The Commissioning team of the client has been identified and formed. |  |  |  |  |  |  |  |  |  |
| 1.4 | Initial stakeholder engagement and permitting plans have been identified. |  |  |  |  |  |  |  |  |  |
| 1.5 | Initial handover plan is prepared |  |  |  |  |  | √ |  |  |  |
| - Tender for Design |  |  |  |  |  |  |  |  |  |  |
| 2.1 | Commissioning scope and plan included in the designer scope of work |  |  |  |  |  | √ |  |  |  |
| 2.3 | Required resources (contractor and consultants) of testing and commissioning have been included in the scope if needed. |  |  |  |  |  |  |  |  |  |
| - Design |  |  |  |  |  |  |  |  |  |  |
| INFO. | The responsibilities of the commissioning team during the design review and the required deliverables during the design stage are shown in Attachment 1.1, refer to EPM-KT0-PR-000006_002 : Testing and Commissioning Flow Charts/Project Stage Gates |  |  |  |  |  |  |  |  |  |
| 3.1 | The commissioning owner project requirements have been reviewed for clarity and completeness to recommend improvements (if any). |  |  |  |  |  | √ |  |  |  |
| 3.2 | Basis of Design is developed, reviewed, and accepted. |  |  |  |  |  | √ |  |  |  |
| 3.3 | Commissioning methodology is prepared and reviewed |  |  |  |  |  | √ |  |  |  |
| 3.4 | Constructability review is considered. |  |  |  |  |  |  |  |  |  |
| 3.5 | Commissionability review is considered. |  |  |  |  |  | √ |  |  |  |
| 3.6 | Stakeholder engagement plan has been updated. |  |  |  |  |  | √ |  |  |  |
| 3.7 | O/M training requirements have been defined |  |  |  |  |  | √ |  |  |  |
| 3.8 | Initial handover plan including turnover packages has been updated. |  |  |  |  |  | √ |  |  |  |
| 3.9 | Design turnover packages have been prepared and approved |  |  |  |  |  | √ |  |  |  |
| - Tender for Construction |  |  |  |  |  |  |  |  |  |  |
| 4.1 | Commissioning scope of work is included in the construction scope of work |  |  |  |  |  | √ |  |  |  |
| 4.2 | Required testing and commissioning resources are included in the scope of work |  |  |  |  |  | √ |  |  |  |
| - Construction |  |  |  |  |  |  |  |  |  |  |
| 5.1 | - The Testing and Commissioning plan and Methodology are developed/updated reviewed and approved. |  |  |  |  |  | √ |  |  |  |
| 5.2 | The testing and commissioning schedule has been identified and approved |  |  |  |  |  | √ |  |  |  |
| 5.3 | Training for O/M personnel has been planned and implemented accordingly |  |  |  |  |  |  |  |  |  |
| 5.4 | - The required construction turnover packages have been prepared, verified, and approved. |  |  |  |  |  | √ |  |  |  |
| - Testing and Commissioning |  |  |  |  |  |  |  |  |  |  |
| 6.1 | - The main contractor has conducted the integration works of the system successfully along with verification and approval of the client representative. |  |  |  |  |  | √ |  |  |  |
| 6.2 | - O&M Service Contract is activated as required |  |  |  |  |  | √ |  |  |  |
| 6.3 | - Training for O/M personnel has been performed as required. |  |  |  |  |  | √ |  |  |  |
| 6.4 | - Stakeholder engagement and permitting plan have been updated |  |  |  |  |  |  |  |  |  |
| 6.5 | - All Testing and Commissioning turnover packages are completed and approved as per plan. |  |  |  |  |  | √ |  |  |  |
| 6.6 | - Initial handover certificate has been issued |  |  |  |  |  | √ |  |  |  |
| - Handover & Closeout |  |  |  |  |  |  |  |  |  |  |
| 7.1 | - Schedule and plan for final acceptance are prepared and approved accordingly |  |  |  |  |  | √ |  |  |  |
| 7.2 | - Final handover certificate has been issued |  |  |  |  |  | √ |  |  |  |
| 7.3 | - The main contractor has submitted a clear demobilization plan and it is approved |  |  |  |  |  |  |  |  |  |
| No. | Reviewer's Comments (against each SLD) |  |  | Resolution |  |  |  |  |  |  |
| Originator's Name / Signature and Date: |  |  |  |  | Checker's Name / Signature and Date: |  |  |  |  |  |