## Project RRTM
[6 empty] | Rev | Date | By | Chk | Rvd | App | Aut | Description
Contractor Project Records Retention
|  |  |  | & Turnover Matrix Template |  | XXX | DD/MM/YYYY | [5 empty] | Issued for XXX
Initial
Document Description |  | Retention Code | Responsible Department | Comments | Contractor Retention Requirements |  |  |  | Contractor Turnover to Entity Requirements
[5 empty] | HARD COPY Originals | SOFT COPY |  | Version Required | HARD COPY Originals |  |  | SOFT COPY |  | Version Required
1.0 Project Management Documents
| Contract Copy |  | Project Management |  | ü | ü | [5 empty] | ü
| All Specifications received from EPMO/PMT |  | Project Management |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| All Other Contract documents received from EPMO/PMT |  | Project Management |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Approved Change Orders |  | Project Management |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| EPMO/PMT Conference Notes and Meeting Notes |  | Project Management |  | ü | ü | [5 empty] | ü
| Letters Issued to PMT |  | Project Management |  | ü | ü | [5 empty] | ü
| Letters Received from PMT |  | Project Management |  | ü | ü | [5 empty] | ü
| Letters to A/E Consultant |  | Project Management |  | ü | ü | [5 empty] | ü
| Letters from A/E Consultant |  | Project Management |  | ü | ü | [5 empty] | ü
| Other Letters Issued |  | Project Management |  | ü | ü | [5 empty] | ü
| Other Letters Received |  | Project Management |  | ü | ü | [5 empty] | ü
| Internal and external email communication |  | Project Management |  | ü | ü
| Interoffice Memoranda |  | Project Management |  | ü | ü
| Photographs, Negatives & Video (Logs maintained by DC) |  | Project Management |  | ü | ü | [5 empty] | ü
| Project Organization chart |  | Project Management |  | ü | ü | [5 empty] | ü
| Project Team CVs |  | Project Management |  | ü | ü | [5 empty] | ü
| Project Execution Plan |  | Project Management |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Project Specific Procedures |  | Project Management |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Project Presentations |  | Project Management |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Correspondence with General Entity |  | Project Management |  | ü | ü | [5 empty] | ü
| Document and Data furnished by Entity, such as Entity Design Standards, Study Packs, Toolkits, etc. per Contract Requirement |  | Project Management |  | ü | ü | [5 empty] | ü
| Other Document and Data furnished by Entity for Information and Use |  | Project Management |  | ü | ü | [5 empty] | ü
| CDs from Entity for Contractual Deliverables or Information/Use |  | Project Management |  | ü | ü | [5 empty] | ü
| Insurance Policies/Warranties |  | Project Management |  | ü | ü |  |  | ü |  |  | ü
Construction - General
| Site Instructions |  | Construction |  | N/A | ü | [5 empty] | ü |  | Final Rev
| Stop Work Orders |  | Construction |  | ü | ü | [5 empty] | ü
| Closed Non-Conformance NCRs |  | Construction |  | ü | ü | [5 empty] | ü
| Closed Punch lists |  | Construction |  | ü | ü | [5 empty] | ü
| Site Weekly Meetings Minutes of Meetings (MOM) |  | Construction |  | ü | ü | [5 empty] | ü
| Other MOMs |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü
| Approved Shop Drawings |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü |  | Final Rev
| As-Built Drawings, including singles lines, area classification, P&ID |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü |  | Final Rev
| Approved Material Approval Submissions (MAS) |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü |  | Final Rev
| Approved Material Inspection Requests (MIR) |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü |  | Final Rev
| Approved Requests for Inspections (RFI) |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü
| Approved Final RFIs |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü
| Approved Tests Reports, including Factory Acceptance Tests (FAT), Manufacturer's Test Reports (MTR) and Site Acceptance Tests (SAT) |  | Construction |  | ü | ü |  | All Revs |  |  |  | ü
Construction - Electrical Turnover Packages (See Note 1)
| Lighting: Internal |  | Construction |  | ü | ü | [5 empty] | ü
| Lighting: External |  | Construction |  | ü | ü | [5 empty] | ü
| Automatic Lighting Control System |  | Construction |  | ü | ü | [5 empty] | ü
| Power: Equipment power supply |  | Construction |  | ü | ü | [5 empty] | ü
| Power: Conventional power outlets |  | Construction |  | ü | ü | [5 empty] | ü
| Earthing |  | Construction |  | ü | ü | [5 empty] | ü
| Grounding |  | Construction |  | ü | ü | [5 empty] | ü
| Lightning Protection |  | Construction |  | ü | ü | [5 empty] | ü
| Normal power distribution network: MV network |  | Construction |  | ü | ü | [5 empty] | ü
| Normal power distribution network: LV network |  | Construction |  | ü | ü | [5 empty] | ü
| Electrical Power Management System |  | Construction |  | ü | ü | [5 empty] | ü
| Emergency power generation and distribution network: MV network |  | Construction |  | ü | ü | [5 empty] | ü
| Emergency power generation and distribution network: LV network |  | Construction |  | ü | ü | [5 empty] | ü
| Uninterruptible Power supply (UPS) |  | Construction |  | ü | ü | [5 empty] | ü
| Isolated Power system |  | Construction |  | ü | ü | [5 empty] | ü
| Electrical Systems studies: |  | Construction |  | ü | ü | [5 empty] | ü
| a) Detailed Load Calculation. |  | Construction |  | ü | ü | [5 empty] | ü
| b) Load flow and stability. |  | Construction |  | ü | ü | [5 empty] | ü
| c) short circuit study. |  | Construction |  | ü | ü | [5 empty] | ü
| d) Harmonic study. |  | Construction |  | ü | ü | [5 empty] | ü
| e) Load Shedding scheme. |  | Construction |  | ü | ü | [5 empty] | ü
| Escalators, Elevators, Hoists |  | Construction |  | ü | ü | [5 empty] | ü
Construction - Low Current Turnover Packages (See Note 1)
| Fire Detection and Alarm |  | Construction |  | ü | ü | [5 empty] | ü
| Security Access Control |  | Construction |  | ü | ü | [5 empty] | ü
| IPCCTV |  | Construction |  | ü | ü | [5 empty] | ü
| Wireless Master Clock |  | Construction |  | ü | ü | [5 empty] | ü
| VOIP Communication |  | Construction |  | ü | ü | [5 empty] | ü
| Wireless network |  | Construction |  | ü | ü | [5 empty] | ü
| Structured Cabling |  | Construction |  | ü | ü | [5 empty] | ü
| IT ( Data) Network |  | Construction |  | ü | ü | [5 empty] | ü
| Nurse Call System |  | Construction |  | ü | ü | [5 empty] | ü
| Door Entry intercom and Access Control |  | Construction |  | ü | ü | [5 empty] | ü
| Audio/Visual |  | Construction |  | ü | ü | [5 empty] | ü
| Public address |  | Construction |  | ü | ü | [5 empty] | ü
| IPTV and CATV |  | Construction |  | ü | ü | [5 empty] | ü
| Digital signage |  | Construction |  | ü | ü | [5 empty] | ü
| Real Time Location |  | Construction |  | ü | ü | [5 empty] | ü
| Q-Matic |  | Construction |  | ü | ü | [5 empty] | ü
| Building Management System (BMS) |  | Construction |  | ü | ü | [5 empty] | ü
| Electrical Power Management System (EPMS) |  | Construction |  | ü | ü | [5 empty] | ü
| External Fiber optic connectivity |  | Construction |  | ü | ü | [5 empty] | ü
| LC Systems grounding and bonding |  | Construction |  | ü | ü | [5 empty] | ü
| Parking Management and Assistance |  | Construction |  | ü | ü | [5 empty] | ü
Construction - Mechanical Turnover Packages (See Notes 1, 2)
| 1. Heating, Ventilating, and Air Conditioning |  | Construction |  | ü | ü | [5 empty] | ü
| a. Ducting Distribution System |  | Construction |  | ü | ü | [5 empty] | ü
| b. Chilled Water Piping System |  | Construction |  | ü | ü | [5 empty] | ü
| c. Low Pressure Hot Water Piping System for VAV |  | Construction |  | ü | ü | [5 empty] | ü
| d. High Pressure Steam Piping System |  | Construction |  | ü | ü | [5 empty] | ü
| e. Low Pressure Steam Piping System (Clean Steam) |  | Construction |  | ü | ü | [5 empty] | ü
| f. Building Management System (BMS) |  | Construction |  | ü | ü | [5 empty] | ü
| 2. Domestic Water System |  | Construction |  | ü | ü | [5 empty] | ü
| a. Cold Water System |  | Construction |  | ü | ü | [5 empty] | ü
| b. Hot Water and Recirculation System |  | Construction |  | ü | ü | [5 empty] | ü
| 3. Drainage System |  | Construction |  | ü | ü | [5 empty] | ü
| a. Building Combined Soiled and Waste |  | Construction |  | ü | ü | [5 empty] | ü
| b. Building Rain Water |  | Construction |  | ü | ü | [5 empty] | ü
| c. External Drainage System |  | Construction |  | ü | ü | [5 empty] | ü
| d. Sewage Lifting Pumps |  | Construction |  | ü | ü | [5 empty] | ü
| 4. Treated Water System |  | Construction |  | ü | ü | [5 empty] | ü
| a. Reverse Osmosis |  | Construction |  | ü | ü | [5 empty] | ü
| b. Reverse Osmosis and De-ionized Water System |  | Construction |  | ü | ü | [5 empty] | ü
| c. Softened Water |  | Construction |  | ü | ü | [5 empty] | ü
| 5. Fire and Life Safety System- Mechanical |  | Construction |  | ü | ü | [5 empty] | ü
| a. Sprinkler and Stand Pipe System |  | Construction |  | ü | ü | [5 empty] | ü
| b. Smoke Control System |  | Construction |  | ü | ü | [5 empty] | ü
| c. Staircase Pressurization System |  | Construction |  | ü | ü | [5 empty] | ü
| d. Clean Agent – Novec and FM200 |  | Construction |  | ü | ü | [5 empty] | ü
| e. Double Interlock Pre-action System |  | Construction |  | ü | ü | [5 empty] | ü
| f. Kitchen Hood Suppression |  | Construction |  | ü | ü | [5 empty] | ü
| g. Drop Curtains |  | Construction |  | ü | ü | [5 empty] | ü
| h. Roll Up Fire Doors |  | Construction |  | ü | ü | [5 empty] | ü
| 6. Irrigation Water System- Treated Sewer Effluent |  | Construction |  | ü | ü | [5 empty] | ü
| 7. Gas Services (LPG, Medical) |  | Construction |  | ü | ü | [5 empty] | ü
| 8. Any remaining mechanical services, including underground services. |  | Construction |  | ü | ü | [5 empty] | ü
Construction - Other Documents
| Combined Underground Services drawings, as-built |  | Construction |  | ü | ü | [5 empty] | ü
| Cable Terminations Test Reports |  | Construction |  | ü | ü | [5 empty] | ü
| Cable Schedules |  | Construction |  | ü | ü | [5 empty] | ü
| Electrical Equipment Megger Sheets |  | Construction |  | ü | ü | [5 empty] | ü
| Calibrated Equipment Certifications |  | Construction |  | ü | ü | [5 empty] | ü
| Pipe Supports Calculations |  | Construction |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Test Reports (Other then what included in Turnover Packages) |  | Construction |  | ü | ü | [5 empty] | ü
| Calibrated Equipment Usage Logs |  | Construction |  | ü | ü | [5 empty] | ü
| Hydraulic Test Records - ASME, NFPA, Other |  | Construction |  | ü | ü | [5 empty] | ü
| Quality Control/Test Reports per site-specific procedures (not specified elsewhere) |  | Construction |  | ü | ü | [5 empty] | ü
| Field Radiographs |  | Construction |  | ü | ü | [5 empty] | ü
| Welding Procedures & Qualification Records (by Supplier) |  | Construction |  | ü | ü | [5 empty] | ü
| Welding Test records |  | Construction |  | ü | ü | [5 empty] | ü
| Logs - Concrete |  | Construction |  | ü | ü | [5 empty] | ü
| Concrete Placement Boundaries, Tests, Batch, & Records |  | Construction |  | ü | ü | [5 empty] | ü
| Visitor Records |  | Construction |  | ü | ü | [5 empty] | ü
Document Control
| Project Closeout Index |  | Document Control |  | ü | ü | [5 empty] | ü
| Project Storage/Archive Box List |  | Document Control |  | ü | ü | [5 empty] | ü
Engineering
| Calculations and Index |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Design Analysis (not including Calculations) |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Design Basis - All Revisions |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Design Verification Reports |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Engineering Study Report |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Engineering Studies |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Other Studies - Technical Only |  | Engineering |  | ü | ü | [5 empty] | ü |  | Final Rev
| CAD files (AutoCAD, Microstation) |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Engineering Software Application Programs - List used only |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Drawing Control Register |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Drawings - All Revisions |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Drawings - Electrical Cable Schedule |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Circuit & Raceway Schedule |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Drawings generated by Project |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Sketches |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Data Sheets |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Shop Drawings - All Revisions |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Mechanical Equipment List |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü
| Electrical Equipment List |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü
| Pipe Support Index |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü
| Valve Index |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü
| Geotechnical Records |  | Engineering |  | ü | ü |  | All Rev |  |  |  | ü |  | Final Rev
| Certificate of Occupancy |  | Engineering |  | ü | ü |  |  | ü |  |  | ü
ES&H
| Health and Safety Management Plan |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Emergency Response Plans |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Risk Assessments |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Personnel Injury/Medical History |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Safety and Health Historical Statistical and Research Reports |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| First Aid Logs |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Hazardous Work Permit & Log |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Safety Induction Training Records |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Safety Training Records |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| ID Badge/Security Cards Issue Records |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Security Incident Reports |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Security Investigation Files |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Material Safety Data Sheets |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Accident Reports & Investigations |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Safety Tool Box Meeting Records |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Project Induction/Orientation Booklet |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Project Induction/Orientation Training Records |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Security Incident Reports |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Security Investigation Files |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Material Safety Data Sheets |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Accident Reports & Investigations |  | ES&H |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
Project Controls
| Monthly Progress Reports |  | Project Controls |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Studies and Reports (including Engineering, Client-furnished, Technical, Consultant) |  | Project Controls |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Project Execution Plan |  | Project Controls |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Construction Schedules: Weekly, Bi-Weekly and Monthly updates |  | Project Controls |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Manpower Historical Curves |  | Project Controls |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
Procurement
| Incoming Supplier Submittals (before Review and Status) - this covers all supplier docs regardless of type of documents submitted. Supplier Docs shown under separate items in this document are those with supplier doc review completed and status items. |  | Procurement |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Manuals - System Operation (not included in Turnover Packages) |  | Procurement |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Materials Certification: steel reinforcement |  | Procurement |  | ü | ü | [5 empty] | ü
| Operations and Maintenance Manual (not included in Turnover Packages) |  | Procurement |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
| Spare Parts Lists (not included in Turnover Packages) |  | Procurement |  | ü | ü | [5 empty] | ü
| Supplier Welder Qualification/Certification |  | Procurement |  | ü | ü | [5 empty] | ü
| Suppliers Quality Assurance Plan (not included in Turnover Packages) |  | Procurement |  | ü | ü | [5 empty] | ü
| Supplier Specifications & Addenda -- All Revisions |  | Procurement |  | ü | ü | [5 empty] | ü
| Procurement Tracking report - Final Revision with History |  | Procurement |  | ü | ü |  | Final Rev |  |  |  | ü |  | Final Rev
Notes:
1 | Mechanical and Electrical System Turnover Package(s) shall include:
1. List of System and Equipment
2. Description of the system installed
3. Record drawings and documents
4. As Built drawings (redline mark-up and CAD version (with As-Built revision issue))
5. Warranty information for all systems, including individual product and equipment warranties
6. Approved Material Approval Submission (MAS)
7. Approved Material Inspection Requests (MIR)
8. Approved Tests Reports, including Factory Acceptance Tests (FAT), Manufacturer's Test Reports (MTR) and Site Acceptance Tests (SAT)
9. Approved Testing & Commissioning Reports
10. Operations & Maintenance (O&M) manuals
11. Training Manuals (with any Training Aids) and Training Reports
12. Software Turnover, including licenses, passwords, files and databases
13. Two Year Operating Spares List
14. Equipment Service Contracts, if applicable
2 | Low Current Systems Turnover Package(s) shall include:
1 . Operations & Maintenance (O&M) Manuals
2. As-Built drawings (redline mark-up and CAD version (with As-Built revision issue))
3. Record drawings and documents
3. Equipment drawings
4. Revised set of system wiring diagrams
5. Equipment manuals and cut sheets
6. Listing of devices, with serial numbers
7. Certificates of Compliance
8. Training Manuals (with any Training Aids) and Training Reports
9. Software Turnover, including licenses, passwords, files and databases
10. Licenses for all other devices and equipment
11. Warranty information for all systems, including individual product warranties
12. Approved Material Approval Submission (MAS)
13. Approved Material Inspection Requests (MIR)
14. Approved Tests Reports, including Factory Acceptance Tests (FAT), Manufacturer's Test Reports (MTR) and Site Acceptance Tests (SAT)
15. Approved Testing & Commissioning Reports
16. Two Year Operating Spare Parts list
17. Loose equipment keys
3 | List of Typical Main Mechanical Equipment:
1. Screw Air Cooled Chillers
2. Centralized Air Handling Units
3. Free Standing AHU
4. Precision Units
5. Boilers
6. Pumps
a. Chilled Water Pumps
b. Domestic Water Pumps
c. Condensate Pumps
d. Recirculation Pumps
e. Fire and Jockey Pumps
7. Heat Exchangers
8. Clean Steam Generators
9. Condensate Return Unit
10. Exhaust Fans
a. Isolation Jet Fans
b. Centrifugal Fans
c. In-line Fans
11. Fan Coil Units
12. Condensate Receiver and Tanks