Evidence Matrices Template - Project Outline Business Case

Document No. EPM-S00-TP-000007 Rev. 002

Document Submittal History:

| Rev.: | Rev Status | Date: | Entity | Prepared by: | Reviewed by: | Approved by: |
| --- | --- | --- | --- | --- | --- | --- |
| 00X | For XXXXX | DD/MM/YYYY | XXXXX | NAME | NAME | NAME |
| Signatures: |  |  |  |  |  |  |

THIS NOTICE MUST ACCOMPANY EVERY COPY OF THIS DOCUMENT

IMPORTANT NOTICE

This document, (“Document”) is the exclusive property of the Expenditure Efficiency & Projects Authority (“Expro”).

This Document should be read in its entirety including the terms of this Important Notice. The government entities may disclose this Document or extracts of this Document to their respective consultants and/or contractors, provided that such disclosure includes this Important Notice.

Any use or reliance on this Document, or extracts thereof, by any party, including government entities and their respective consultants and/or contractors, is at that third party’s sole risk and responsibility. Expro, to the maximum extent permitted by law, disclaim all liability (including for losses or damages of whatsoever nature claimed on whatsoever basis including negligence or otherwise) to any third party howsoever arising with respect to or in connection with the use of this Document including any liability caused by negligent acts or omissions.

This Document and its contents are valid only for the conditions reported in it and as of the date of this Document.

Table of Contents

1.0	Assessment of Delivery Approach	6

2.0	Business Case and Stakeholders	10

3.0	Review of Current Phase (IF APPLICABLE)	12

4.0	Readiness for next phase: Investment Decision	12

How to use this Template?

The template has an empty third column on the right-hand side. This should be completed to supply the required evidence listed in the second column. In most cases the evidence will be references to other documents or outcomes of workshops.

The evidence, should be available before the Gateway Review starts. The information is likely to be found in the documents suggested below, but may be located in other project documents or elsewhere in the Entity’s documentation system. Key documents:

- Project initiation document or equivalent, along with the Project Brief with the project’s mandate, broad scope and the need for change, e.g. Strategic Outline Case;

- Cost report on the project to date, against budget, and

- Draft high-level definition of the business requirements and total scope of change.

The Evidence Matrices should support the Gateway Review, whose purposes is:

- Confirm the Outline Business Case now the project is fully defined;

- Confirm that the objectives and desired outputs of the project are still aligned with the programme to which it contributes;

- Ensure that the delivery strategy is robust and appropriate;

- Ensure that the project’s plan through to completion is appropriately detailed and realistic, including any contract management strategy;

- Ensure that the project controls and organization are defined, financial controls are in place and the resources are available;

- Confirm funding availability for the whole project;

- Confirm that the development and delivery approach and mechanisms are still appropriate and manageable;

- If appropriate, check that the supplier market capability and track record are fully understood (or existing supplier’s capability and performance), and that there will be an adequate competitive response from the market to the requirement;

- Confirm that the project will facilitate good client/supplier relationships;

- For a procurement project, confirm that there is an appropriate procurement plan in place that will ensure compliance with legal requirements and all applicable EU rules, while meeting the project’s objectives and keeping procurement timescales to a minimum;

- Confirm that appropriate project performance measures and tools are being used;

- Confirm that there are plans for risk management, issue management (business and technical) and that these plans will be shared with suppliers and/or delivery partners;

- Confirm that quality procedures have been applied consistently since the previous Review;

- For IT-enabled projects, confirm compliance with IT and information security requirements, and IT standards;

- For construction projects, confirm compliance with health and safety and sustainability requirements;

- Confirm that internal organizational resources and capabilities will be available as required for future phases of the project;

- Confirm that the stakeholders support the project and are committed to its success, and

- Evaluation of actions taken to implement recommendations made in any earlier assessment of deliverability.

# Assessment of Delivery Approach

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| 1.1 Have all the relevant options for delivery been investigated and do these consider both the business needs of the organization and address relevant government priorities? | - Examination and assessment of options, including the use of internal resources. |  |
| 1.2 Are the business needs clearly understood by the client organization and likely to be understood by those involved in delivery? | Detailed output/outcome-based definition of requirements Specification to include key success factors to show how achievement of outputs/outcomes will be assessed Appropriate quality criteria applied to information for the delivery organization (internal or external). |  |
| 1.3 Are the project outputs/outcomes accurately reflected in the requirement specification? | Depending on the nature of the delivery, an appropriate form of requirement specification reviewed and endorsed by stakeholders - Appropriate mechanism to articulate the requirement to potential suppliers, internal or external, quality assured to ensure that suppliers will understand what is wanted. |  |
| 1.4 Where appropriate, have options for the procurement route been evaluated, including sources of supply? | All appropriate sourcing options examined (e.g. use of internal resources, single or multiple suppliers; opportunities for collaboration, Shared Services, use of existing frameworks, etc.). For construction projects, evidence that integrated procurement routes have been fully evaluated. Where PPP is the proposed option, confirmation that it is appropriate Comparison with similar projects and analysis, supported by commercial intelligence on market capability Reasons for selecting sourcing options documented and justified. |  |

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| 1.5 Will the project be attractive to the market? | Detailed market soundings taken, including an examination of recent similar procurements by others or a commentary on the capacity of the market and the nature of the project’s likely suppliers Initial assessment of likely suppliers An assessment of market capacity to deliver An assessment of the competitive interest in the requirement If appropriate, assurance that the organization has adequate expertise and capacity to undertake internal delivery of the requirement Analysis of potential variations or innovations. |  |
| 1.6 Has the proposed procurement procedure been evaluated? | Reasons for following this procedure understood, related risks evaluated (such as impact on timescales and bid costs for suppliers), decision justified and documented If appropriate, an electronic reverse auction or a Dynamic Purchasing System has been considered and the risks and benefits evaluated Legal advice has been sought on any procurement approach |  |
| 1.7 Is the selected delivery strategy defined and endorsed? | Delivery strategy clearly defined, showing reasons for selection and agreed with stakeholders Evidence that government initiatives aimed at achieving excellence in Construction and Transformational Government have been considered Evidence that business continuity and future exit, handover and transition strategies have been considered at high level Confirmation of development, involvement and endorsement of the delivery strategy by the appropriate individuals Strategy to include, as appropriate: description of the key objectives, constraints (e.g. timescale), funding mechanism and risk allocation; the delivery route (how the strategy will be achieved) including sourcing option and contract strategy; procurement procedure time plan to include timetable laid down by procurement rules and time needed for pre-procurement activities, implementation and contingency in the event of unavoidable slippage, with milestones; assessment of marketplace/potential suppliers; the roles, resources and skills needed to manage the delivery strategy; alignment with plans for implementation Procurement innovation and sustainability issues have been considered. |  |

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| 1.8 Have the factors that influence the delivery strategy been addressed? | Documented evidence that key factors influencing the delivery strategy have been considered Evidence that efficiency and predictability of delivery process have been considered, with a process in place for addressing the impact of any deviation from the plan and timetable, and plans for two-way communications with stakeholders and suppliers. |  |
| 1.9 Will the delivery strategy facilitate communication and co-operation between all parties involved? | Communication strategy and support mechanisms in place Evidence that the delivery strategy will include: - early involvement of suppliers to ensure the design is fully informed by the delivery process - clearly defined performance criteria with key performance indicators and a system for measuring performance |  |
| 1.10 Is there adequate knowledge of existing and potential suppliers? Who are the suppliers most likely to succeed? | Evidence showing that adequate knowledge of existing and potential suppliers has been considered Evidence of commercial market intelligence, market sources and potential suppliers Evidence of track records from public and private sector considered (public sector’s ability as a customer to work in this way; private sector track record in meeting similar or equivalent business need) Indications of the types of suppliers most likely to succeed in delivering the required outcomes. |  |

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| 1.11 Is the contract management strategy robust? | Contract management strategy takes account of key factors such as the required ‘intelligent customer’ skills, proposed relationship, management of single or multiple suppliers Evidence of continuity of key project personnel. |  |
| 1.12 Has the project team complied with procurement laws? | The Tender Notice is reviewed, shown to be complete and containing an accurate description. For construction projects, includes requirement for suppliers to provide relevant health and safety information; specification includes government sustainability commitments Implications of the requirement thoroughly considered (e.g. ensuring take-up of new services by the citizen), with contingency plans for phasing out current ways of providing the service Pre-tender Qualification produced in accordance with national laws, and reviewed/accepted by the project |  |
| 1.13 Is the evaluation strategy (including how to demonstrate value for money) accepted by stakeholders and compliant with procurement rules? | Evaluation criteria and model(s) approved by stakeholders Key evaluation criteria linked to business objectives and given appropriate weighting Financial and non-financial aspects of the evaluation separated out Evaluation criteria included in information to potential tenderers and priorities in meeting that need, where applicable (e.g. quality of service, innovation) For construction projects, appropriate weight given to health and safety, sustainability, design quality Where appropriate, the evaluation includes benchmarking the value for money offered by partnering, internal supplier or framework/call-off arrangement Consideration of contract duration, in relation to value for money and whole life costs Consideration of whether to act on behalf of other public sector organizations in the role of a Central Purchasing Body. |  |

# Business Case and Stakeholders

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| 2.1 Does the Business Case continue to demonstrate business need and contribution to the organization’s business strategy? | Continued confirmation that the project will meet business need (including confirmation that priorities remain unchanged where any external factors might have an effect) Confirmation that the objectives and desired outputs of the project are still aligned with the programme to which it contributes, if appropriate. |  |
| 2.2 Is the preferred way forward still appropriate? | Continued confirmation of the way forward, supported by assessment based on indicative assumptions about factors such as interdependencies with other programmes and projects, reliance on partners to deliver, availability of internal resources, etc. |  |
| 2.3 Is the proposed arrangement likely to achieve whole-life value for money? | Bases for calculating costs (value of requirements) and comparison of delivery approaches (e.g. tenders) agreed with key stakeholders Updated Business Case based on the full project definition, market assessment and initial benefits plan Delivery strategy reflected in Business Case Examination of sensitivities and financial implications of handling major risks; assessment of their effect on project return Projects that are not designed to achieve a financial return should include comparisons with similar successful projects to assess the potential to achieve value for money and to set targets. |  |
| 2.4 Are the costs within current budgets? Is the project’s whole-life funding affordable and supported by the key stakeholders? | Reconciliation of projected whole-life costs with available budget, reviewed and accepted or approved by key stakeholders Project costs within organization’s forecasted spending plans. |  |

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| 2.5 Is the organization still realistic about its ability to achieve a successful outcome? | Comparison with similar projects (and similar organizations); assessment of past track record in achieving successful change; plans to manage known weaknesses; where applicable, plans for incremental/modular approaches; contingency plans in place If the project crosses organizational boundaries: there are clear governance arrangements to ensure sustainable alignment with the business objectives of all organizations involved. |  |
| - 2.6 Is there a clear definition of the total project scope? | Updated document showing total project scope including business change, where applicable. |  |
| 2.7 Are the risks and issues relating to business change understood? Is there an initial plan to address these issues? | Risks and issues relating to business change logged, according to the Risk Management Procedure. Account has been taken of relevant impact assessment and appraisal issues such as Regulatory Impact, Sustainable Development and Environmental Appraisal. |  |
| - 2.8 Do stakeholders support the project? Is the organization still fully committed? | Documented involvement of and endorsement by stakeholders. |  |
| - 2.9 Are the benefits to be delivered by the project understood and agreed with stakeholders? Is there an initial plan for realising and evaluating benefits? | Benefits are clearly stated Initial plan for realising and evaluating delivery of benefits, showing costs offset by (e.g. improved quality of service and/or savings over the project’s expected life) Critical success factors for the project are still valid, and agreed with stakeholders. |  |

# Review of Current Phase (IF APPLICABLE)

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| - 3.1 Is the project under control? | Project running to schedule and costs within budget, as shown in project budget and timetable reports. |  |
| 3.2 What caused any deviations such as over or under-runs? | Reconciliations set against budget and time plan, and in accordance with risk allowances. |  |
| 3.3 What actions are necessary to prevent deviations recurring in other phases? | Analysis and plans documented in project management documentation that is continually reviewed and updated. |  |
| 3.4 Are there any assumptions documented at the previous Gateway Review that have not been verified? | Log of outstanding assumptions and plans to verify them; where applicable, classed and managed as issues. |  |

# Readiness for next phase: Investment Decision

| Areas to probe | Evidence expected | Evidence Supplied |
| --- | --- | --- |
| - 4.1 Is the project plan for the remaining stages realistic? | Clear objectives, deliverables and milestones for the next stage defined and signed off by stakeholders Recommendations from last Gateway Review actioned. |  |
| 4.2 Are the project’s timescales reasonable, and compliant with procurement rules? | Timescales are likely to meet business and legislative needs and have been verified with internal stakeholders and suppliers Comparisons with similar projects Where appropriate, written record available of compliance with procurement rules in relation to all procurement project decisions taken Analysis of the effects of any slippage that will affect the project (e.g. procurement costs) and suppliers (e.g. bid costs), with supporting sensitivity analysis. |  |

| Areas to probe | - Evidence expected | Evidence Supplied |
| --- | --- | --- |
| 4.3 What are the arrangements for the next stage of the project? Have its activities been defined and resourced? | Plan showing roles, responsibilities, training requirements, internal and external resources, skills requirements and any project management mentoring resources available Involvement from a business, user and technical perspective A suitable/appropriate plan for the selected delivery approach that identifies all key review and decision points, including any preliminary reviews Appropriate standard form of contract identified, as the baseline for later adaptions as required. |  |
| 4.4 Does the project have resources with, where required, the appropriate skills and experience? | Requisite skills available in the Project Team, and access to external expertise as appropriate Requirements for ‘intelligent customer’ capabilities, where appropriate, identified and plans for putting them in place Project relationships such as team-working and partnering considered, with a plan to implement them where appropriate Internal and external commitment to provide the resources required Job descriptions for key project staff Skills audit undertaken and plans for addressing any shortfall Contract management staff identified to join the procurement team at an early stage, to familiarize themselves with the procurement’s intent and processes Appropriate allocation of key project roles between internal staff and consultants or contractors. |  |