Expro Projects White Book

Project Building Information Modeling Execution Plan (BEP) Template

Volume 6, Chapter 6

Project Building Information Modeling Execution Plan (BEP) Template

Document No. EPM-KE0-TP-000025 Rev 000

Document Submittal History:

| Rev.: | Rev Status | Date: | Entity | Prepared by: | Checked by: | Reviewed by: |  | Approved by: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| XXX | For XXX | dd/mm/yyyy |  | Name | Name | Name |  | Name |
| Signatures: |  |  |  |  |  |  |  |  |  |

THIS NOTICE MUST ACCOMPANY EVERY COPY OF THIS DOCUMENT

IMPORTANT NOTICE

This document, (“Document”) is the exclusive property of Government Expenditure & Projects Efficiency Authority.

This Document should be read in its entirety including the terms of this Important Notice. The government entities may disclose this Document or extracts of this Document to their respective consultants and/or contractors, provided that such disclosure includes this Important Notice.

Any use or reliance on this Document, or extracts thereof, by any party, including government entities and their respective consultants and/or contractors, is at that third party’s sole risk and responsibility. Government Expenditure and Projects Efficiency Authority, to the maximum extent permitted by law, disclaim all liability (including for losses or damages of whatsoever nature claimed on whatsoever basis including negligence or otherwise) to any third party howsoever arising with respect to or in connection with the use of this Document including any liability caused by negligent acts or omissions.

This Document and its contents are valid only for the conditions reported in it and as of the date of this Document.

Table of Contents

1.0	INTRODUCTION	7

1.1	Purpose	7

1.2	Scope	7

1.3	Definitions	7

1.4	References	8

1.5	Project Overview	9

1.6	Design Execution	9

1.7	Project Schedule	9

2.0	BIM EXECUTION	9

2.1	Responsibilities	9

2.2	Strategy	10

2.3	Engineering and Construction Automation Tools & Systems	11

2.4	Engineering Design Sub-Contractor BIM Planning	11

2.5	Modeling Scope & Detail	12

2.5.1	Level of Development	12

2.6	BIM Uses	14

2.6.1	Design Authoring	14

2.6.2	Engineering Analysis	14

2.6.3	Drawing & Schedule Generation	14

2.6.4	Interference Management (Clash Checking)	14

2.6.5	Engineering Progress Tracking	14

2.6.6	Interactive Design Reviews	14

2.6.7	 Shop Detailing	15

2.6.8	Visualization	15

2.6.9	Phasing and Construction Sequencing Simulations (4D)	15

2.6.10	Quantity Take-Off	15

2.6.11	Vendor Equipment Submittals	15

2.6.12	Field Progress Tracking	15

2.6.13	Augmented Reality	15

2.6.14	Digital Fabrication	15

2.6.15	Record Modelling (As-Built)	15

2.6.16	Operations & Maintenance Information and Handover	16

2.6.17	Reality Capture	16

2.6.18	Other	16

3.0	WORK PROCESSES	16

3.1	BIM Model Engineering to Construction	16

3.2	Model Review Procedure	16

3.3	REVIT Procedures (where Revit used)	17

3.3.1	Revit Model Management	17

3.3.2	Revit Revision Standards	18

3.3.3	Drawing Sheet Naming and Numbering	18

3.4	Clash Detection	18

3.5	Shop Drawing & Modeling	19

3.6	As-Built Modeling	19

4.0	STANDARDS AND PROCEDURES	19

4.1	International Standards and Guidance Documents	19

5.0	COLLABORATION	20

5.1	Meetings & communication	20

5.2	Model collaboration	20

6.0	DATA MANAGEMENT & EXCHANGE	20

6.1	Common Data Environment (CDE)	20

6.2	Data Control	20

6.3	Data Structure	21

6.4	Asset and Component Tagging Requirement	21

6.5	Component Attributes	22

6.6	Data Interoperability	23

6.6.1	Engineering Data Formats	23

6.6.2	Electronic Data Interchange	23

6.7	BIM Model Definition	23

6.7.1	Level of Development	24

6.7.2	Geo-Referencing Models	25

6.8	Quality Control	25

6.8.1	Data Quality and completeness	25

6.8.2	Model Coordination	25

6.8.3	Model and Sheet Checking and Approval	25

6.8.4	BIM Audits	26

6.9	Deliverables	26

6.9.1	Deliverables to the Entity	26

6.9.2	Sub-Contractor Model & Data Submittals to A/E	27

6.10	Training/Induction	27

6.11	BIM IS&T Requirements	27

6.11.1	Software	27

6.11.2	Hardware	27

7.0	BIM MODEL QUALITY	27

8.0	SUBMITTAL REQUIREMENTS	27

# INTRODUCTION

[This document must be tailored by the Entity for each project.  The Entity should then give this document to the A/E as a template or basis for the A/E to prepare their own BIM Execution Plan (BEP). There are examples of BIM documentation on the internet that could be useful to the Entity or their consultants in preparing a BEP.  For example, the Denver International Airport (DIA) and the VA BIM Standard from the US Department of Veteran Affairs.[remove this note]

## Purpose

This BIM execution plan is to provide the project team with clear guidance as to the staffing, tools, processes, procedures and systems required to facilitate the flow of information to support the design, procurement and construction of the [Project name] Project.

## Scope

This plan applies to all parties and all work performed on the [Project name] Project where Building Information Modeling (BIM) is utilized.

## Definitions

| Definitions | Description |
| --- | --- |
| A/E | Architectural/Engineering |
| AR | Augmented Reality |
| Automation | Field of specialized software tools and associated work processes involved with the creation of A/E project deliverables. Focus is on CAD/BIM/GIS and IM |
| BEP | BIM Execution Plan |
| BIM | Building Information Model(ing) VERB: A cross-functional collaborative process of creating, collecting & managing information to virtually design, procure, schedule, construct, commission, start-up and operate a facility. BIM therefore develops a digital representation of the physical and functional characteristics of a facility. As such it serves as a shared knowledge resource for information about a facility forming a reliable basis for decisions during its lifecycle from inception onward NOUN: The collection of files and databases used in building the information model of the facility |
| CAD | Computer Aided Design |
| CDE/ Data Warehouse | Common Data Environment: Large store of linked Data and trusted source of truth of the assets |
| CMMS | Computerized Maintenance Management System |
| COBie | Construction Operations Building Information Exchange (COBie) is a non-proprietary data format for the publication of a subset of BIM focused on delivering asset data as distinct from geometric information |
| ER | Defines the information that will be required by the Entity from the A/E, suppliers, and consultants for the operation and maintenance of the completed built asset |
| GIS | Geographic Information System |
| IM | Information Management |
| ICT | Information & Communications Technology |
| LOD | Level of Development |
| MEP/FP | Mechanical, Electrical, Plumbing/Fire Protection |
| SME | Subject Matter Expert |
| Super User | Subject matter expert who will define how the software will be used, support software implementation, and drive its implementation on the project |
| WBS | Work Breakdown Structure |

## References

EPM-KE0-GL-000020 – Project Automation Requirements and Deliverables Guideline

EPM-KE0-PR-000008 – CAD Standards Procedure

EPM-KE0-TP-000012 – Tagging Procedure Template

EPM-ID0-PR-000002 – Project Standard Document Numbering Procedure

EPM-KE0-TP-000024 – BIM Questionnaire Template

EPM-KE0-RG-000014 – BIM Level of Development Matrices

EPM-KE0-RG-000009 – Project Building Information Modeling Execution Plan (BEP) Template

EPM-KE0-PR-000010– 3D Model Review Procedure

Edit above for project specific document references and add additional references as required

## Project Overview

1.3.1    Project Owner

1.3.2    Contract Type

[Engineering services, lump sum etc.]

1.3.3    Project Description

## Design Execution

Describe the strategy of the design execution, that is, if the A/E is hiring outside firms to perform specialty work (structural design, HVAC, etc.) describe who is performing the work and how/when the data will be updated into the design effort

## Project Schedule

Describe the overall project timeline and milestones including when consultants or various internal disciplines (structural, electrical, HVAC, piping, etc.) will complete portions of the work to prepare the final complete 3D design.

# BIM EXECUTION

## Responsibilities

- Define the BIM organization and include a diagram.

- Describe the various roles and contacts, depending on the size and complexity of the project, this will include the Automation Manager, BIM Manager, Discipline BIM Leads, Subcontractor BIM Coordinators, Subject Matter Experts (SME or Super Users), ICT support

Automation Manager: leads all aspects of project automation related to design. Covers CAD/BIM/GIS/IM and related software; main contact with client and subcontractors. Is the main contact when interfacing with the client and subcontractors on Automation related matters. Responsible for all Automation related documentation

BIM Manager: On large projects a BIM Manager will be responsible for the development of and administration of the BIM and the coordination of the BIM stakeholders working through the discipline BIM Leads.

SMEs/Super Users: understand the technical and work process aspects for their disciplines together with a high understanding of the software. On large projects may be full-time in this role but otherwise mainly doing production work

SubContractor BIM Coordinators: Subcontractor (if any) main point of contact for BIM related deliverables to the A/E

ICT Support: ICT infrastructure and desktop hardware and software support

## Strategy

The BIM strategy for the project is to -

CREATE the design information in a 3D model format using discipline-based tools that support design coordination, analysis, and interoperability of data for use through manufacture and construction then into operations.

COLLABORATE at all stages of the project using the BIM model as the basis for review, evaluation and comment.

CONTROL the management of the works using the BIM model to support estimating, scheduling, logistics, and commissioning.

CONSUME the BIM model and the associated project information across all functions and disciplines by allowing access to data to all parties via a Common Data Environment (CDE).

CONTRIBUTE additional information to the model throughout the project lifecycle by all teams to build a complete project information resource to optimize handover for operations.

This BIM Execution Plan (BEP) outlines the tools, systems, processes and protocols required to successfully deliver the strategy. The illustration below [A/E to insert diagram] illustrates the cross-functional interactions needed to achieve this strategy.

## Engineering and Construction Automation Tools & Systems

Include a listing of software used and for what purpose. Use EPM-KE0-RG-000009 - List of Commonly Used Design & Engineering Software to help develop this list

Create a high level diagram showing the flow of information between the contractor and sub-contractors and the Entity

## Engineering Design Sub-Contractor BIM Planning

Each sub-contractor is required to prepare their own BIM Execution Plan, which sets out how the sub-contractor will deliver the required BIM information to the A/E for their scope of work. This is to be submitted to the A/E BIM Manager for review and approval within 30 days of contract award.

Sub-Contractor’s BEP is to cover the following topics –

BIM Uses

CAD Standards

BIM & CAD Software Tools and Applications to be used

Model Schedule. A complete list of all BIM and CAD Models to be prepared by the Designer

BIM Contacts and Roles & Responsibilities. A list of BIM and CAD Coordinators with responsibility for delivering the BIM requirements

BIM File Management. Detailed description of the locations for storage and control of the designer’s electronic design files

Quality Control of Models, Drawings & Data. Methods and procedures for standards compliance checking

Model Development Plan. A plan defining how the BIM will be developed to meet the Project Milestones BIM information exchange methods and formats

BIM Deliverables, including CAD files and model deliverables together with file types. Include data requirements of the Entity and A/E with submission schedule

Interfaces - BIM Coordination includes the facility interfacing process. A Package Interface Lead is assigned. The BIM Coordinator will work with the Package Interface Lead and the BIM Coordinators of interfacing Packages to develop a common approach to the modeling of the interfacing objects such that the interfacing elements are coordinated by geo-location, construction sequence, and by discipline-to-discipline services. The Sub-Contractor BEP should outline that interfacing approach.

Add project specific requirements here also.

## Modeling Scope & Detail

Discuss what will and will not be modeled, the level of detail shown for existing facilities if applicable and scope of others.

All project data and drawings related to the design of a facility shall be generated from 3D models with the following exceptions:

- standard 2D details and legend views

- Flow diagrams and Process and Instrumentation Diagrams (P&IDs)

- Electrical one-line and schematic drawings

If required by the Entity, add this requirement:

Note that all schedules and quantities shall be generated from the project 3D models.

### Level of Development

The Level of Development (LOD) Specification is a reference that specifies and articulates the content and reliability of Building Information Models (BIMs) at various stages in the design and construction process.

The Level of Development (LOD) is defined in section 6.7.1. The LOD Matrix, which describes the LOD for each project phase, is described in Attachment 2. Alternatively the AIA G202: AIA G202-2013 Building Information Modeling Protocol Form outlines other non-data project modeling requirements for each project phase. Additionally, the following items are to be considered standard:

Edit to suit:

- Floor Slabs: Owned by Structural. Include slab depressions and model any penetrations above 600mm X 600mm

- Thin Floor Elements (Carpet, Tile, etc.): Owned by Architectural. To be modeled as non-room bounding

- Structural Walls: Owned by Structural. Full height, no stud framing, no bracing, model any penetrations above 600mm X 600mm

- Structural Framing: Owned by Structural. Model actual beam column, base plate, bracing, joist, and girder sizes. Excludes connections

- Structural Concrete: Owned by Structural. Rebar is normally excluded.

- Nonstructural Walls: Owned by Architectural. True height, no stud framing, no bracing, no MEP/FP connections

- Doors: Owned by Architectural. Model clearances with symbol lines in plan, and with transparent solid in 3D. Exclude hardware.

- Areas and Rooms: Owned by Architectural. Model as fully enclosed or defined.

- Stairs and Railings: Structural supports owned by Structural. Other elements owned by Architectural. Model risers, treads, intermediate landings, and railings per building code requirements.

- Elevators: Shaft clear width and depth owned by Architectural. Cab width and depth owned by Mechanical. Supplemental framing for elevator hoist beams and rail supports owned by Structural.

- Casework: Owned by Architectural. Excludes hardware.

- Ceilings: Owned by Architectural. Model as non-room bounding, do not use “Basic” ceiling type.

- Mechanical Equipment: Owned by Mechanical. Model accurate size to match basis of design and accurate placement. Include service, replacement, and access clearances, as well as coil or tube pull zones, using symbol lines in plan, and transparent solid in 3D.

- Ducts / Diffusers: Owned by Mechanical. Model accurate size and placement, with worst-case scenario thickness. Model diffusers with proper category. Exclude flanges.

- Piping: Owned by Mechanical and Plumbing. Model accurate size and routing. Insulation, while an attribute of the piping, is not normally displayed or may be displayed semi-transparently.

- Fire Protection: Owned by Mechanical and Electrical. Model pumps, risers, mains, and fire alarms. Exclude branch lines, sprinkler heads, and fireproofing.

- Electrical Equipment: Owned by Electrical. Sized to match basis of design. Model required clearances, including cable tray access, with transparent solid in 3D. Model cable trays and all conduit 1-1/2” or greater.

- Quantity Takeoff Analysis: I should be assumed that the Entity will use the 3D model quantity takeoff capabilities for estimating and sequencing purposes. Accuracy and currency of quantities shall be maintained in all models at scheduled deliverable dates.

## BIM Uses

BIM (both graphical models and non-graphical data) is normally started in engineering but built upon and in collaboration with other departments, suppliers and sub-contractors during the design phase of the project. This information will be consumed by later functions where that data is input into their work processes. Typical uses are summarized in the table below against each function.

A/E to list the BIM Uses to be employed on this project as agreed with the Entity and include a description. E.g.:

### Design Authoring

The process by which the 3D software is used to digitally develop the building or facility design. The disciplines work collaboratively by working in a common environment where each contributor to the model can view the input of the others and develop their model for each project milestone according to the LOD required. This is a key part of BIM where 3D objects can be linked to database properties to define these objects and further include them in other uses below and more.

### Engineering Analysis

The geometric BIM models produced from the BIM authoring tools will be linked to, or exported to, analysis software for structural design analysis and calculation as required.

### Drawing & Schedule Generation

General arrangement drawings, coordination drawings, location drawings and schedules of components and materials for all work scope that is modelled will be generated from the BIM model as sheet sets that are contained in the BIM project model for that discipline. Typical details, assembly and component details, and shop drawings may be created separately from the BIM model. The details of drawings generated separately from BIM Models are to be stated in each sub-contractor’s BIM Execution Plan.

### Interference Management (Clash Checking)

The A/E is responsible for Design coordination between disciplines and will run clash checks in either the authoring or reviewing software to identify spatial interferences between modeled elements. A clash register will be maintained for review and action during design reviews. Lead Engineers will not be permitted to approve an element as LOD 350 unless it is confirmed as being clash free against all related models for that work area.

### Engineering Progress Tracking

Describe the method to be used for tracking the progress of the model and the relation of LOD to model progress.

### Interactive Design Reviews

The BIM model will be viewed live during interactive design reviews for all work scope and disciplines. Various formats of the model and viewing applications may be used. Actions arising will be recorded against specific objects, zones or models and issued as comments to the model authors either through meeting minutes, comment sheets or reports.

### Shop Detailing

Detail or fabrication drawings such as steel detailing drawings and fabrication piping isometrics will be extracted from the model

### Visualization

The BIM model will be used to create graphic visualizations and animations to assist communication of the works to Sub-Contractors, Suppliers, the Owner and other Stakeholders. This will also include demonstrating and illustrating safe methods of working, both to enhance graphics and posters for craft labor and through animations and toolbox talks, (e.g. showing the safe work method on an IPad on site, an example being excavation support).

### Phasing and Construction Sequencing Simulations (4D)

Discuss how 4D planning and visualization will be employed on the project.

### Quantity Take-Off

Quantity take-offs (QTO) will be extracted from the BIM model and made available in a location and format to be confirmed between Project Controls, Procurement and Engineering, but which will, as a minimum align with the Work Breakdown Structure (WBS).

### Vendor Equipment Submittals

Discuss the provision of equipment, materials, systems or assemblies from suppliers and will include the supply of BIM models of that work scope in compliance with project information requirements and LOD.

### Field Progress Tracking

Discuss how the BIM will be used to track progress in the field.

### Augmented Reality

The BIM model will be made available on site using mobile devices and will be viewable using AR technology to visualize accurately on site both hidden elements and yet to be constructed elements of the works. This may include temporary works.

### Digital Fabrication

The BIM model will be made available to manufacturers for the automatic fabrication of building components using CNC machines to minimize tolerances and waste and maximize productivity. In particular for structural steelwork, rebar and metalwork (ductwork) production.

### Record Modelling (As-Built)

The BIM model will be revised as work packages are completed to record the as-built status of the works. The LOD for completed objects recorded as constructed by Field staff will be updated to LOD 500 (see section 6.7.1).

### Operations & Maintenance Information and Handover

The BIM model and database will store operational and maintenance information progressively and will be used to both visualize and report the collation of work packages ready for handover to the Owner for Operations and Maintenance.

### Reality Capture

Existing conditions and As-Constructed works will be rapidly captured for incorporation into the BIM Model using laser-scanning equipment to generate point cloud data sets. This data can be used directly in the BIM authoring tools and visualization tools. Clash Checks between point cloud data and designed models can be carried out to validate early works prior to later trades and sub-contractors works on site.

### Other

Describe other BIM Uses here that the Entity has planned to use.

# WORK PROCESSES

## BIM Model Engineering to Construction

Describe the work processes involved with the development of the BIM – include diagrams of the work flow from developing conceptual models through detail design and as-built. Describe how model reviews are conducted and how models are checked, how quantities and drawings are extracted from the model.

## Model Review Procedure

Typical Model Review activities include:

- Design Review

- LOD Matrix compliance check

- Model data checks

- Checking model against project requirements

- Compliant component tagging

- Checking index sheet/drawing lists

- Check of package for text, symbol, sheet layout and plotting inconsistencies

- Spelling or grammatical errors

- Drawing formatting

- Minutes and record keeping

Develop this section in detail or create a separate procedure document. Refer to EPM-KE0-PR-000010– 3D Model Review Procedure

## REVIT Procedures (where Revit used)

Remove this section and replace with procedures for other software.

If Revit is used as the model authoring software, in addition to the A/Es Revit guides and instructions, the following guidelines are recommended good practice.

### Revit Model Management

To maintain smaller Revit file size and optimal model functionality, the following items should be completed on a regular schedule (ideally weekly):

- Copy the Central File into a backup folder.

- Open the Central File with the “Audit” checkbox selected, detach from Central and keep Work sets when prompted, then “Save As Compact Model” in the original location under the original filename.

- Check model file size and verify that it does not exceed the Entity standard “Not to exceed” number.

- Check number of Detail and Model groups – this number should be kept to a minimum necessary.

- Verify that any links present are still in use, remove if no longer required. Remove any missing links. Any required external references should be placed on their own dedicated Work set.

Monitor Work sets through dedicated single-Work set views to ensure items are being placed on correct Work set.

- Note any improper or excessive use of in-place families or generic models. These types of elements can be a drain on resources, and if repeated across the project, can impact model performance.

- Note any seemingly unused or temporary views, and verify with the project team that they can be deleted.

- Check Errors and Warnings – this number should ideally be kept to a minimum, as too many warnings will impact model performance, and certain design activities can cause these to multiply quickly. Generate a Warning Report in Excel and delegate to the project team, tracking unresolvable warnings to avoid duplicate efforts.

### Revit Revision Standards

Revisions shall be per project and across disciplines, not per sheet.

### Drawing Sheet Naming and Numbering

Drawing [Sheet] Naming

- 1ST FLOOR shall be used in place of FIRST FLOOR or LEVEL 1

- Area X shall be used to designate a portion of the Key Plan and shall correlate to the sequence modifier in the sequence number e.g. 12X

- Drawing Titles to be places on sheets shall be given unique titles

Drawing Sheet Numbering

Sheets shall be numbered to follow the last 4 elements of the document number (set this as a sheet number prefix parameter if using Revit software) so as to be able to match with the model number per 9.1 above:

| Location Code | Discipline Code | Document Type Code | Sequence Number |
| --- | --- | --- | --- |
| Element 4 | Element 5 | Element 6 | Element 7 |
| 6 Characters | 3 Characters | 2 Characters | 6 Characters |

Refer to EPM-ID0-PR-000002 - Project Standard Document Numbering Procedure for more information about the elements making up the document number.

## Clash Detection

Internal clash detection should be conducted after 30% model completion but early enough to achieve a clash free model by the 60% model complete milestone. Once started, the formal clash detection process should be repeated at least every 2 weeks. For CAD systems that support “live” or interactive clash detection, this functionality should be turned on at the beginning of the project.

The following considerations must be taken into account:

- File names and locations must remain the same. For this reason, archiving at project milestones should consist of saving copies of the models in another network folder, and continuing to work within the original.

- Ensure software settings include all valid objects that will be included in the clash

- At a minimum Project BIM Leads will host interdisciplinary clash meetings at project milestones, and delegate clashes to be resolved within 5 business days – in time for the process to clash detection cycle to begin again. System settings must reflect the ownership of clashes between disciplines established on the project. Eg. A clash between a pipe and a structural member should be assigned to the Plumbing discipline

## Shop Drawing & Modeling

Describe the LOD required for the issuance of shop drawings.

## As-Built Modeling

The BIM will be revised as work packages are completed to record the as-built status of the works. The LOD for completed objects recorded as constructed by field staff will be updated to LOD 500 (see section 6.7.1).

# STANDARDS AND PROCEDURES

Building Information Management shall be setup so that deliverables are in line with the CAD Standards Procedure EPM-KE0-PR-000008

## International Standards and Guidance Documents

The below list of standards are included for reference, and have been used in the preparation of this BIM Execution Plan.

- Level of Development Specification: Version 2013. (Reference provided for guidance only) www.bimforum.org/lod

- US Army Corp of Engineers (USACE) Minimum Modelling Matrix (M3), Version 1.2, dated 03 Oct 2013 (USACE_M3_v1.2_20131016.xlsx)

https://cadbim.usace.army.mil/default.aspx?p=a&t=1&i=14

- AIA Document G202 – 2013 – Project Building Information Modelling Protocol Form

- Uniformat II - Elemental Classification for Building Specifications, Cost Estimating and Cost Analysis

# COLLABORATION

Collaboration is vital to the success of a BIM Project. There are two aspects to collaboration; communication between people, and the control and sharing of the project information and data.

## Meetings & communication

Set the meeting schedules for BIM support personnel, attendance at design coordination meetings, constructability review and model review sessions.

## Model collaboration

As part of the BIM, the design shall be authored using the BIM software collaboratively and in real time. Where work is performed in multiple offices or where subcontractors and suppliers are major participants in the BIM, the A/E will facilitate the maximize “live” collaboration practicably possible and minimize the frequency and time lag of BIM updates to the A/E’s master BIM from external participants. The BIM shall not be created at the end of the project only to meet project deliverables.

# DATA MANAGEMENT & EXCHANGE

## Common Data Environment (CDE)

The Common Data Environment is the engineering working environment where all current, controlled project design information is stored and made available by controlled access. It is normally an application or group of applications that form the “single source of truth” for the building information. If the concept of the CDE is utilized it should be defined here and shown diagrammatically.

## Data Control

Describe access to “Work in Progress” and permissions to the applications.

## Data Structure

Show the data hierarchy data. Normally this follows the WBS in the applications as appropriate and folder structures in file shares.

## Asset and Component Tagging Requirement

Typical assets that require tagging are listed below per the project tagging procedure EPM-KE0-TP-000012:

| Master Format Division |  |  |  |  |  |  | Asset Types |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Division 14 - Conveying Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Elevators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Division 21 - Fire Suppression |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Fire Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Division 22 - Plumbing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Domestic Water Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Backwater Valves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Sanitary Sewerage Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Facility Packaged Sewage Pumping Stations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Sump Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | General Service Packaged Air Compressors and Receivers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Electric Domestic Water Heaters |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Fuel-Fired Domestic Water Heaters |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Domestic Water Heat Exchangers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Division 23 - Heating, Ventilating, and Air-Conditioning (HVAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Facility Fuel Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Fire Dampers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Smoke-Control Dampers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | HVAC Fans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Constant-Air-Volume Units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Variable-Air-Volume Units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Ventilation Hoods |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Heating Boilers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Boiler Feed water Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Furnaces |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Fuel-Fired Heaters |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Heat Exchangers for HVAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Refrigerant Compressors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Refrigerant Condensers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Packaged Water Chillers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Cooling Towers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Indoor Central-Station Air-Handling Units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Packaged Outdoor HVAC Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Custom-Packaged Outdoor HVAC Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Evaporative Air-Cooling Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Decentralized Unitary HVAC Equipment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Convection Heating and Cooling Units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Radiant Heating Units |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Division 26 - Electrical |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Medium-Voltage Transformers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Medium-Voltage Switchgear |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Medium-Voltage Metering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Low-Voltage Transformers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Low-Voltage Switchgear |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Switchboards and Panel boards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Static Uninterruptible Power Supply |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Division 28 - Electronic Safety and Security |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Fire Detection and Alarm Annunciation Panels and Fire Stations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Division 33 - Utilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Water Utility Pumping Stations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Water Supply Wells |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Packaged Utility Lift Stations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Packaged Utility Wastewater Pumping Stations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Fuel-Oil Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Gasoline Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Diesel Fuel Pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Utility Transformers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | High-Voltage Switchgear and Protection Devices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Medium-Voltage Utility Switchgear and Protection Devices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Component Attributes

Attributes are the non-graphical information attached to objects in the 3D Model that defines various characteristics of the object. Attributes can include properties such as parametric values that drive physical sizes, material definitions and characteristics (e.g. wood, metal), manufacturer data, and industry classification codes.

Attributes can also define supplementary physical entities that are not necessarily shown graphically in the Model, such as insulation around a duct, hardware on a door, content of conduit, or transformer properties. Where Exchange Requirements have been defined by the Entity, data must be delivered to the Entity per the Exchange Requirements definition and schedule in Construction Operations Building Information Exchange (COBie) format unless noted otherwise. The A/E shall add attributes for internal purposes however, for the above listed assets, the following typical data will need to be collected by design and construction teams to support Computerized Maintenance Management System (CMMS) and Computer-aided Facility Management (CAFM) systems requirements:

Tag/ attribute

- Asset tag

- Asset description

- Location Code

- Spec Reference

- Manufacturer

- Manufacturer Model Number

- Serial Number

- Installation Date

- Warranty Start Date

- Warranty Duration

- Warranty Description

Model objects shall also have an attribute assigned for the current LOD for discrete model objects.

## Data Interoperability

A/E to complete as per internal and Entity requirements

### Engineering Data Formats

List the file extensions used on the projects together with their parent applications and version.

### Electronic Data Interchange

List file types to be used between applications e.g. Revit to Aconex = IFC format.

## BIM Model Definition

### Level of Development

The LOD values defined below are based upon the BIMForum interpretation of AIA G202-2013 Building Information Modeling protocol.

LOD 100 - elements are not geometric presentations.  They may be symbols or other generic representations of information that can be derived from other model elements.  Any information derived from LOD 100 elements must be considered approximate.

LOD 200 - elements are represented graphically but are generic placeholders, e.g., volume, quantity, location, or orientation. Any information derived from LOD 200 elements must be considered approximate

LOD 300 - elements are graphically represented as specific systems, objects, or assemblies from which quantity, shape, size, location, and orientation can be measured directly, without having to refer to non-modeled information such as notes or dimension call-outs

LOD 350 - elements are enhanced beyond LOD 300 by the addition of information regarding interfaces with other building systems.  For example, an LOD 350 masonry wall element would include jamb conditions, bond beams, grouted cells, dowel locations, and joints – information that enables the model user to coordinate the wall element with other systems in the structure

LOD 400 - elements are modeled at sufficient detail and accuracy for fabrication of the represented component.

LOD 500 - facilities management - This level will have suitable geometry and information to support operations and maintenance. Geometry and data should be as-built and field verified.

An LOD matrix per element Uniformat II Industry Classification code is described in Attachment B of this document.

### Geo-Referencing Models

The project coordinate system is: [enter coordinate system]

Refer to the BIM and CAD Standards for the method of registration between BIM models and the coordinate system to ensure correct geo-referencing of the project model.

## Quality Control

### Data Quality and completeness

Quality Control and Assurance of the BIM Data will be done through the following processes of design coordination, checking, review and audit.

    - Coordination of the BIM Data through Design Reviews, Clash checks etc.

    - Checking of the deliverables created from the BIM Model prior to approval. (Including checks that the drawings and model are consistent)

    - Regular audits of the BIM by each respective discipline to check for data quality and completeness

    - A/E Automation check of the BIM supplied by sub-contractors prior to incorporation of the A/E master BIM

    - Regular A/E Internal audits of the BIM by the A/E Automation team.

### Model Coordination

Model (or Design) Coordination is a continuous process undertaken by the design teams. Each Design Package team is required to formally record (through meeting minutes or reports) the completion and actions arising from these practices.

- Interactive Design Reviews

- Interference Management (Clash Checking)

- Phasing and Construction Sequencing Simulations (4D BIM if utilized)

### Model and Sheet Checking and Approval

BIM Models and Sheets (Drawings) will be checked by the Design Contractor Design Team and approved by the Design Manager, prior to submission to the Entity for acceptance. A QC checklist will be used for each type.

#### Model QC Checklist

Each model must have an associated checklist used during the checking and approval process that contains the following checks:

Model Integrity Checks

- Content (objects and data) integrity and inclusions/exclusions

- LOD

- Areas inclusions/exclusions

- Spaces and zones inclusions/exclusions

- Schedules including schedule summations

- Tags and tag agreement with schedule data

- Sizes and types

- General notes

Standards Check

- Adherence to CAD or BIM standards

- Delivery format – scale, orientation, view types on sheets

- Detailing – information and section cuts, detail references

- Annotations and Tags

- Dimensioning

- Title block and title text including naming and numbering

- Line work

- Layering in CAD

Coordination Checks

- Linked Files

- Geo-Referencing location, conformance with alignment

- Clash Reports

- Visual Checks

The Model QC Checklists must be submitted with the design submissions to the Entity. One checklist per model.

#### Sheet QC Checklist

Each set of drawings within a design package must have an associated checklist used during the checking and approval process that contains checks against the following:

- CAD Standards Check

- Dimensioning

- Title block and title text including naming and numbering

- Cross-References

- Specification and Material References

- Annotation and Tagging

- Survey Grid References

- Check and Approval Names

- Reference (XRef) Files are current

The Sheet QC Checklists must be submitted with the Design Submissions, one checklist per package.

### BIM Audits

Audits of the BIM Management Process will be undertaken regularly in conjunction with the Entity Quality Team. The BIM Audits will cover any aspects of this BEP, and for BIM and CAD Standards compliance. The audit schedule will be issued in advance by the Entity and will detail the areas to be audited in each case.

## Deliverables

### Deliverables to the Entity

List the deliverables per the Prime Contract.

### Sub-Contractor Model & Data Submittals to A/E

Sub-contractor BIM deliverables must be captured contractually and managed by the A/E Automation group. The Entity requirements must be flowed down to the sub-contractors.

## Training/Induction

It is the responsibility of all parties and each Design Sub-Contractor to supply competent staff trained in the applications and tools they will be required to use on the Project.

A/E is responsible for providing guidance on the particular requirements applicable to the Project.

## BIM IS&T Requirements

### Software

Refer to the Project Automation Plan for the software to be used on the project. Check if the Entity mandates the use of any software.

### Hardware

Refer to the A/E ICT department for workstation and hardware information.

# BIM MODEL QUALITY

Consistent tag data and attribute definitions throughout the lifecycle of the project development are fundamental to the success of the project models ability to deliver many BIM deliverables such s drawings, quantity reports, and asset management data deliverables. Describe the quality processes and tools in this section.

# SUBMITTAL REQUIREMENTS

The following BIM related documents must be included as part of the submittal requirements from the A/E to the Entity. Similarly these documents need to be submitted from subcontractors and suppliers to the A/E where applicable.

| Deliverable Type | With Proposal | Official Milestone Submittals 30%, 60%, 100% and handover | Regular Submittal as Agreed During Execution Phase |
| --- | --- | --- | --- |
| BIM Authoring Tool Questionnaire | x | x |  |
| Contractor and Sub-Contractor BIM Execution Plan | x | x |  |
| Model Data Quality Check Reports |  | x | x |
| Clash Report |  | x |  |
| Model handover |  | x | x |
| List of BIM Open Issues |  | x | x |
| Quantity Reports |  | x | x |
| Deviation Request to the BIM Automation Requirements | x | x | x |

[edit to suit project requirements]