Project Representative List of Project Definition Deliverables

| Estimate Class > | Class 5 | Class 4 | Class 3 | Class 2 | Class 1 |
| --- | --- | --- | --- | --- | --- |
| Level of Project Definition | Geographic location / Country - Regional specific / General Site Conditions | As for Class 5 plus: | As for Class 4 plus: | As for Class 3 plus: | Completed or nearly completed design |
|  | Gross dimensions | Layout / reference project plot plan (with assumed major utilities interface points location), assumed subsurface conditions | Actual project location, preliminary plot plan/plant layout (typically Issued For Approval (IFA) for overall plot plan), preliminary site assessment, preliminary understanding of sub-surface condition (for local foundation requirements). | Site assessment complete, site investigation / geotechnical report complete with substantial understanding of foundation requirements/design. | Process P&IDs typically Issued For Construction (IFC) and Auxiliaries/Utilities typically Issued For Design (IFD)/IFC. HAZOP completed and action items closed. |
|  | Preliminary Block Flow Diagrams, process description/expected plant capacity/configuration | Process Flow/Block Diagrams | Preliminary P&IDs (typically IFA for process and Issued For Review (IFR) for utilities), preliminary PFDs on material handling and major systems, preliminary definition of utility requirements. | Process and Utilities P&IDs typically Issued For Hazard Study Review (IFH). (For Power projects with substantial historical / reference basis, redline markup of P&IDs for steam, condensate, feed water, fuel gas and circulating water systems may be used.) HAZOP significantly defined. | Typically 50% of model reviews completed, 90% reviews status. |
|  |  | Battery limit scope, general description/sizing of facilities, draft scope of work description (including design basis, facility services, major interconnections, etc.), scope comparison data | Preliminary design of major structures and facilities, design documents for civil/earthwork (e.g. track alignments, surveys, etc.), preliminary piping models, preliminary single line diagram / power distribution design, preliminary water balance | Large bore modeled and routed for critical systems . |  |
|  |  | Preliminary equipment list (may have sizing, material/performance specifications, weights, etc.) | Specifications preliminary/complete for major equipment and key bulk materials. | Specifications complete for most major equipment and key bulk materials. |  |
|  |  |  | Scope description including preliminary definition of vendor scope and overall scope related qualifications and assumptions. |  |  |