## Dashboard (2) (hidden)
1. ALIGNMENT LENGTH | 2. ENGINEERING / DESIGN |  | 3. KEY MILESTONES | 4. PROJECT COMPLETION %, REVENUE BASIS
5. STRUCTURES |  | 6. CONSTRUCTION
9. MANPOWER |  |  |  |  | es&h

## A.CoverPage
1. Health, Safety, Security & Environment (HSSE)
2. Quality
| 3. Critical Issues, Etc. | 4. Progress
3. Progress
3. Progress
5. Key Milestones
6. Manpower
5. Key Milestones
7. Quantity Tracker
8. Costs and Changes
9. Shop Drawings
10. Procurement
5. Key Milestones
11. Skyline
12. Testing & Commissioning
EPM-KPR-TP-000008 Rev. 001
Health, Safety, Security:
One RI occurred when a formwork operative was hammering a nail into formwork when the hammer bounced back from the timber and hit his safety glasses which caused a small laceration to his left eyebrow. One NM occurred when a subcontractor dump truck bucket became detached from the lifting arm whilst unloading material. The bucket tilted approx. 60 degrees onto its right hand side.
Environmental:
One small diesel spill occurred in a non sensitive environmental area and was cleaned up.
Progress:
Current Construction Progress is at 4.1% with a plan of 5.0%. The lack of progress has be attributed to the excessive equipment breakdowns. A new Caterpillar 5110 is expected to be mobilized next month.
Key Achievements:
XYZ
Critical Issues:
XYZ
Risk & Opportunities:
XYZ
Remarks:
Entity:
Registration Date:
Project Title:
Next Stg. Gt. Date:
Expro No.:
Eng. Contract No.:
Location:
Con. Contract No.:
Province:
Reporting Period:
Doc. No.:

## 0.INTRO
Project Summary Report
ConstructionTemplate
Stage Gate 6,7,8
Entity: |  | Registration Date:
Project Title: |  | Next Stg. Gt. Date:
Expro No.: |  | Eng. Contract No.:
Location: |  | Con. Contract No.:
Province: |  | Reporting Period:
Doc. No.:
Contractor / Consultant:
CR No.:

## 1.HSSE
Incident
Period | Job Hours | NM | FA | RI | LWDC | FAT | EI
ITD
YTD
RP
Incident Rates
Period | NM | FA | RI | LWDC | FAT | AFR | EI
ITD
YTD
RP
Legend:
AFR | Accident Frequency Rate |  |  | FAT | Fatalities |  |  | NM | Near Misses
EI | Environmental Incident |  |  | ITD | Inception To Date |  |  | RI | Recordable Incident
FA | First Aid |  |  | LWDC | Lost Work Day Case |  |  | RP | Reporting Period

## 2.QA-QC
Quality |  | Quality
| 2015-05-24 |  | 2015-05-24
Closed NCR | 0 | Closed NCR | 0
Closed TQ's | 11 | Closed TQ's | 20
Open NCR | 0 | Open NCR | 0
Open TQ's | 5 | Open TQ's | 7 | Outstanding | 0-10 Days | 11-20 Days | 21-30 Days | 31-60 Days | > 60 Days
TQs
Issued NCR | 0 | Issued NCR | 0 | NCRs
Issued NCR's | 16 | Issued NCR's | 27
Design NCrs
Closed NCR's | 10
Open NCR's | 7
Punchlist
[10 empty] | Construction to Commissioning | Plan | Actual
[10 empty] | System Turnovers | 5 | 10
[10 empty] | Project to Entity | Plan | Actual
[10 empty] | System Turnovers | 5 | 10
[10 empty] | Punchlist Items | Last Rep. Period | This Rep. Period
Total Cumulative Punchlist items
Total Open Punchlist Items

## 4.Progress
Plan:
| 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | F2Y | F3Y | F4Y | F5Y | F6Y | F7Y | F8Y
Plan | 0% | 1.869% | 3% | 5% | 8.5% | 12.5% | 15% | 17.5% | 20% | 22.5% | 25% | 27.5% | 30% | 32.5% | 35% | 37.5% | 40% | 42.5% | 72.5% | 100% | 100% | 100% | 100% | 100% | 100%
Forecast |  |  |  | 4.059% | 6.089% | 8.12% | 10.15% | 12.18% | 14.21% | 16.24% | 19% | 22% | 25% | 28% | 32% | 35% | 38% | 41%
Actual | 0% | 1.331% | 2.029% | 4.059%: 4.059% | 72.5% | 100% | 100% | 100% | 100% | 100% | 100%

## 5.Key Milestones
Milestone | Planned Date | Forecast Date | Actual Date | Variance | Notes
Completion of Section 1D Earthwork Activities | 2017-03-13 | 2017-03-13 | 2017-05-07 | 55
Completion of Section 1C Earthwork Activities | 2017-03-20 | 2017-03-20 | 2017-05-30 | 71
Delivery of Main Transformer | 2017-04-15 | 2017-04-15 | 2017-05-15 | 30
Completion of Concrete Works at Overpass C1-O003 KM @ 0+027.67 | 2017-03-28 | 2017-03-28
Completion of Concrete Works at Box Culvert C1-C044 KM @ 4+425 | 2017-03-18 | 2017-03-18
Geotechnical Seismic Calculations | 2017-03-20 | 2017-03-20
Completion of Pipe Culvert C1-P030 KM @ 3+035 | 2017-03-10 | 2017-03-10 | 2017-03-12 | 2
Start of Pipe Culvert C1-P027 KM @ 2+665 | 2017-03-10 | 2017-03-10 | 2017-03-20 | 10
Completion of Sub-Grade Crushing for KM 0+000 - 8+740 | 2015-05-15 | 2015-05-15

## 6.Resources
Head-Count | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01
Planned Headcount | 5 | 5 | 8 | 8 | 10 | 15 | 20 | 20 | 25 | 30 | 35 | 35 | 40 | 45 | 45 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 30 | 10
Forecast Headcount | 2 | 2 | 3 | 3 | 8 | 8 | 10 | 20 | 25 | 30 | 35 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 10
Actual Headcount | 2 | 2 | 3 | 3 | 8 | 8 | 10 | 20 | 25 | 30 | 35 | 50 | 50 | 50 | 50 | 50 | 50
48
Hours | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01
Planned | 240 | 240 | 384 | 384 | 480 | 720 | 960 | 960 | 1200 | 1440 | 1680 | 1680 | 1920 | 2160 | 2160 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 1920 | 1440 | 480
Cum. Planned | 240 | 480 | 864 | 1248 | 1728 | 2448 | 3408 | 4368 | 5568 | 7008 | 8688 | 10368 | 12288 | 14448 | 16608 | 19008 | 21408 | 23808 | 26208 | 28608 | 31008 | 32928 | 34368 | 34848
Forecast | 96 | 96 | 144 | 144 | 384 | 384 | 480 | 960 | 1200 | 1440 | 1680 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400 | 1440 | 1440 | 1440 | 1440 | 1440 | 864 | 288
Cum. Forecast | 96 | 192 | 336 | 480 | 864 | 1248 | 1728 | 2688 | 3888 | 5328 | 7008 | 9408 | 11808 | 14208 | 16608 | 19008 | 21408 | 22848 | 24288 | 25728 | 27168 | 28608 | 29472 | 29760
Actual | 96 | 96 | 144 | 144 | 384 | 384 | 480 | 960 | 1200 | 1440 | 1680 | 2400 | 2400 | 2400 | 2400 | 2400 | 2400
Cum. Actual | 96 | 192 | 336 | 480 | 864 | 1248 | 1728 | 2688 | 3888 | 5328 | 7008 | 9408 | 11808 | 14208 | 16608 | 19008 | 21408

## 7.QtyTk
[7 empty] | JOBHOURS | [7 empty] | PERFORMANCE
|  |  | QUANTITIES | [5 empty] | SPENT |  | EARNED |  | SCHEDULE |  | SPI |  | JHP |  | PERCENT COMPLETE |  |  | UNIT RATE (hrs/unit)
Cost Account | Description | UOM | Current Forecast | Current Budget | To Date | This Period | Current Forecast | Current Budget | To Date | This Period | To Date | This Period | To Date | This Period | To Date | This Period | To Date | This Period | Schedule (C.B.) | Actual (C.B.) | Actual (C.F.) | Current Forecast | Current Budget | To Date | This Period
|  |  | A | B | C | D | E | F | G | H | I=C/B*F | J=D/B*F | K | L | M=I/K | N=J/L | O=I/G | P=J/H | Q=K/F | R=I/F | S=I/E | T=E/A | U=F/B | V=G/C | W=H/D
100 | Sitework | M2
110 | Concrete | M3
120 | Steel | MT
130 | Architectural | M2
140 | Piping | LM
150 | Electrical | LM
160 | Instrumentation | EA
170 | Pumps & Drivers | EA
TOTAL
|  |  | NOTES: | UOM = Unit of Measurement
Current Budget = Original Budget + Scope Change
Current Forecast = Original Budget + Scope Change + Trends
SPI = Schedule Perfrmance Index (Good performance => 1.0 Bad performance < 1.0)
JHP = Job Hour Performance (others refer as Performance Factor) (Good performance => 1.0 Bad performance < 1.0)

## 8.Cost
Description | TOTAL (Jobhours) | TOTAL (SAR) | UNIT RATE (SAR/HR)
Contract Value
Previous Approved Variations
This Period's Approved Variations
Sub-Total | 0 | 0
Pending Variations
TOTAL | 0 | 0
Contract ITD
Description | TOTAL (SAR) | Days Overdue
Invoiced to Date
Paid to Date
Advanced Payment
Balance
Overdue
Cost Perf. Index
 | time axis 2014-12-30 to 2015-03-03
|  |  |  | 0.035455 | 0.035455 |  |  | 0.037037 | 0.037037 | 0.037037 | 0.037037 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.035494 | 0.032959 | 0.032959 | 0.032959 | 0.032959 | 0.032629 | 0.032629 | 0.032629 | 0.032629 | 0.032629 | 0.032629 | 0.032629 | 0.032629 | 0.032629 | 7 |  | 0.038462 | 0.038462 | 0.038462 | 0.038462 | 0.038462 | 0.038462 |  | 0.040486 | 0.040486 | 0.040486 | 0.040486 | 0.040486 | 0.040486 | 0.037594 | 0.037594 | 0.037594 | 0.037594 | 0.037594 | 0.037594 | 0.037594 | 0.037594
|  |  |  | 0 | 1118 |  |  | 5324 | 5880 | 0 | 3016 | 3800 | 4086 | 3321 | 1539 | 5246 | 5842 | 8706 | 1870 | 3450 | 1100 | 1100 | 0 | 1180 | 0 | 4200 | 840 | 0 | 980 | 0 | 2313 | 714 | 1490 | 770 | 1820 | 663527.74 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3788 | 4423 | 4326 | 2698 | 5016 | 3804 | 0 | 1100 | 4528 | 4512 | 7348 | 5421
|  |  |  | 0 | 0 |  |  | 3251 | 8397 | 0 | 2907 | 5424 | 7354 | 7684 | 8000 | 8047 | 0 | 0 | 5509 | 7124 | 6920 | 7234 | 6154 | 5387 | 0 | 5345 | 5072 | 6589 | 8320 | 5755 | 3601 | 7518 | 8057 | 8595 | 7974 | 497122.41 |  | 6900 | 7680 | 0 | 0 | 0 | 0 |  | 6642 | 0 | 4965 | 7770 | 7896 | 8417 | 10969 | 10111 | 0 | 9939 | 11306 | 11739 | 12421 | 9523
|  |  |  | 3101 | 1403 |  |  | 2997 | 3100 | 5393 | 5015 | 5175 | 4757 | 5500 | 4600 | 0 | 5740 | 5141 | 4493 | 4693 | 3980 | 4000 | 2854 | 3681 | 4992 | 4606 | 4774 | 4407 | 5000 | 3495 | 3392 | 4274 | 3701 | 6931 | 6010 | 615481.27 |  | 5291 | 5500 | 3500 | 5446 | 2764 | 2345 |  | 2895 | 3242 | 4618 | 3000 | 5500 | 6000 | 5500 | 5212 | 1909 | 4188 | 5354 | 4902 | 6838 | 5303
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 111.28 | 0 |  |  | 0 | 0 | 0 | 0 | 111.14 | 0 | 0 | 0 | 0 | 24.43 | 0 | 0 | 0 | 24.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118.1 |  | 0 | 55.8 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 54.49 | 52.7 | 0 | 107.62 | 0 | 0 | 112.93 | 57.16 | 0 | 0
|  |  |  | 102 | 85 |  |  | 83 | 0 | 76.9062 | 138 | 126 | 18 | 72 | 0 | 0 | 84 | 0 | 88 | 18 | 89 | 0 | 0 | 40.5 | 14 | 0 | 0 | 166 | 120 | 0 | 116 | 95 | 117.5 | 0 | 70 | 5175.63 |  | 0 | 127 | 134 | 120 | 0 | 122 |  | 110 | 277 | 110 | 90 | 90 | 430 | 0 | 90.5 | 0 | 0 | 139 | 207 | 106.43 | 0
|  |  |  | 0 | 0 |  |  | 65 | 0 | 72 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 53 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 250 | 90
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2.25 | 23.2
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 3117 | 1286 |  |  | 10135 | 21633 | 5622 | 11496 | 16718 | 5244 | 22325 | 21900 | 16899 | 6365 | 16377 | 16653 | 20036 | 18872 | 19691 | 16306 | 15589 | 5389 | 16440 | 15647 | 21238 | 22472 | 15814 | 11495 | 23289 | 21613 | 25578 | 23212 | 2008860.213 |  | 22011 | 22630 | 4000 | 3931 | 2983 | 2690 |  | 19792 | 3417 | 18003 | 21316 | 22823 | 24676 | 27034 | 28708 | 1909 | 25658 | 31664 | 32981 | 34786 | 29850
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32596 | 39943 | 37101 | 45613 | 44482 | 55000 | 59453 | 78342 | 76000.89 | 63455.94 | 55126 | 61328 | 81000 | 50180 | 30547 | 45941 | 61428 | 76519 | 73720 | 2257090.9131 |  | 64779 | 62000 | 0 | 0 | 0 | 59074 |  | 125775 | 56921 | 86854 | 94525 | 105233 | 90000 | 110000 | 107102 | 0 | 86314 | 103633 | 100542 | 98619 | 109196
|  |  |  | 2289 | 0 |  |  | 0 | 0 | 0 | 409 | 0 | 706 | 0 | 0 | 0 | 1768 | 0 | 0 | 0 | 0 | 0 | 0 | 1495.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1372934.92 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618.85 | 10130.69 | 4184.97 | 0
[36 empty] | 7838.64 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[60 empty] | 1-Mar to 9-Mar | 2015-03-09 | 2015-03-15 | 2015-03-22 | 2015-03-29 | 2015-04-05 | 2015-04-12 | 2015-04-19 | 2015-04-26 | 2015-05-03 | 2015-05-10 | 2015-05-17 | 2015-05-24 | 2015-05-31 | 2015-06-07 | 2015-06-14 | 2015-06-21 | 2015-06-28 | 2015-07-05 | 2015-07-12 | 2015-07-19 | 2015-08-02 | time axis 2014-12-30 to 2015-03-01
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 7 | 7 | 7.0385 | 7.0769 | 7.1154 | 7.1538 | 7.1923 | 7.2308 | 7.2308 | 7.2713 | 7.3117 | 7.3522 | 7.3927 | 7.4332 | 7.4737 | 7.5113 | 7.5489 | 7.5865 | 7.6241 | 7.6617 | 7.6992 | 7.7368 | 7.7744 | 8 | 0.21429 | 8.2143 | 8.4643 | 8.7143 | 8.9286 | 9.3029 | 9.36 | 9.6 | 9.84 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 663527.74 | 667315.74 | 671738.74 | 676064.74 | 678762.74 | 683778.74 | 687582.74 | 687582.74 | 688682.74 | 693210.74 | 697722.74 | 705070.74 | 710491.74 | 743855.74 | 24781 | 768636.74 | 776951.34 | 790133.34 | 802978.34 | 807062.28 | 820996.28 | 807797.8753 | 814261.28 | 821939.28 | 837343.76 | 852366.76 | 866109.76 | 871934.76 | 878090.76 | 869399.44 | 889630.44 | 947805.44 | 957611.44 | 1023077.44 | 1068509.18 | 1269801.18
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 497122.41 | 497122.41 | 504022.41 | 511702.41 | 511702.41 | 511702.41 | 511702.41 | 511702.41 | 511702.41 | 518344.41 | 518344.41 | 523309.41 | 531079.41 | 538975.41 | 547392.41 | 558361.41 | 568472.41 | 568472.41 | 578411.41 | 589717.41 | 601456.41 | 613877.41 | 623400.41 | 687967.42 | 44200 | 732167.42 | 768995.21 | 836220.21 | 899029.21 | 900113.95 | 967882.95 | 1032947.95 | 1086210.95 | 1105197.95 | 1205048.2 | 1274295.2 | 1348233.96 | 1440804.2457 | 1469172.2457 | 1395533.2733 | 1409898.2733 | 1448480.2733 | 1491091.5107 | 1536115.9539 | 1571958.2014 | 1697764.9904
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 615481.27 | 615481.27 | 620772.27 | 626272.27 | 629772.27 | 635218.27 | 637982.27 | 640327.27 | 640327.27 | 643222.27 | 646464.27 | 651082.27 | 654082.27 | 659582.27 | 665582.27 | 671082.27 | 676294.27 | 678203.27 | 682391.27 | 687745.27 | 692647.27 | 699485.27 | 704788.27 | 740580.27 | 25263 | 765843.27 | 779390.71 | 812926.71 | 849936.71 | 873067.27 | 907027.27 | 944714.27 | 977634.27 | 1009201.27 | 970386.4 | 991782.4 | 1010190.4 | 939396.4 | 953109.41 | 977579.35 | 984269.24 | 986699.42 | 998157.27 | 1010637.22 | 1013620.94 | 1045552.88
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1022 | 6948 | 15608.418 | 21590.418 | 27254.418 | 44941.1882 | 67876.8611 | 68015.1887 | 69355.1534
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 241.92 | 241.92 | 241.92 | 241.92 | 241.92 | 241.92 | 475.92 | 11549.38 | 13679.38 | 25125.73 | 33228.95 | 35374.95
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8811.4
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1118.1 | 1118.1 | 1118.1 | 1173.9 | 1173.9 | 1173.9 | 1173.9 | 1173.9 | 1173.9 | 1173.9 | 1173.9 | 1173.9 | 1173.9 | 1228.39 | 1281.09 | 1281.09 | 1388.71 | 1388.71 | 1388.71 | 1501.64 | 1558.8 | 1558.8 | 1558.8 | 1558.8 | 0 | 1558.8 | 1869.71 | 1869.71 | 2229.51 | 2419 | 2419 | 2419 | 2419 | 2419 | 2602.84 | 2602.84 | 2602.84 | 3171.118 | 3171.118 | 13895.68 | 14230.68 | 14615.64 | 0 | 300
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5175.63 | 5175.63 | 5175.63 | 5302.63 | 5436.63 | 5556.63 | 5556.63 | 5678.63 | 5678.63 | 5788.63 | 6065.63 | 6175.63 | 6265.63 | 6355.63 | 6785.63 | 6785.63 | 6876.13 | 6876.13 | 6876.13 | 7015.13 | 7222.13 | 7328.56 | 7328.56 | 8335.15 | 781 | 9116.15 | 8513.9 | 9949.9 | 10900.9 | 12040.04 | 12207.04 | 12477.04 | 12650.04 | 12600.5396 | 12516.38 | 12907.02 | 12992.02 | 13158.02 | 13556.22 | 13895.68 | 14230.68 | 14615.64 | 15304.12 | 15808.63 | 15887.88 | 20405.2403
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 170 | 170 | 258 | 878.66 | 984.52 | 984.52 | 1644.52 | 1874.52 | 1104.96 | 1131.36 | 1157.76 | 1188.76 | 1088.61 | 1106.11 | 1878.86
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 46 | 56 | 84 | 32.0915 | 158 | 179 | 934.5078 | 962.5078 | 977.5078 | 988.5078 | 988.5078 | 12990.74 | 13441.74 | 14252.68 | 18726.23 | 20228.17
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 350 | 440 | 1035 | 164 | 1199 | 404 | 1889.58 | 3228.04 | 3228.8446 | 5140.0199 | 7108.4325 | 8130.1378 | 9424.5587 | 3185.281 | 4428.5385 | 5322.7785 | 6455.6985 | 8050.4385 | 11898.4 | 13690.7 | 16130.95 | 18726.23 | 20228.17 | 22796.35 | 24799.3112
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 891.21 | 1794.65 | 3293.75 | 4216.54 | 4877.65 | 5141.06 | 5804.32 | 7078.39 | 8113.74 | 9221.53 | 11725.28 | 12558.28 | 12990.74 | 13441.74 | 14252.68 | 14811.11 | 14829.86 | 14829.86 | 14866.3
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 6.25 | 29.45 | 113.45 | 0 | 113.45 | 0 | 21.93 | 66.9471 | 120.6999 | 213.7595 | 320.8857 | 391.7968 | 527.1433 | 834.6405 | 1076.8859 | 1532.4323 | 2097.4077 | 2571.1377 | 3157.3 | 3683.87 | 4796.77 | 5562.065 | 6543.243 | 7334.453 | 7734.7798
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 2369.75 | 16209.75 | 17209.75 | 23709.75 | 20613.25 | 22498.25 | 23398.25
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001 | 4132.5 | 16479
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1696 | 1696 | 9224
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2.25 | 361.85
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2008860.213 | 2008860.213 | 2030871.213 | 2053501.213 | 2057501.213 | 2061432.213 | 2064415.213 | 2067105.213 | 2067105.213 | 2086897.213 | 2090314.213 | 2108317.213 | 2129633.213 | 2152456.213 | 2177132.213 | 2204166.213 | 2232874.213 | 2234783.213 | 2260441.213 | 2292105.213 | 2325086.213 | 2359872.213 | 2389722.213 | 2569933.213 | 122799 | 2692732.213 | 2939334.976 | 3090017.976 | 3269940.976 | 3818979.536 | 3999399.536 | 4187526.536 | 4343818.536 | 4545349.536 | 4528634.733 | 4699201.373 | 4876461.673 | 4962326.673 | 5035951.673 | 5066582.78 | 5103989.18 | 5193144.18 | 5318180.18 | 5440200.52 | 5545187.1 | 5851834.1
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2257090.9131 | 2257090.9131 | 2321869.9131 | 2383869.9131 | 2383869.9131 | 2383869.9131 | 2383869.9131 | 2442943.9131 | 2442943.9131 | 2568718.9131 | 2625639.9131 | 2712493.9131 | 2807018.9131 | 2912251.9131 | 3002251.9131 | 3112251.9131 | 3219353.9131 | 3219353.9131 | 3305667.9131 | 3409300.9131 | 3509842.9131 | 3608461.9131 | 3717657.9131 | 4428877.9131 | 649246 | 5078123.9131 | 5529603.691 | 5711216.691 | 5960762.691 | 10614967.1194 | 10934845.1194 | 11364169.1194 | 11873597.1194 | 12340299.1194 | 9193661.4 | 9488141.4 | 9724549.4 | 9754940.4 | 9978878.4 | 10847758.08 | 10909965.48 | 11344099.48 | 11803963.48 | 12165961.95 | 13799002.8 | 14226988.8
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1372934.92 | 1375553.77 | 1385684.46 | 1389869.43 | 1389869.43 | 1395532.54 | 18063.93 | 1413596.47 | 1728271.3135 | 1741923.7635 | 1758253.9835 | 2050536.7435 | 2077942.4935 | 2119935.2035 | 2148402.1635 | 2172790.5935 | 2897751.69 | 2898897 | 2898897 | 2891278.27 | 2891278.27 | 3516114.76 | 3516114.76 | 3518155.23 | 3518155.23 | 3522039.63 | 4037717.26 | 4088429.9048
|  |  |  | 2015-01-31: 7838.64; 2015-02-01: 7838.64; 2015-02-02: 7838.64; 2015-02-03: 7838.64; 2015-02-04: 7838.64; 2015-02-05: 7838.64; 2015-02-06: 7838.64; 2015-02-07: 7838.64; 2015-02-08: 7838.64; 2015-02-09: 7838.64; 2015-02-10: 7838.64; 2015-02-11: 7838.64; 2015-02-12: 7838.64; 2015-02-13: 7838.64; 2015-02-14: 7838.64; 2015-02-15: 7838.64; 2015-02-16: 7838.64; 2015-02-17: 7838.64; 2015-02-18: 7838.64; 2015-02-19: 7838.64; 2015-02-20: 7838.64; 2015-02-21: 7838.64; 2015-02-22: 7838.64; 2015-03-01: 7838.64 | 0 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 0 | 0 | 0 | 0 | 0 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64 | 7838.64
|  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
90257538.1974
5318180.18
11803963.48
3518155.23
7838.64
0
9327142.2213

## 8.CO&Trends
| Change Order Log | Date Initiated | Value (SAR) | Days | Comments
| Current Budget Last Report |  | 45000000 | 350
1 | Upgrade A/C System | 2016-07-17 | 3000000 | 30
2 | Increase the area of Kitchen | 2016-08-18 | 850000 | 45
3 | Material change | 2016-09-07 | -600000 | 0
4 | Labor Change | 2016-09-28 | 1150000 | -10
5
6
7 | Current Budget This Report |  | 49400000 | 415
8
9 | Pending Change Order Log | Date Initiated | Value (SAR) |  | Comments
10 | Increase thermal insulation |  | 250000
11 | Delete Car Park Covers |  | -340000
12
13
14 | Total Pending |  | -90000
Cash GM
CWC
GM TOTAL

## 9.POs
Shop Drawings | [11 empty] | Materials Approval Sheets (MAS)
|  | Total | Total Processed Drawings |  |  |  |  | Total | To Go | Pending | Total | Total | Total Processed Drawings |  |  |  |  | Total | To Go | Pending | Total
Discipline |  |  | A | B | C | D | E | Processed |  | with Designer | Submittals |  | A | B | C | D | E | Processed |  |  | Submittals
Civil
Structural
Architectural
MEP | Mechanical
Electrical
ELV
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials Approval Sheets (MAS)
|  | Total | Total Processed Drawings |  |  |  |  | Total | To Go | Pending | Total
Discipline |  |  | A | B | C | D | E | Processed |  | with Designer | Submittals
Civil
Structural
Architectural
MEP | Mechanical
Electrical
ELV
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Procurement Summary Report
[22 empty] | Discipline |  | Delivery First | Delivery First | Total Material Submittals (MAS) | Total Processed MAS | TO GO MAS | Total Number P.O. | Total Actual P.O. | TO GO P.O.
[22 empty] | Civil |  | DD/MM/YYYY | DD/MM/YYYY
[22 empty] | Structural |  | DD/MM/YYYY | DD/MM/YYYY
[22 empty] | Architectural |  | DD/MM/YYYY | DD/MM/YYYY
[22 empty] | MEP | Mechanical | DD/MM/YYYY | DD/MM/YYYY
[23 empty] | Electrical | DD/MM/YYYY | DD/MM/YYYY
[23 empty] | ELV | DD/MM/YYYY | DD/MM/YYYY
[23 empty] | Plumbing | DD/MM/YYYY | DD/MM/YYYY
[22 empty] | TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CODE
[32 empty] | A | Reviewed; Work may proceed
[32 empty] | B | Reviewed with comments; Revise and resubmit;
[32 empty] | C | Work may proceed subject to incorporation of comments
[32 empty] | D | Objection - Revise and resubmit; Work may not proceed
[32 empty] | D | Rejected
[32 empty] | E | Review not required; Work may proceed

## 11.Skyline
BUILDING SERVICES SYSTEM TESTING & COMMISSIONING HAND-OVER SKYLINE
SUB-SYSTEMS COUNT | 5
4
| 3 | [8 empty] | 300-A
| 2 |  |  |  |  | 200-C |  |  |  | 100-D |  | 300-C |  | 300-E
| 1 |  |  | 200-A | 200-B | 200-D | 100-A | 100-B | 100-C | 100-E | 300-B | 300-D | 100-F | 300-F | 300-G | 300-H
| Increment |  |  | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 | 1
| Cumulative |  |  | 1 | 2 | 4 | 5 | 6 | 7 | 10 | 11 | 13 | 14 | 16 | 17 | 18
Week Count from Award |  | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Week Ending |  | 2017-09-22 | 2017-09-29 | 2017-10-06 | 2017-10-13 | 2017-10-20 | 2017-10-27 | 2017-11-03 | 2017-11-10 | 2017-11-17 | 2017-11-24 | 2017-12-01 | 2017-12-08 | 2017-12-15 | 2017-12-22 | 2017-12-29 | 2018-01-05
LEGEND:
|  | SYSTEM |  |  |  |  | SYSTEM |  |  |  |  | SYSTEM
|  | 100 | MECHANICAL SYSTEM |  |  |  | 200 | ELECTRICAL SYSTEM |  |  |  | 300 | LOW CURRENT SYSTEM
|  | SUB-SYSTEM |  |  |  |  | SUB-SYSTEM |  |  |  |  | SUB-SYSTEM
| 1 | 2017-09-22: 100-A; 2017-09-29: Fire Sprinkler, Hydrants & Hose; 2017-10-20: 7; 2017-10-27: 200-A; 2017-11-03: Power; 2017-11-24: 11; 2017-12-01: 300-A; 2017-12-08: BMS
| 2 | 2017-09-22: 100-B; 2017-09-29: Water; 2017-10-20: 8; 2017-10-27: 200-B; 2017-11-03: Lighting; 2017-11-24: 12; 2017-12-01: 300-B; 2017-12-08: Fire Alarm
| 3 | 2017-09-22: 100-C; 2017-09-29: Drainage; 2017-10-20: 9; 2017-10-27: 200-C; 2017-11-03: Emergency Generator Power; 2017-11-24: 13; 2017-12-01: 300-C; 2017-12-08: Data Infrastructure (IT)
| 4 | 2017-09-22: 100-D; 2017-09-29: Life Safety System; 2017-10-20: 10; 2017-10-27: 200-D; 2017-11-03: Earthing & Lightning; 2017-11-24: 14; 2017-12-01: 300-D; 2017-12-08: Access Control
| 5 | 2017-09-22: 100-E; 2017-09-29: HVAC; 2017-11-24: 15; 2017-12-01: 300-E; 2017-12-08: CCTV
| 6 | 2017-09-22: 100-F; 2017-09-29: Irrigation; 2017-11-03: Started; 2017-11-24: 16; 2017-12-01: 300-F; 2017-12-08: PA-BGM
[8 empty] | Completed |  |  | 17 | 300-G | Audio/Video
[11 empty] | 18 | 300-H | WIFI & Access Points

## 12.T&C
Test Description | Planned Start | Planned Finish | Forecast Start | Forecast Finish | Actual Start | Actual Finish | % Completed
Mechanical System T&C | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%
Electrical System T&C | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%
Extra Low Voltage System T&C | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%
High Voltage System T&C | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%
Fire and Life Safety System Integration Testing | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%
ELV System Integration Testing | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%
Other Integration Testing | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%
Post-occupancy Testing | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 10%