## Quantity Tracker Summar
| Project No. : ____________________________________ | [20 empty] | Report Date : ________________
| Project Descripton : ______________________________ | [20 empty] | Week Ending : _______________
Project Location : ________________________________
Entity : ________________________________________
Contractor : ____________________________________
[8 empty] | JOBHOURS | [7 empty] | PERFORMANCE
|  |  |  | QUANTITIES | [5 empty] | SPENT |  | EARNED |  | SCHEDULE |  | SPI |  | JHP |  | PERCENT COMPLETE |  |  | UNIT RATE (hrs/unit)
| Cost Account | Description | UOM | Current Forecast | Current Budget | To Date | This Period | Current Forecast | Current Budget | To Date | This Period | To Date | This Period | To Date | This Period | To Date | This Period | To Date | This Period | Schedule (C.B.) | Actual (C.B.) | Actual (C.F.) | Current Forecast | Current Budget | To Date | This Period
|  |  |  | A | B | C | D | E | F | G | H | I=C/B*F | J=D/B*F | K | L | M=I/K | N=J/L | O=I/G | P=J/H | Q=K/F | R=I/F | S=I/E | T=E/A | U=F/B | V=G/C | W=H/D
| 100 | Sitework | M2
| 110 | Concrete | M3
| 120 | Steel | MT
| 130 | Architectural | M2
| 140 | Piping | LM
| 150 | Electrical | LM
| 160 | Instrumentation | EA
| 170 | Pumps & Drivers | EA
TOTAL
|  |  |  | NOTES: | UOM = Unit of Measurement
Current Budget = Original Budget + Scope Change
Current Forecast = Original Budget + Scope Change + Trends
SPI = Schedule Perfrmance Index (Good performance => 1.0 Bad performance < 1.0)
JHP = Job Hour Performance (others refer as Performance Factor) (Good performance => 1.0 Bad performance < 1.0)
This Document is the exclusive property of Government Expenditure & Projects Efficiency Authority and is subject to the restrictions set out in the Important Notice contained in this Document.

## Quantity Tracker Details
QUANTITY TRACKER DETAILS
| Project No. : ____________________________________ | [20 empty] | Report Date : ________________
| Project Descripton : ______________________________ | [20 empty] | Week Ending : _______________
Project Location : ________________________________
Entity : ________________________________________
Contractor : ____________________________________
[8 empty] | JOBHOURS | [7 empty] | PERFORMANCE
|  |  |  | QUANTITIES | [5 empty] | SPENT |  | EARNED |  | SCHEDULE |  | SPI |  | JHP |  | PERCENT COMPLETE |  |  | UNIT RATE (hrs/unit)
| Cost Account | Description | UOM | Current Forecast | Current Budget | To Date | This Period | Current Forecast | Current Budget | To Date | This Period | To Date | This Period | To Date | This Period | To Date | This Period | To Date | This Period | Schedule (C.B.) | Actual (C.B.) | Actual (C.F.) | Current Forecast | Current Budget | To Date | This Period
|  |  |  | A | B | C | D | E | F | G | H | I=C/B*F | J=D/B*F | K | L | M=I/K | N=J/L | O=I/G | P=J/H | Q=K/F | R=I/F | S=I/E | T=E/A | U=F/B | V=G/C | W=H/D
| 100.100.100 | Structural Excavation - Machine & Hand | M3## | 4461.09 | 6458.93 | 4460.86 | 133.8258 | 2963.91 | 3520 | 4691.5 | 86 | 2431.088 | 72.9326 | 2505 | 74.4081 | 0.97049 | 0.98017 | 0.51819 | 0.84805 | 71.16% | 69.06% | 82.02% | 0.66439 | 0.54498 | 1.0517 | 0.64263
| 100.100.200 | Backfill, Machine & Some Hand | M3## | 10177.32 | 4712.62 | 4200 | 126 | 25666.07 | 16081.51 | 16564 | 350 | 14332.2275 | 429.9668 | 15639.6705 | 326.0918 | 0.9164 | 1.3185 | 0.86526 | 1.2285 | 97.25% | 89.12% | 55.84% | 2.5219 | 3.4124 | 3.9438 | 2.7778
| 100.100.100 | Trench'g Excav & Bkf'l, Excavation | M3## | 3411.03 | 3820.05 | 3450 | 103.5 | 7260 | 7397.45 | 16210.5 | 170.745 | 6680.8556 | 200.4257 | 7369.8492 | 224.5225 | 0.90651 | 0.89268 | 0.41213 | 1.1738 | 99.63% | 90.31% | 92.02% | 2.1284 | 1.9365 | 4.6987 | 1.6497
| 100.100.100 | Trench'g Excav & Bkf'l, Backfill | M3## | 3645.72 | 4394.33 | 3645.51 | 109.3653 | 7659.82 | 8395.35 | 7215 | 201 | 6964.7324 | 208.942 | 7170.847 | 231.77 | 0.97126 | 0.90151 | 0.96531 | 1.0395 | 85.41% | 82.96% | 90.93% | 2.101 | 1.9105 | 1.9791 | 1.8379
| 100.100.300 | Bored Piles - Spoil Removal | M3 | 678 | 676 | 670 | 20.1 | 789.11 | 786.68 | 1779 | 35 | 779.6976 | 23.3909 | 770 | 27.7901 | 1.0126 | 0.8417 | 0.43828 | 0.66831 | 97.88% | 99.11% | 98.81% | 1.1639 | 1.1637 | 2.6552 | 1.7413
| 100.100.400 | Fencing, Chain Link | LM | 176.9 | 231 | 97 | 2.91 | 2782.33 | 2860 | 2018 | 30 | 1200.9524 | 36.0286 | 1050 | 22.7569 | 1.1438 | 1.5832 | 0.59512 | 1.201 | 36.71% | 41.99% | 43.16% | 15.7283 | 12.381 | 20.8041 | 10.3093
| 100.100.400 | Fencing, Gates | EA | 6 | 8 | 2 | 0.06 | 107.4 | 244 | 80 | 3 | 61 | 1.83 | 55 | 1.4054 | 1.1091 | 1.3021 | 0.7625 | 0.61 | 22.54% | 25% | 56.8% | 17.9 | 30.5 | 40 | 50
| 100.100.500 | Guard Posts | EA | 110 | 100 | 90 | 2.7 | 480 | 450 | 350 | 15 | 405 | 12.15 | 445.5 | 12.6816 | 0.90909 | 0.95808 | 1.1571 | 0.81 | 99% | 90% | 84.38% | 4.3636 | 4.5 | 3.8889 | 5.5556
| 100.100.600 | Drainage & Sewers (Gravity only) Manhls, Catch Basins & other | EA | 4 | 4 | 4 | 0.12 | 68.12 | 68 | 115 | 4 | 68 | 2.04 | 65 | 2.4444 | 1.0462 | 0.83456 | 0.5913 | 0.51 | 95.59% | 100% | 99.82% | 17.03 | 17 | 28.75 | 33.3333
| 100.100.100 | Structural Excavation - Machine and Hand | M3## | 4462.67 | 6451.42 | 4462.67 | 133.8801 | 4950 | 5200 | 6293.5 | 95 | 3597.0196 | 107.9106 | 3207.5866 | 99.9976 | 1.1214 | 1.0791 | 0.57155 | 1.1359 | 61.68% | 69.17% | 72.67% | 1.1092 | 0.80602 | 1.4103 | 0.70959
| 100.100.200 | Backfill, Machine & Some Hand | M3## | 1899 | 5433.75 | 1899 | 56.97 | 4034.49 | 10911 | 4671.5 | 125 | 3813.2025 | 114.3961 | 2895 | 131.0008 | 1.3172 | 0.87325 | 0.81627 | 0.91517 | 26.53% | 34.95% | 94.52% | 2.1245 | 2.008 | 2.46 | 2.1941
| 100.100.100 | Trench'g Excav & Bkf'l, Excavation | M3## | 5099.14 | 4890 | 4560 | 136.8 | 5926.81 | 5367.57 | 6223 | 158 | 5005.3413 | 150.1602 | 5105 | 156.8462 | 0.98048 | 0.95737 | 0.80433 | 0.95038 | 95.11% | 93.25% | 84.45% | 1.1623 | 1.0977 | 1.3647 | 1.155
| 100.100.100 | Trench'g Excav & Bkf'l, Backfill | M3## | 3560 | 3498.66 | 3332.4 | 99.972 | 11600 | 11461.62 | 7841.5 | 359 | 10916.9518 | 327.5086 | 11082 | 373.7254 | 0.98511 | 0.87633 | 1.3922 | 0.91228 | 96.69% | 95.25% | 94.11% | 3.2584 | 3.276 | 2.3531 | 3.591
| 100.100.300 | Bored Piles - Spoil Removal | M3 | 647.56 | 648 | 647.56 | 19.4268 | 751.17 | 751 | 724.5 | 35 | 750.4901 | 22.5147 | 735 | 26.9973 | 1.0211 | 0.83396 | 1.0359 | 0.64328 | 97.87% | 99.93% | 99.91% | 1.16 | 1.159 | 1.1188 | 1.8016
| 100.100.400 | Landscaping Fencing & Roads - Fencing | LM | 44 | 44 | 43 | 1.29 | 393.8 | 394 | 453 | 15 | 385.0455 | 11.5514 | 370 | 13.6048 | 1.0407 | 0.84906 | 0.84999 | 0.77009 | 93.91% | 97.73% | 97.78% | 8.95 | 8.9545 | 10.5349 | 11.6279
Note : UOM with ## are main commodity
This Document is the exclusive property of Government Expenditure & Projects Efficiency Authority and is subject to the restrictions set out in the Important Notice contained in this Document.