## NPMO Architecture DL
SN | Deliverable | Tool | Deliverable Contents | Developed During * | Deliverable/ Data required for
[5 empty] | Proccurement | Construction | Start-Up & Commissioing | Project Controls | Comments
1 | Arch. Adjacency Diagram | MS Excel | This diagram shows primary and secondary relationships between rooms / spaces in the facilities (i.e., which ones must be next to each other and which ones should be in a close vicinity. This feeds the development of the floor plans developed in the schematic design process. | B
2 | Arch. program of spaces / rooms | MS Word / MS Excel | Defines spacial requirements for each room / space in a building facility including usage, electrical and mechanical requirements and staff. This feeds the development of the floor plans developed in the schematic design process. | B
3 | Architectural Rendering | InfraWorks, 3DS Max, Revit, Stingray | Perspective views of the overall project, usually a color rendering. | B |  | Y
4 | Virtual Reality Files | NavisWork, InfraWorks, Stingray | 3-dimensional design review packages to offer 3D viewing of a design in real-time to allow design-review, comment, red-lining or measurement. | B |  | Y |  | Y
5 | Requirements Matrix | MS Word / MS Excel | Provides details of client requirements and assurance that requirements have been met for occupancy and operation of completed facilities. | B
6 | Building Area Calculations | MS Word / MS Excel/ Revit Architectural / 2D | Provides illustration of Gross Floor Area, Gross Leasable and Net Usable areas for Office Buildings planned for tenant leasing | B
7 | Building Code Analysis and Compliance report | MS Word | Based on the codes defined in the design criteria, this report determines the code requirements for the Use Group and Building Type in order to facilitate the design process. | B
8 | Building Fire and Life Safety Analysis Report, including Egress Analysis | MS Word / Revit Architectural / 2D | Analysis of the building's performance in meeting requirements for fire, life safety, and safe evacuation of personnel for egress out of the building in an emergency situation. | D
9 | Index / Legend / Symbols Sheet | Revit Architectural / 2D | List / Description of architectural drawings, abbreviations, symbols, and legends. | D |  | Y | Y
10 | Conceptual Design Drawings / Sketches and Rendering | InfraWorks, 3DS Max, Revit, Stingray | General layout studies and sketches evaluating project design alternatives. | B |  | Y
11 | Site Master Plan | Revit Architectural | Depicts site development and facilities / land use in various project phases such as pre-construction, first phase facility construction, first phase operation during second phase construction, etc., until final phase turnover to the client. | B |  | Y |  | Y
12 | Site Plan | Revit Architectural | Depicts site development of buildings, facilities and landscaping. | B |  | Y |  | Y
13 | Reflected Ceiling Plans | Revit Architectural | Plans of ceilings including electrical, mechanical, piping, fire-suppression layout. | D |  | Y | Y
14 | Roof Plans | Revit Architectural | Plan view of each building roof showing materials, drainage, equipment, access hatches, fall arrest, Building Maintenance Units (BMU) and any special details. | D |  | Y
15 | Enlarged Floor Plans | Revit Architectural | Plans of partial areas of building, enlarged to more clearly show arrangement and details. | D |  | Y
16 | Floor Plans | Revit Architectural | Plan view of all building floors showing location and arrangement of architectural components. This will also include Fire and Life Safety plans and Floor, Wall and Ceiling Finishes plans. | D |  | Y
17 | Building Cross Sections | Revit Architectural | Shows sections through buildings to show relation of walls and roof to structure, heights, and materials. This will also include Fire and Life Safety compartment sections. | B/D |  | Y
| Building Interior Elevations | Revit Architectural | Internal elevations indicating finishes, heights and elevational details. | D |  | Y
18 | Building Interior Details | Revit Architectural | Large scale plan / section details for special interior conditions. | D |  | Y
19 | Building Exterior Elevations | Revit Architectural | Shows each building façade identifying materials and arrangement of architectural elements. Shall include louver, window and door tag. Elevations and heights shall also be shown. | D |  | Y
20 | Out-Building Plans, Elevations, and Sections | Revit Architectural | Plan, exterior elevation, and cross section of smaller buildings (combined on one drawing). | D |  | Y
21 | Stairs, Plans and Sections | Revit Architectural | Shows plan and section view of stairs and stair shafts. Riser count, stair angle, heights and landing levels shall be indicated including landing and balustrade elevations. | D |  | Y
22 | Wall Sections | Revit Architectural | Shows at a larger scale the assembly of materials and systems in each type of building wall. | D |  | Y
23 | Building Exterior Details | Revit Architectural / 2D | Large scale plan / section details for exterior conditions including thermal insulation and air-tightness considerations | D |  | Y
24 | Wall Details | Revit Architectural / 2D | Wall details including anchorage, construction, and reinforcement. Details to include fire-stopping and opening and penetration details. | D |  | Y
25 | Door Schedule and Details | Revit Architectural / 2D | List of doors, sizes, types, and reference details. Shows head, jamb, electronic locking systems, key pads, swipe card identification and sill conditions for each type door for each wall / floor condition. Provide each door with a unique identification number and door hardware schedule. | D | Y | Y |  | Y
26 | Membrane Roofing Details | Revit Architectural / 2D | Plan and section details for membrane roofing conditions. | D |  | Y
27 | Metal Roofing Details | Revit Architectural / 2D | Plan and section details for metal roofing conditions. | D |  | Y
28 | Miscellaneous Details | Revit Architectural / 2D | Large scale plan / section details of miscellaneous conditions. | D |  | Y
29 | Interior Wall Elevations | Revit Architectural | View of interior walls (when required). | D |  | Y
30 | Finish / Paint Schedule | Revit Architectural | Lists each building room and specifies ceiling, wall, and floor substrates and finishes including wall base/skirting. | D | Y | Y |  | Y
31 | Wall Type Schedules | Revit Architectural | List of interior walls, sizes, construction types, and reference details. Shows anchorage and penetration conditions for each wall. | D | Y | Y |  | Y
32 | Window Schedule and Details | Revit Architectural | List of windows including size, types, reference details, and specific details showing head, jamb, and sill conditions for each wall condition. Provide each window with a unique identification number. | D | Y | Y |  | Y
33 | Control Desk Detailed Design | Revit Architectural | Room layout and Ergonomic Studies (Input from Rail Systems) | D
34 | Elevator Plans, Sections, and Details | Revit Architectural | Plan and section view of elevator hoist way (coordination with lift and escalator subcontractor). | D |  | Y
35 | Landscaping Plans and Details | 2D | Shows planting, landscape and irrigation plans, plant material, surface utilities and irrigation schedule and installation details. Shall also include sidewalks, site lighting, site furniture, bollards and water features. | D |  | Y
36 | Louver Schedule and Louver Details | Revit Architectural | List of louvers including size, types, reference details, and specific details showing head, jamb, and sill conditions for each wall condition. Provide each louver with a unique identification number. | D | Y | Y |  | Y
37 | Colony Site Layout Drawings | Revit, 2D | Housing colony site planning drawings, including roadway, building, and landscaping arrangements. | D
38 | Counters / Station layout and specification notes | Revit Architectural | Counters / Station layout and specification notes. | D |  | Y
39 | Design Management Plan | MS Word | Designer's understanding of the SOW and Services to be provided including organization chart, high light sub-consultant, delivery schedule. Developed by Design Subcontractor. Not a standard deliverable; typically by subcontractor per Exhibit D of subcontract. | D
40 | Pedestrian flow model | Various Simulation software | Used to test the floor plan of space / room to ensure the level of service for that facility is met and verify choking conditions / scenarios. | D
41 | Signage Drawings & Details | Revit Architectural | Exterior and Interior set of drawings & details (if applicable). | D |  | Y |  | Y
42 | Furniture Layout | Revit | Layout and schedules. | D |  | Y
43 | Furniture cut sheets and other Catalog Items | Revit | Furniture cut sheets and other Catalog Items. | D
44 | Sustainability Design Plan / LEED | MS Word | Sustainability Plan and Report to meet project-specific requirements. | B
45 | Material Assignment Schedule (MAS) and Contract Assignment Schedule (CAS) | MS Excel | Developed by Contracts group with Engineering input | B&D | Y |  |  | Y
46 | Construction Facilities / Site Coordinating Plan | 2D | Shows the location and type of required facilities, including lay down areas, trailer locations, fabrication areas, and temporary warehouses. | B&D |  | Y
47 | Permitting submittals | PDF | Includes documents and drawings required for applicable construction and environmental permitting activities for the project | B |  | Y
48 | Design Basis / Design Criteria Document | MS Word | Refer document EPM-KEA-TP-000003 for the contents of Design Criteria | B
49 | Scope of Work/ Specifications | MS Word | Description of the work to be constructed including Products, Installation requirements, Quality standards to be achieved | B&D | Y | Y | Y
50 | Data Sheet(s) | MS Word/ MS Excel | Engineered component data sheets which are generated to include all functional requirements for the inclusion within subcontract packages. | D |  | Y | Y
51 | Bulk Quantity Takeoff / BOQ | MS Excel/ MS Access | Bulk Quantity Takeoffs (QTOs) for tracking engineering-released quantities at 30%, 60%, & 90% Milestones to support construction installation: Cables (LM), Cable trays/ conduits (LM) by Facility and / or System | B&D |  | Y |  | Y
52 | Tagged Material Tracking / BOQ | MS Excel/ MS Access | Equipment and Specialty Items (EA): Includes tags, sizes, description, qty, physical dimensions, weight, capacity, datasheet (fit / function) type information. | B&D |  | Y | Y | Y
53 | Engineering Progress Report | MS Excel | Engineering provides input of the progress and performance measurement tool used on the project | D |  | Y | Y | Y
|  |  | Electronic documents once printed, are uncontrolled and may become outdated. Refer to ECMS for current revision. This Document is the exclusive property of Government Expenditure & Projects Efficiency Authority. And is subject to the restrictions set out in the Important Notice contained in this Document. | * B- Basic Design phase, D - Detailed Design Phase
**THIS LIST IS NON-EXHAUSTIVE AND DOES NOT REPRESENT A COMPLETE SET OF ARCHITETCURAL DELIVERABLES. ALL PROJECTS WILL REQUIRE A UNIQUE DETAILED LIST TO BE PREPARED USING THE ABOVE AS GUIDANCE.