## Sheet1
Tender Status Report (TSR) Template
| DATE OF REPORT: | <<INSERT DATE OF TSR>> | [13 empty] | KEY TO MILESTONE DATES: | Critical / Overdue | Due in next 7 days | Due between 7 to 14 days | Completed
TSR Ref | Agreement Number | Agreement Title | Departments / Key Personnel |  |  | Dates | Requisition Dates (Originators Milestones) |  |  | Prequalification Period |  |  |  | Tender Period | [8 empty] | Comments
|  |  | Originating Department | Originator | Contract Specialist |  | 60% | 90% | 100% | EOI Issued | PQQ Issued | PQQ Due | Tenderers Selected | ITT Issued | Tender Opening | Shortlisting Complete | Evaluations & Negotiations Completed | Recommendation to Award Submitted | Authority Approval to Award | Ministry of Finance Approval | Agreement Executed | Notice to Proceed
1 | [5 empty] | S
F
A
2 | [5 empty] | S
F
A
3 | [5 empty] | S
F
A
4 | [5 empty] | S
F
A
5 | [5 empty] | S
F
A
6 | [5 empty] | S
F
A
* Dates
S = Scheduled / Baseline as per Project Master Schedule
F = Current Forecast for uncompleted Milestones
A = Actual Date Milestone Completed