## Sheet1
| BUDGET |  |  |  |  | EARNED |  |  |  | FORECAST |  | VARIANCE |  | PERCENT COMPLETE
| Original Budget |  | Scope Change | Trends | Current Budget | Schedule Earned | Actual Earned | Actual Hrs | To Date Perf | To Go Fct | Total Fct | Sched Var | Cost Var | Sched (Bud) | Actual (Bgt) | Actual (Fct)
| (A) | (B) | (C ) | (D) | (E=A+C) | (F) | (G) | (H) | (I=G/H) | (J=K-H) | (K=A+C+D) | (M=G-F) | (N=G-H) | (O=F/E) | (P=G/E) | (Q=G/K)
Code Discipline Description | A |  | B | C | D=A+B | E | F | G | H=F/G | I=J-G | J=A+B+C | K=F-E | M=F-G | N=E/D | O=F/D | P=F/J
D Area D - Facilities
Architectural | 365 | 365 |  |  | 365 | 250 | 254 | 153 | 1.6601 | 212 | 365 | 4 | 101 | 68.4932 | 69.589 | 69.589
Eng'rg Management | 7717 | 7717 | 0 | 160 | 7717 | 1233 | 1233 | 1167 | 1.0566 | 6710 | 7877 | 0 | 66 | 15.9777 | 15.9777 | 15.6532
Civil | 13909 | 14134 | 225 | 0 | 14134 | 11009 | 10856 | 7011 | 1.5484 | 7123 | 14134 | -153 | 3845 | 77.8902 | 76.8077 | 76.8077
Electrical | 3485 | 3485 |  |  | 3485 | 2815 | 2862 | 2952 | 0.96951 | 533 | 3485 | 47 | -90 | 80.7747 | 82.1234 | 82.1234
General | 1370 | 1370 |  |  | 1370 | 1091 | 988 | 781 | 1.265 | 589 | 1370 | -103 | 207 | 79.635 | 72.1168 | 72.1168
Instrumentation | 898 | 898 |  |  | 898 | 677 | 616 | 186 | 3.3118 | 712 | 898 | -61 | 430 | 75.3898 | 68.5969 | 68.5969
Mechanical | 1252 | 1552 | 300 | 0 | 1552 | 940 | 982 | 337 | 2.9139 | 1215 | 1552 | 42 | 645 | 60.567 | 63.2732 | 63.2732
Structural | 1650 | 1650 |  |  | 1650 | 1255 | 1179 | 841 | 1.4019 | 809 | 1650 | -76 | 338 | 76.0606 | 71.4545 | 71.4545
Area D Total | 30646 | 31171 | 525 | 160 | 31171 | 19270 | 18970 | 13428 | 1.4127 | 17903 | 31331 | -300 | 5542 | 61.8203 | 60.8578 | 60.5471
| BUDGET |  |  |  |  | EARNED |  |  |  | FORECAST |  | VARIANCE |  | PERCENT COMPLETE
| Original Budget |  | Scope Change | Trends | Current Budget | Schedule Earned | Actual Earned | Actual Hrs | To Date Perf | To Go Fct | Total Fct | Sched Var | Cost Var | Sched (Bud) | Actual (Bgt) | Actual (Fct)
| (A) | (B) | (C ) | (D) | (E=A+C) | (F) | (G) | (H) | (I=G/H) | (J=K-H) | (K=A+C+D) | (M=G-F) | (N=G-H) | (O=F/E) | (P=G/E) | (Q=G/K)
Code Discipline Description | A |  | B | C | D=A+B | E | F | G | H=F/G | I=J-G | J=A+B+C | K=F-E | M=F-G | N=E/D | O=F/D | P=F/J
D Area D - Facilities
Architectural | 365 | 365 |  |  | 365 | 250 | 254 | 153 | 1.6601 | 212 | 365 | 4 | 101 | 68.4932 | 69.589 | 69.589
Eng'rg Management | 7717 | 7717 | 0 | 160 | 7717 | 1233 | 1233 | 1167 | 1.0566 | 6710 | 7877 | 0 | 66 | 15.9777 | 15.9777 | 15.6532
Civil | 13909 | 14134 | 225 | 0 | 14134 | 11009 | 10856 | 7011 | 1.5484 | 7123 | 14134 | -153 | 3845 | 77.8902 | 76.8077 | 76.8077
Electrical | 3485 | 3485 |  |  | 3485 | 2815 | 2862 | 2952 | 0.96951 | 533 | 3485 | 47 | -90 | 80.7747 | 82.1234 | 82.1234
General | 1370 | 1370 |  |  | 1370 | 1091 | 988 | 781 | 1.265 | 589 | 1370 | -103 | 207 | 79.635 | 72.1168 | 72.1168
Instrumentation | 898 | 898 |  |  | 898 | 677 | 616 | 186 | 3.3118 | 712 | 898 | -61 | 430 | 75.3898 | 68.5969 | 68.5969
Mechanical | 1252 | 1552 | 300 | 0 | 1552 | 940 | 982 | 337 | 2.9139 | 1215 | 1552 | 42 | 645 | 60.567 | 63.2732 | 63.2732
Structural | 1650 | 1650 |  |  | 1650 | 1255 | 1179 | 841 | 1.4019 | 809 | 1650 | -76 | 338 | 76.0606 | 71.4545 | 71.4545
Area D Total | 30646 | 31171 | 525 | 160 | 31171 | 19270 | 18970 | 13428 | 1.4127 | 17903 | 31331 | -300 | 5542 | 61.8203 | 60.8578 | 60.5471

## Tracker Set-up
LOG ID | DOCUMENT TYPE
Log D1T | Process Systems Drawings Log | [8 empty] | BUDGET F/C | TO GO | % COMP. | EARNED BUDGET
Activity Txxx - Drawings (Type 1) | AREA | Start CADD | IFR | IFA | IFH | IFD | IFC | Database Complete | Revisions Complete
|  | 5% | 20% | 30% | 50% | 60% | 80% | 90% | 100%
Drawing # 1, Unit 1 | S - Location 1
F - Location 1
A - Location 1
Drawing # 2, Unit 1 | S - Home Office
F - Home Office
A - Home Office
Subtotal for Activity Txxx | S - Location 1
F - Location 1
A - Location 1
S - Home Office
F - Home Office
A - Home Office
Activity Tzzz - Drawings (Type 1) | AREA | Start CADD | IFR | IFA | IFH | IFD | IFC | Database Complete | Revisions Complete
|  | 5% | 20% | 30% | 50% | 60% | 80% | 90% | 100%
Drawing # 1, Unit 1 | S - Location 1
F - Location 1
A - Location 1
Drawing # 2, Unit 1 | S - Home Office
F - Home Office
A - Home Office
Subtotal for Activity Tzzz | S - Location 1
F - Location 1
A - Location 1
S - Home Office
F - Home Office
A - Home Office
LOG ID | DOCUMENT TYPE
Log HAS | Process Systems Drawings Log | [8 empty] | BUDGET F/C | TO GO | % COMP. | EARNED BUDGET
Activity T@@@ - Drawings (Type 2) | AREA | Start CADD | IFR | IFA | IFH | IFD | Revisions Complete
|  | 5% | 30% | 50% | 70% | 90% | 100%
Drawing # 1, Unit 1 | S - Location 1
F - Location 1
A - Location 1
Drawing # 2, Unit 1 | S - Home Office
F - Home Office
A - Home Office
Subtotal for Activity T@@@ | S - Location 1
F - Location 1
A - Location 1
S - Home Office
F - Home Office
A - Home Office
Activity T### - Drawings (Type 2) | AREA | Start CADD | IFR | IFA | IFH | IFD | Revisions Complete
|  | 5% | 30% | 50% | 70% | 90% | 100%
Drawing # 1, Unit 1 | S - Location 1
F - Location 1
A - Location 1
Drawing # 2, Unit 1 | S - Home Office
F - Home Office
A - Home Office
Subtotal for Activity T### | S - Location 1
F - Location 1
A - Location 1
S - Home Office
F - Home Office
A - Home Office
LOG ID | DOCUMENT TYPE
Log CT | Process Systems Calculations | [8 empty] | BUDGET F/C | TO GO | % COMP. | EARNED BUDGET
Activity T+++ - Calculation | AREA | Start | IFR | IFA/IFQ | IFP/IFC | Vendor Print Code 1/4#
|  | 5% | 30% | 50% | 90% | 100%
Calculation # 1 | S - Location 1
F - Location 1
A - Location 1
Calculation # 2 | S - Home Office
F - Home Office
A - Home Office
Subtotal for Activity T+++ | S - Location 1
F - Location 1
A - Location 1
S - Home Office
F - Home Office
A - Home Office
LOG ID | DOCUMENT TYPE
Log TT | Process Systems Tasks | [8 empty] | BUDGET F/C | TO GO | % COMP. | EARNED BUDGET
Activity T$$$ - Supervision | AREA | 0% | 20% | 40% | 60% | 80% | 100%
Engineering Discipline Lead | S - Location 1
F - Location 1
A - Location 1
Engineering Discipline Lead | S - Home Office
F - Home Office
A - Home Office
Subtotal for Activity T$$$ | S - Location 1
F - Location 1
A - Location 1
S - Home Office
F - Home Office
A - Home Office